## Work List
Exported on: 2026-09-21 05:32:54
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: GONDALWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BANKHEDI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1732007011/DP/22012034597737 — Vasudha vandan vatika school parisar gram baniyakhedi GP gondalwada | Ongoing | 55847.4 | 0 | 2023-10-06
BANKHEDI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1732007011/IF/22012034433149 — braxaropan sevdayal,kamlesh ramdash | Ongoing | 189000 | 0 | 2018-09-24
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732007011/IF/22012035606056 — ek bagiya maa ke nam halki bai baniyakhedi | Approved | 0 | 0 | 2025-08-16
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732007011/IF/22012035651373 — Ek bagiya Man ke naam Munni Bai / ramdayal | Approved | 175106.21 | 0 | 2025-12-12
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/3657935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146082845 | Ongoing | 27000 | 4200 | 2026-05-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/3727877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106325039 | Ongoing | 27000 | 0 | 2025-12-30
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/3745134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118178809 | Ongoing | 27000 | 0 | 2025-10-07
BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/4569444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116582812 | Ongoing | 27000 | 0 | 2024-11-26
BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/4570277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116606488 | Ongoing | 27000 | 0 | 2024-10-01
BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/4578141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118109030 | Completed | 23490 | 0 | 2024-11-26 | 2026-08-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/4862444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102104759 | Ongoing | 27000 | 0 | 2025-08-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/4862887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116563132 | Ongoing | 27000 | 0 | 2025-04-01
BANKHEDI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5246765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118136369 | Approved | 27000 | 0 | 2025-03-26
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5251044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116683571 | Completed | 23490 | 0 | 2025-08-19 | 2026-08-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5260356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117438628 | Ongoing | 27000 | 0 | 2025-08-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5270099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118182479 | Completed | 23490 | 0 | 2025-09-09 | 2026-08-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5279529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118136515 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5284503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118145512 | Ongoing | 27000 | 0 | 2025-11-11
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5297924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116563203 | Ongoing | 27000 | 0 | 2025-08-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5308850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116725820 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5311585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106174498 | Ongoing | 27000 | 0 | 2025-08-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5324287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114162391 | Ongoing | 27000 | 0 | 2025-08-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5326855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146848405 | Ongoing | 27000 | 0 | 2025-08-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5342961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118187912 | Ongoing | 27000 | 0 | 2025-08-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5484176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118153484 | Approved | 27000 | 0 | 2025-04-03
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5484525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114162937 | Ongoing | 27000 | 0 | 2025-09-30
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5485484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117122263 | Ongoing | 27000 | 0 | 2025-09-09
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5485765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142777514 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5485854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116610200 | Ongoing | 27000 | 0 | 2025-08-26
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5684822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117135877 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114028420 | Completed | 23490 | 0 | 2025-10-07 | 2026-08-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117866305 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118135767 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105314566 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118182194 | Ongoing | 27000 | 2100 | 2026-05-19
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105309319 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116584534 | Ongoing | 27000 | 0 | 2025-10-07
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113896303 | Completed | 23490 | 0 | 2025-11-04 | 2026-08-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116582721 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100987583 | Approved | 27000 | 0 | 2025-05-20
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142777716 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142778235 | Completed | 23490 | 0 | 2025-12-16 | 2026-08-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142778629 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114162467 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5816968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106324909 | Ongoing | 27000 | 0 | 2025-11-04
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5870561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116683739 | Ongoing | 27000 | 0 | 2026-08-11
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5882449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142778097 | Ongoing | 27000 | 0 | 2026-02-24
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5882457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118190262 | Ongoing | 27000 | 0 | 2026-02-24
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5882463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116600716 | Physically Completed | 23490 | 0 | 2026-02-24 | 2026-08-16
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5882465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118176613 | Completed | 23490 | 0 | 2026-02-24 | 2026-08-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5882473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142778769 | Ongoing | 27000 | 0 | 2026-02-24
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5882525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116584626 | Ongoing | 27000 | 0 | 2026-02-24
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5904991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117776568 | Approved | 27000 | 0 | 2026-02-10
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5905871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117450546 | Ongoing | 27000 | 0 | 2026-08-11
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5905920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124734928 | Approved | 27000 | 0 | 2026-02-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5908409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116602430 | Approved | 27000 | 0 | 2026-02-10
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5908883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114028961 | Ongoing | 27000 | 2100 | 2026-05-19
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5911713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105310454 | Ongoing | 27000 | 0 | 2026-06-02
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5913371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116688936 | Ongoing | 27000 | 0 | 2026-08-11
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5913388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117138431 | Approved | 27000 | 0 | 2026-02-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5918122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117791963 | Approved | 27000 | 0 | 2026-02-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5919341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117121222 | Approved | 27000 | 0 | 2026-02-10
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5920219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117429639 | Ongoing | 27000 | 0 | 2026-08-11
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5920408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117256316 | Approved | 27000 | 0 | 2026-02-11
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5921591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118288812 | Ongoing | 27000 | 0 | 2026-05-19
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5924015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118291973 | Ongoing | 27000 | 2100 | 2026-08-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/5929438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117910978 | Approved | 27000 | 0 | 2026-02-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/6068017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105311495 | Approved | 27000 | 0 | 2026-02-16
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/6074829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116672617 | Ongoing | 27000 | 0 | 2026-07-21
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/6219300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116611688 | Approved | 27000 | 0 | 2025-04-03
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732007011/IF/IAY/6376841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116664940 | Approved | 27000 | 0 | 2026-07-10
BANKHEDI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1732007011/LD/22012034942181 — Vruksharopan CSC parisar ke pass gram baniya khedi | New | 0 | 0 | 2024-06-29
BANKHEDI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732007011/WC/22012035149821 — जल क्षमता विस्तारीकरण | Ongoing | 456343 | 0 | 2024-01-12
BANKHEDI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1732007011/WC/22012035194727 — Khet talab nirman rameshchand/kishori | Ongoing | 259881.12 | 0 | 2024-03-16