## Work List
Exported on: 2026-10-23 15:44:36
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: SEMKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BANKHEDI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1732007050/AV/22012034663017 — Puliya Nirman kary Kherapati Mandir ke Samne | New | 0 | 0 | 2024-12-24
BANKHEDI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1732007050/IF/22012034847937 — nandanfaludhan kosha bai/ nanhelal gram semkheda | Ongoing | 144199.83 | 0 | 2021-09-08
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732007050/IF/22012035351393 — khet talab nirman shersingh / hariram gram patha | New | 0 | 0 | 2025-04-14
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732007050/IF/22012035351479 — KHET TALAB NIRMAN SHERSINGH / HARIRAM GRAM PATHA | Approved | 0 | 0 | 2025-04-14
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732007050/IF/22012035383697 — KHET TALAB NIRMAN SHASHI BAI/NARAYAN GRAM PATHA | New | 0 | 0 | 2025-04-14
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732007050/IF/22012035383755 — KHET TALAB BHAGAT SINGH /JAWAHARLAL GRAM PATHA | Approved | 147621.16 | 0 | 2025-04-14
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732007050/IF/22012035610535 — ak bagiya ma ke nam jankibai choudhary122822602 | Approved | 170229.08 | 0 | 2025-08-16
BANKHEDI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/105185 — Construction of IAY House -IAY REG. NO. MP-32-007-050-001/76 | Approved | 27000 | 0 | 2015-10-08
BANKHEDI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/3661830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115781764 | Ongoing | 27000 | 0 | 2023-08-26
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5147067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115795566 | Ongoing | 27000 | 0 | 2025-04-09
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5167985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115798248 | Ongoing | 27000 | 0 | 2025-04-09
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5168666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120764760 | Ongoing | 27000 | 6300 | 2025-04-09
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5203378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117663710 | Ongoing | 27000 | 0 | 2025-04-09
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5221071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117808510 | Physically Completed | 27000 | 0 | 2025-04-09 | 2026-09-06
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5235992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117771121 | Ongoing | 27000 | 0 | 2025-05-21
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5238119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115405164 | Ongoing | 27000 | 0 | 2025-04-09
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5903420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117673376 | Physically Completed | 27000 | 0 | 2026-03-18 | 2026-09-13
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5904008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115795761 | Ongoing | 27000 | 0 | 2026-04-22
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5904307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126212694 | Ongoing | 27000 | 10800 | 2026-04-22
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5904435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115791194 | Ongoing | 27000 | 8400 | 2026-04-15
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5905245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126426188 | Ongoing | 27000 | 25200 | 2026-07-08
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5906120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120767789 | Approved | 27000 | 0 | 2026-02-04
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5906704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146944843 | Completed | 23490 | 0 | 2026-02-25 | 2026-08-11
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5907340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115785698 | Ongoing | 27000 | 8400 | 2026-02-25
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5907702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117781540 | Ongoing | 27000 | 2100 | 2026-05-13
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5908643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120768455 | Ongoing | 27000 | 12600 | 2026-09-02
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5908825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115385688 | Approved | 27000 | 0 | 2026-02-04
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5909171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123890065 | Ongoing | 27000 | 12600 | 2026-08-28
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5909662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120768115 | Ongoing | 27000 | 12600 | 2026-09-09
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5913954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124178147 | Ongoing | 27000 | 0 | 2026-03-18
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5914107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120768235 | Approved | 27000 | 0 | 2026-02-04
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5918969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114866957 | Ongoing | 27000 | 6300 | 2026-06-10
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5918992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115407238 | Ongoing | 27000 | 14700 | 2026-09-02
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5920273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149571556 | Ongoing | 27000 | 4200 | 2026-05-06
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5920510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146153734 | Ongoing | 27000 | 6300 | 2026-04-15
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5921402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115379248 | Ongoing | 27000 | 23100 | 2026-07-08
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5922313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117253253 | Ongoing | 27000 | 0 | 2026-03-18
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5924210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149569489 | Ongoing | 27000 | 12600 | 2026-09-02
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5924519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115664640 | Ongoing | 27000 | 21000 | 2026-07-08
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5925806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120768282 | Ongoing | 27000 | 0 | 2026-06-10
BANKHEDI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/5927026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115798812 | Approved | 27000 | 0 | 2026-02-04
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/6073275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115799268 | Ongoing | 27000 | 18900 | 2026-05-06
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/6097889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146942569 | Physically Completed | 23490 | 5200 | 2026-04-15 | 2026-08-02
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/6100093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149669019 | Ongoing | 27000 | 0 | 2026-05-06
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/6100097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149672468 | Ongoing | 27000 | 12600 | 2026-05-06
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/6175486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146152198 | Ongoing | 27000 | 10500 | 2026-09-09
BANKHEDI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/6219078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115353756 | Completed | 23490 | 0 | 2026-05-01 | 2026-08-11
BANKHEDI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732007050/IF/IAY/974803 — Construction of IAY House -IAY REG. NO. MP3677053 | Approved | 27000 | 0 | 2017-04-01
BANKHEDI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732007050/RC/22012034851017 — Pradhanmantri road se kamlesh thakur ke makan ki or semkheda | Ongoing | 48000 | 0 | 2026-02-18