## Work List
Exported on: 2026-10-27 03:36:38
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: PRATAPPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SIHORA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1733001043/AV/22012034375145 — Aanganbadi bhavan nirman pratappur no2 | Ongoing | 180000 | 0 | 2019-04-11
SIHORA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1733001043/DP/22012034621099 — plantetion work bhikhakheda shantidham k pass | Approved | 417325.18 | 0 | 2024-04-01
SIHORA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1733001043/DP/22012034625920 — plantetion work shantidham pratappur | Approved | 477625.26 | 0 | 2024-04-01
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733001043/IF/22012035543639 — khet talab nirman manish kumar /bal krishan | Ongoing | 450885.64 | 0 | 2025-06-06
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733001043/IF/22012035553121 — khet talab nirman putto bai/uma/govind | Approved | 450885.64 | 0 | 2025-04-01
SIHORA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/121373 — Construction of IAY House -IAY REG. NO. MP-33-001-043-002/12A | Approved | 27000 | 0 | 2016-01-21
SIHORA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/132604 — Construction of IAY House -IAY REG. NO. MP-33-001-043-002/57A | Approved | 27000 | 0 | 2016-01-15
SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/1733970 — Construction of IAY House -IAY REG. NO. MP3161197 | Approved | 27000 | 0 | 2018-04-20
SIHORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/1865385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1805640 | Ongoing | 27000 | 0 | 2018-08-29
SIHORA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/205742 — Construction of IAY House -IAY REG. NO. MP-33-001-043-002/269 | Approved | 27000 | 0 | 2016-03-31
SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/2234503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1806161 | Ongoing | 27000 | 0 | 2019-12-13
SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/2234889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1859584 | Ongoing | 27000 | 0 | 2019-11-11
SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/2235166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2179821 | Ongoing | 27000 | 0 | 2019-11-11
SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/2239415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1795196 | Approved | 27000 | 0 | 2019-07-09
SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/2270280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1973471 | Approved | 27000 | 0 | 2019-07-18
SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/2279380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2181449 | Approved | 27000 | 0 | 2019-07-23
SIHORA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/3289167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3086666 | Ongoing | 27000 | 0 | 2022-03-09
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/3722425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120991425 | Ongoing | 27000 | 0 | 2025-03-24
SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/3917231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127942821 | Ongoing | 27000 | 0 | 2022-08-08
SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/4164032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123483383 | Approved | 27000 | 0 | 2022-05-26
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/4583936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119281147 | Ongoing | 27000 | 0 | 2025-11-01
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/4622803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127153499 | Ongoing | 27000 | 0 | 2024-10-18
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/4771068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124803160 | Ongoing | 27000 | 0 | 2024-11-17
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5174246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127255809 | Ongoing | 27000 | 0 | 2026-01-27
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5222891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120366603 | Ongoing | 27000 | 0 | 2025-05-03
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5231197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118849867 | Physically Completed | 27000 | 0 | 2025-09-20 | 2026-10-04
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5240185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127928138 | Approved | 27000 | 0 | 2025-03-09
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5377093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127319248 | Ongoing | 27000 | 0 | 2025-05-21
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5380882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120366492 | Physically Completed | 27000 | 3600 | 2025-11-14 | 2026-09-27
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5523045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120992203 | Ongoing | 27000 | 4200 | 2025-07-23
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5634532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127199811 | Ongoing | 27000 | 0 | 2025-07-29
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5636473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127926463 | Physically Completed | 27000 | 0 | 2025-07-23 | 2026-09-27
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5787200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123525155 | Approved | 27000 | 0 | 2025-03-20
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5787264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120992864 | Approved | 27000 | 0 | 2025-03-09
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5787265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120994789 | Approved | 27000 | 0 | 2025-03-28
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5787689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120993303 | Ongoing | 27000 | 0 | 2026-09-19
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5787726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120278505 | Ongoing | 27000 | 0 | 2026-10-13
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5787911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116477275 | Ongoing | 27000 | 0 | 2025-09-04
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5788088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127146642 | Physically Completed | 27000 | 0 | 2025-09-24 | 2026-10-04
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5788199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119575341 | Approved | 27000 | 0 | 2025-04-23
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001043/IF/IAY/5789673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118843134 | Ongoing | 27000 | 0 | 2025-11-01
SIHORA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1733001043/RC/22012034840645 — main road nahar k pass se nipaniya tak | Approved | 0 | 0 | 2025-01-26
SIHORA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1733001043/RC/22012034840646 — main road nahar k pass se nipaniya tak | Ongoing | 1337000 | 0 | 2025-05-03
SIHORA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1733001043/RS/22012034517112 — Community sanitary complex Pratappur | Ongoing | 75000 | 0 | 2021-09-16