## Work List
Exported on: 2026-10-26 11:31:49
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: GUNHARU
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SIHORA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733001021/IF/IAY/202089 — Construction of IAY House -IAY REG. NO. MP-33-001-021-003/29 | Approved | 27000 | 0 | 2015-12-14
SIHORA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Plantation in Institutions for Community | Plantation | 1733001060/DP/22012034620704 — Community plantation shantidham parisar me gram gunheru GP gunheru | Ongoing | 453563.17 | 0 | 2024-07-15
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733001060/IF/22012035527960 — JGSA_khet talab nirman kandhi lal Dahiya/ Vishnu urf shukla | Ongoing | 147621.16 | 0 | 2025-05-19
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733001060/IF/22012035599097 — EK BAGIYA MAA KE NAAM HITGRAHI DEVKI BAI | Ongoing | 283815.85 | 0 | 2025-09-01
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733001060/IF/22012035604039 — Ek bagiya maa ke nam DEVKI BAI Gunharu | New | 0 | 0 | 2025-08-15
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733001060/IF/22012035627089 — EK BAGIYA MAA KE NAAM gauri bai | Approved | 154091.94 | 0 | 2025-08-01
SIHORA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/1886536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3447695 | Ongoing | 27000 | 0 | 2019-04-10
SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/4173718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116698111 | Ongoing | 27000 | 0 | 2022-06-21
SIHORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/4400365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117299855 | Approved | 27000 | 0 | 2022-09-19
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/4694713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116333971 | Ongoing | 27000 | 0 | 2025-03-08
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5776757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116735477 | Ongoing | 27000 | 0 | 2025-08-29
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5776792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116750351 | Ongoing | 27000 | 15600 | 2025-08-29
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5776998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120603541 | Ongoing | 27000 | 0 | 2025-09-19
SIHORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5777693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121642478 | Approved | 27000 | 0 | 2025-03-21
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5778511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116725432 | Ongoing | 27000 | 0 | 2025-08-29
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5779270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122016553 | Ongoing | 27000 | 12300 | 2026-02-13
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5819233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120854125 | Ongoing | 27000 | 2100 | 2025-09-24
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/5819420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122009913 | Ongoing | 27000 | 0 | 2025-09-24
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6074893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116719328 | Ongoing | 27000 | 0 | 2026-09-17
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6075650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117291890 | Ongoing | 27000 | 0 | 2026-05-27
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121991977 | Approved | 27000 | 0 | 2026-02-18
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117612905 | Ongoing | 27000 | 0 | 2026-10-10
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120865809 | Approved | 27000 | 0 | 2026-02-25
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120819197 | Approved | 27000 | 0 | 2026-02-28
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120301795 | Ongoing | 27000 | 0 | 2026-10-10
SIHORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117497420 | Approved | 27000 | 0 | 2026-02-25
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122023119 | Ongoing | 27000 | 0 | 2026-10-10
SIHORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/6356915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116722678 | Ongoing | 27000 | 0 | 2026-10-14
SIHORA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1733001060/IF/IAY/640335 — Construction of IAY House -IAY REG. NO. MP1009840 | Ongoing | 27000 | 0 | 2017-10-31
SIHORA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1733001060/WC/22012034442863 — R.R.F- gabion structure2nos-bah nala | Ongoing | 180000 | 0 | 2019-03-14
SIHORA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1733001060/WC/22012034442866 — R..F.R.-gabion structure-4 no-bah nalla/kanadi | Ongoing | 180000 | 0 | 2019-03-14