## Work List
Exported on: 2026-09-06 19:14:50
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: KHABRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733002075/IF/22012035515035 — Khet Talab - Bhure Lal/Balkishan | New | 0 | 0 | 2025-04-14
MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1733002075/IF/22012035563374 — Khet Talab - Bhure Lal / Balkishan Mehra | New | 0 | 0 | 2025-05-14
MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733002075/IF/22012035621765 — Ek Bagiya Maa Ke naam - Sunita Gram-Khabra | Ongoing | 270537.6 | 0 | 2025-12-05
MAJHOULI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/1726305 — Construction of IAY House -IAY REG. NO. MP1817852 | Ongoing | 27000 | 0 | 2018-07-02
MAJHOULI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/3306606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1346935 | Approved | 27000 | 0 | 2021-10-31
MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/4565101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116429140 | Ongoing | 27000 | 0 | 2024-10-05
MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/4743240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113868566 | Ongoing | 27000 | 0 | 2025-03-16
MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/4819538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113846233 | Completed | 23490 | 0 | 2025-03-18 | 2026-07-27
MAJHOULI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/4819959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113927980 | Ongoing | 27000 | 0 | 2025-03-15
MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/5127388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113685282 | Physically Completed | 23490 | 0 | 2025-04-08 | 2026-08-02
MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/5135034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128514785 | Ongoing | 27000 | 0 | 2025-06-19
MAJHOULI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/5463889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123407246 | Ongoing | 27000 | 1820 | 2025-07-17
MAJHOULI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/634719 — Construction of IAY House -IAY REG. NO. MP1286059 | Ongoing | 27000 | 0 | 2018-07-17
MAJHOULI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/839202 — Construction of IAY House -IAY REG. NO. MP1346953 | Ongoing | 27000 | 0 | 2017-05-27
MAJHOULI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733002075/IF/IAY/954346 — Construction of IAY House -IAY REG. NO. MP3155713 | Ongoing | 27000 | 0 | 2017-09-19
MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1733002075/WC/22012035173449 — Naveen Tabal Nirman Dhanadi | Ongoing | 2289038.14 | 0 | 2024-06-20
MAJHOULI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002075/WC/22012035254124 — Cantoor Trench - Bhadkura ke Paas 24-25 | Ongoing | 740550.95 | 0 | 2025-05-23
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002075/WC/22012035254136 — Cantoor Trench - Malkhan ke khet ke paas Dhanadi 24-25 | Ongoing | 710360.25 | 0 | 2026-08-24
MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733002075/WC/22012035254139 — Pond - Shantidham ke paas Khabra 24-25 | Approved | 0 | 0 | 2024-08-15
MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733002075/WC/22012035254142 — Pond - Atthi ke khet ke paas Dhanadi 24-25 | Approved | 0 | 0 | 2024-08-15
MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1733002075/WC/22012035255165 — Percolation Tank - Biriya Bhatiya Ke paas 25-26 | Approved | 0 | 0 | 2024-08-15
MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1733002075/WC/22012035255166 — Percolation Tank - Dhanadi Khasra No 149 25-26 | Approved | 0 | 0 | 2024-08-15
MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1733002075/WC/22012035255168 — Percolation Tank - Dhanadi Khasra No 151 25-26 | Approved | 0 | 0 | 2024-08-15
MAJHOULI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1733002075/WC/22012035255171 — Pond - Atthi ke khet ke paas Dhanadi 25-26 | Approved | 0 | 0 | 2024-08-15
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035329847 — Cantoor tranch kher mai ke paas dhanadi | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330448 — cantoor tranch shaskiya narshari ke pass dhanadi | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330452 — cantoor tranch cantoor tranch naveen talab ke paas dhanadi | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330454 — cantoor tranch irrigation tank ke paas dhanadi | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330458 — cantoor tranch khandiya ke paas | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330460 — cantoor tranch malkhan ke khet ke paas | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330488 — cantoor tranch bade nale ke paas dhanadi | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330491 — cantoor tranch kulaha hill side | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330493 — cantoor tranch bade nalaa kae paas dhanadi | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035330494 — cantoor tranch khandiya bhatiya ke paaas dhanadi | Approved | 0 | 0 | 2026-07-30
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035331291 — cantoor tranch bade nala ke paas bhadkura | Approved | 0 | 0 | 2026-08-03
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1733002075/WC/VB/22012035331294 — check dem nirman viriya bhatiya ke kinare | New | 0 | 0 | 2026-08-03
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035331301 — CANTOOR TRANCH KATANGI MARG KINARE GRAM DHANADI | Approved | 0 | 0 | 2026-08-03
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035331303 — CANTOOR TRANCH KHERHAU KE KINARE DHANADI | Approved | 0 | 0 | 2026-08-03
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035331304 — CANTTOR TARANCH GRAM DHONDA KI OR DHANADI | Approved | 0 | 0 | 2026-08-01
MAJHOULI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1733002075/WC/VB/22012035331306 — CANTOOR TRANCH BHADKHURA KI OR DHANADI | Approved | 0 | 0 | 2026-08-03