## Work List
Exported on: 2026-09-15 12:50:41
Filters applied:
Data source: MGNREGA
District: JABALPUR
Block: All
Panchayat: JARAUND
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PATAN | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 173300306903001 — जरोंद से रिछाई पंहुच मार्ग मुरकीकरण | Completed | 829000 | 493459.94 | 2008-06-03 | 2012-02-15
PATAN | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733003069/AV/22012034374782 — आंगनवाड़ी भवन बाउन वाल हैंड पंप निर्माण कार्या ग्राम jaraund | Completed | 180000 | 148402 | 2018-09-18 | 2024-09-18
PATAN | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/AV/22012034400004 — CC Road & Naali nirman 14th Vitt 2019 | Deleted | 0 | 0 | 2019-01-26
PATAN | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Village/Rural Haat for community / Construction of Village/Rural Haat for community | Construction of Village Haats | 1733003069/AV/22012034539684 — Construction Of Dhan/Gehun Uparjan Kendra Platform-Jaraun-2021 | Closed | 0 | 0 | 2020-08-15
PATAN | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1733003069/AV/22012034585174 — Dining arrangement in GMS Jaraund | Closed | 0 | 0 | 2021-07-01
PATAN | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1733003069/AV/22012034600411 — Saskiya Prathamik Shala Parisar Me baundrywall Nirmand Karya Gram jarond | Completed | 53000 | 52422 | 2021-10-12 | 2023-12-26
PATAN | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1733003069/AV/22012034601845 — Saskiya Prathamik Shala Parisar Me baundrywall Nirmand Karya Gram jarond | Deleted | 0 | 0 | 2021-08-15
PATAN | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1733003069/AV/22012034614492 — Baundrywall Nirmand Karya Shaskiy Prathamik Shala Parisar Gram Jarond | Closed | 25000 | 0 | 2021-10-02
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1733003069/AV/22012034645992 — किचिन भवन की वाटर प्रूफिंग कार्य जरोंद | Completed | 6000 | 5916 | 2023-10-04 | 2024-02-02
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1733003069/AV/22012034645993 — किचिन भवन की वाटर प्रूफिंग कार्य जरोंद | Closed | 0 | 0 | 2023-08-15
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1733003069/AV/22012034645994 — शा. प्रा.भवन छत की वाटर प्रूफिंग कार्य जरोंद | Completed | 10000 | 9704 | 2023-10-04 | 2024-02-02
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733003069/AV/22012034653793 — SHANTIDHAM UNYAN AVAM SHED NIRMAN KARYA JARAUND | Ongoing | 248547.06 | 162920.32 | 2024-03-05
PATAN | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733003069/DP/22012034423000 — Vraksha ropan karya khel maiden ke baju me sashkiya bhumi par | Closed | 342540 | 0 | 2018-04-14
PATAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1733003069/DP/22012034582226 — PODHAROPAN KARYA ROAD SIDES GRAM JAROND PMGSY MARG SE MAIN ROAD KI OR JAROND | Closed | 435815.48 | 0 | 2023-04-14
PATAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1733003069/DP/22012034591392 — AMARAT VATIKA GP BHAVAN AVM SAMUDAYAK BHAVAN KE SAMIP JARAUND | Ongoing | 55847.4 | 4584 | 2023-09-08
PATAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733003069/DP/22012034618593 — COMMUNITY PLANTATION WORK GRAM JAROND NEAR DUNDI ROAD PART ONE | Ongoing | 1498947.68 | 43001.72 | 2024-07-15
PATAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1733003069/DP/22012034619176 — COMMUNITY PLANTATION WORK GRAM JAROND NEAR NEW POND DUNDI ROAD PART TWO | Approved | 899392.51 | 0 | 2024-06-09
PATAN | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1733003069/DP/46 — जरोंद से डूडी मार्ग पर जेटोपा कार्य वंक्षारोपण | Completed | 0 | 5996 | 2011-08-29 | 2012-07-13
PATAN | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1733003069/FP/211 — नाला विस्‍तारीकरण कार्य जरौद | Completed | 0 | 103572 | 2011-05-31 | 2014-07-30
PATAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Renovation of sub-minor Canal for Community / Renovation of sub-minor Canal for Community | Renovation of Canal | 1733003069/IC/22012034387822 — for jungle clearance and slipped earh removal from canal bed raising of BARODA MIN RD0.25TO1.8KM | Completed | 231825.16 | 75240 | 2021-04-28 | 2021-08-08
PATAN | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003069/IF/22012034347878 — वृक्षारोपण शान्तिधाम जरोंद | Completed | 335000 | 29384 | 2017-06-08 | 2026-02-01
PATAN | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003069/IF/22012034354019 — बृक्षारोपण कार्य सार्वजानिक स्थल में ग्राम जरोंद | Completed | 335000 | 134042 | 2017-06-22 | 2023-09-01
PATAN | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034472177 — med badhan karya ramdayal ke khet me | Completed | 33000 | 12324 | 2019-03-08 | 2020-07-17
PATAN | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034472180 — med badhan karya suresh ke khet me | Completed | 23000 | 9648 | 2019-03-08 | 2020-07-17
PATAN | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034540244 — med badhan karya kallu / mohan bpl laghu kishan | Deleted | 0 | 0 | 2020-01-26
PATAN | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034540245 — med badhan karya gajraj/chhidiya bpl st laghu kishan | Deleted | 0 | 0 | 2020-01-26
PATAN | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034540246 — med badhan karya anand / kanchedi laghu kishan | Deleted | 0 | 0 | 2020-01-26
PATAN | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034540247 — med badhan karya jeevan/chhidiya bpl laghu kishan | Deleted | 0 | 0 | 2020-01-26
PATAN | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034540248 — med badhan karya pradeep/anandi laghu kishan | Deleted | 0 | 0 | 2020-01-26
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034551052 — med badhan karya kallu /mohan bpl laghu kishan | Completed | 24105.07 | 17028 | 2020-05-17 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034551053 — med badhan karya gajraj /chhidiya lal laghu kishan | Completed | 34362.53 | 26220 | 2020-05-17 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034551055 — med badhan karya anand lal laghu kishan | Closed | 17950.59 | 0 | 2020-04-14
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034551056 — med badhan karya pradeep /anadi lal laghu kishan | Closed | 35388.28 | 0 | 2020-04-14
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034551058 — med badhan karya ram kishan lal laghu kishan | Completed | 27182.31 | 18620 | 2020-05-10 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034551279 — med badhan karya long bai /jagdish laghu kishan | Completed | 35901.11 | 19498 | 2020-05-10 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034556292 — med badhan karya munnu/ babu lal laghu kishan | Completed | 30772.37 | 22560 | 2020-05-26 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034556293 — med badhan karya krashankant/madan gopal laghu kishan | Completed | 23592.16 | 18620 | 2020-05-18 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034557237 — med badhan karya jeevan/chhidiya laghu kishan | Completed | 35388.28 | 24420 | 2020-05-26 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034557238 — med badhan karya kodi lal/halke laghu kishan | Completed | 30054.4 | 19914 | 2020-05-26 | 2021-08-08
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034557239 — med badhan karya sukhchan /sarju laghu kishan | Completed | 29746.63 | 23955 | 2020-05-25 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034560513 — med badhan karyamaya bai ke khet me laghu kishan | Completed | 24617.91 | 18048 | 2020-06-02 | 2020-07-17
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1733003069/IF/22012034560965 — med badhan karya jeevan/chhidiya bai laghu kishan | Deleted | 0 | 0 | 2020-04-14
PATAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1733003069/IF/22012034563906 — med badhan karya ramesh/chhote lal laghu kishan | Completed | 18976.33 | 13912 | 2020-06-09 | 2020-07-17
PATAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733003069/IF/22012034761850 — ctr medbadhan-mamta bai w/o rishiram | Completed | 19953.1 | 1140 | 2021-06-10 | 2026-01-29
PATAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733003069/IF/22012034768546 — मेड बंधान कार्य -राधाबाई/बेनीप्रसाद डूडी | Closed | 0 | 0 | 2021-04-14
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733003069/IF/22012035602590 — Ek bagiya Maa ke naam SAROJ gram JAROND gp JAROND | Approved | 151411.74 | 0 | 2025-04-14
PATAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1733003069/IF/9993704654 — IAY JEERA BAI W/O NONE LAL | Completed | 14000 | 14310 | 2016-01-16 | 2018-01-03
PATAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1733003069/IF/9993707216 — indra aawas sudha bai/ rupnarayan | Completed | 84310 | 14310 | 2016-01-24 | 2018-02-09
PATAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1733003069/IF/9993707218 — indra aawas rewti bai/ ram singh | Completed | 84310 | 14310 | 2016-01-24 | 2018-01-03
PATAN | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/2168828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1417468 | Completed | 15840 | 15840 | 2019-07-25 | 2020-01-20
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3133959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4792271 | Completed | 17370 | 17178 | 2021-06-24 | 2022-03-12
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3134031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4811454 | Completed | 17370 | 16726 | 2021-06-17 | 2022-07-15
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3134051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4779981 | Completed | 17370 | 17130 | 2021-07-01 | 2022-07-15
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3134070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4837012 | Completed | 17370 | 16988 | 2021-06-24 | 2022-03-12
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3134145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4788236 | Deleted | 23490 | 0 | 2021-05-18
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3134661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4853758 | Completed | 17370 | 17130 | 2021-06-17 | 2022-07-15
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3134730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4139095 | Completed | 17370 | 17100 | 2021-06-10 | 2022-02-04
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3223562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4423709 | Completed | 17370 | 17352 | 2021-09-04 | 2022-12-28
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3358765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4480645 | Approved | 23490 | 0 | 2021-11-16
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3363915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5192437 | Completed | 17370 | 17354 | 2022-02-23 | 2022-12-28
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3363991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5196244 | Completed | 17370 | 17286 | 2022-02-01 | 2022-07-15
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5221368 | Completed | 17370 | 17678 | 2022-02-18 | 2022-10-15
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5225346 | Completed | 17370 | 17616 | 2022-06-28 | 2022-10-15
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5242822 | Completed | 17370 | 17177 | 2022-02-09 | 2022-07-15
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5260759 | Completed | 17370 | 17364 | 2022-03-01 | 2023-02-11
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5262963 | Deleted | 23490 | 0 | 2021-11-16
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5264295 | Completed | 17370 | 16984 | 2022-02-09 | 2022-07-31
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5268514 | Completed | 17370 | 16791 | 2022-02-05 | 2022-07-15
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5270521 | Completed | 17370 | 17315 | 2022-09-13 | 2023-07-24
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5285697 | Completed | 17370 | 17286 | 2022-01-29 | 2022-07-15
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3364857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5285719 | Completed | 17370 | 18274 | 2022-02-05 | 2022-09-20
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3367097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5531148 | Completed | 17370 | 17286 | 2022-04-01 | 2022-09-20
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3367121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5534557 | Completed | 17370 | 18190 | 2022-01-30 | 2022-09-20
PATAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3367279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5556796 | Completed | 17370 | 17235 | 2022-03-07 | 2023-08-23
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3725498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116114180 | Completed | 18360 | 17634 | 2022-06-30 | 2023-01-24
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3764181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118420731 | Completed | 18360 | 17854 | 2022-06-17 | 2022-10-15
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3836950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853519 | Completed | 18360 | 18008 | 2022-06-17 | 2023-01-24
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3866189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144746318 | Completed | 18360 | 17952 | 2022-09-09 | 2023-07-14
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/3953915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150871257 | Completed | 18360 | 18008 | 2022-06-28 | 2023-04-10
PATAN | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/408016 — Construction of IAY House -IAY REG. NO. MP1245373 | Completed | 15030 | 15030 | 2017-02-23 | 2018-03-05
PATAN | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/408019 — Construction of IAY House -IAY REG. NO. MP1245378 | Completed | 15030 | 15030 | 2017-03-02 | 2018-01-11
PATAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4189507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113495243 | Completed | 18360 | 18030.2 | 2022-09-11 | 2023-07-14
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4546522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106956817 | Completed | 21870 | 21870 | 2024-10-01 | 2026-01-01
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4585567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120711262 | Completed | 21870 | 21870 | 2024-10-01 | 2026-01-01
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4609082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123862900 | Completed | 21870 | 21870 | 2024-10-01 | 2026-01-01
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4609085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123863239 | Completed | 21870 | 21870 | 2024-10-16 | 2026-01-01
PATAN | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/469552 — Construction of IAY House -IAY REG. NO. MP1821397 | Completed | 15030 | 15030 | 2017-03-22 | 2018-03-05
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4803400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144742241 | Completed | 23490 | 21384 | 2024-11-15 | 2026-01-28
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4937383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106682042 | Completed | 23490 | 23400 | 2025-08-13 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4940339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113581400 | Completed | 23490 | 21782 | 2025-04-28 | 2026-02-04
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4941030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113494883 | Approved | 23490 | 0 | 2025-02-27
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4941031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113495063 | Completed | 23490 | 22574 | 2025-04-01 | 2026-02-01
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4941032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113495115 | Completed | 23490 | 22975 | 2025-03-22 | 2026-01-01
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4942111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114660200 | Completed | 23490 | 22890 | 2025-03-22 | 2026-01-01
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4942896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114893492 | Completed | 23490 | 22331 | 2025-04-10 | 2026-02-04
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4942897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114893568 | Completed | 23490 | 22302 | 2025-04-28 | 2026-02-04
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4943579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115071502 | Completed | 23490 | 22302 | 2025-04-28 | 2026-02-04
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4943581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115071813 | Completed | 23490 | 22686 | 2025-03-22 | 2026-01-01
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4945247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116114329 | Completed | 23490 | 21811 | 2025-04-10 | 2026-02-04
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4945258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116121241 | Completed | 23490 | 23480 | 2025-08-29 | 2026-01-07
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4945259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116121299 | Approved | 23490 | 0 | 2025-02-27
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4947848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853055 | Completed | 23490 | 22851 | 2025-04-28 | 2026-01-07
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4947849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853101 | Approved | 23490 | 0 | 2025-03-03
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4947852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853236 | Completed | 23490 | 23400 | 2025-08-13 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4947854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853423 | Physically Completed | 23490 | 22822 | 2025-04-28 | 2026-03-29
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4947856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853465 | Completed | 23490 | 22822 | 2025-04-28 | 2026-01-07
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4948807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117973863 | Completed | 23490 | 21870 | 2025-03-22 | 2026-01-01
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4954055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120710390 | Approved | 23490 | 0 | 2025-02-27
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4979018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144740840 | Completed | 23490 | 22071 | 2025-04-28 | 2026-02-01
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/4979019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144749759 | Ongoing | 23490 | 8320 | 2025-10-06
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5163336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144745282 | Approved | 23490 | 0 | 2025-03-11
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5164473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113494945 | Ongoing | 23490 | 16120 | 2025-11-05
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5194219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123876614 | Completed | 23490 | 23400 | 2025-08-30 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5203991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113495603 | Ongoing | 23490 | 4131 | 2025-04-28
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5221515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116852932 | Approved | 23490 | 0 | 2025-03-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5226032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116852791 | Completed | 23490 | 22620 | 2025-06-25 | 2026-02-04
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5233497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120711130 | Completed | 23490 | 23140 | 2025-08-13 | 2026-01-07
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5240671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144741953 | Approved | 23490 | 0 | 2025-03-08
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5246307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113494784 | Completed | 23490 | 23400 | 2025-08-30 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5247028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114893328 | Completed | 23490 | 23140 | 2025-10-23 | 2026-05-15
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5247403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113755330 | Completed | 23490 | 21320 | 2025-08-20 | 2026-03-05
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5253311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117973290 | Completed | 23490 | 23400 | 2025-08-13 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5261555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116121184 | Completed | 23490 | 22331 | 2025-04-28 | 2026-02-01
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5267139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114653636 | Approved | 23490 | 0 | 2025-03-22
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5268693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117973539 | Completed | 23490 | 22302 | 2025-04-28 | 2026-02-04
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5271882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113495204 | Completed | 23490 | 23400 | 2025-08-13 | 2026-02-23
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5279549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120713119 | Completed | 23490 | 23400 | 2025-09-19 | 2026-03-18
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5294985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106956784 | Completed | 23490 | 23120 | 2025-09-28 | 2026-01-07
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5295064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144740521 | Approved | 23490 | 0 | 2025-02-26
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5295782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114654256 | Physically Completed | 23490 | 22880 | 2025-10-23 | 2026-03-29
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5297902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123874477 | Completed | 23490 | 22851 | 2025-04-10 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5302144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144743029 | Completed | 23490 | 23140 | 2025-08-20 | 2026-01-06
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5303167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853481 | Approved | 23490 | 0 | 2025-03-22
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5312860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114893528 | Completed | 23490 | 22591 | 2025-04-10 | 2026-02-04
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5321248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114654093 | Physically Completed | 23490 | 21840 | 2026-02-11 | 2026-04-05
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5321541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123866382 | Completed | 23490 | 23111 | 2025-04-10 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5322801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106956626 | Completed | 23490 | 22360 | 2025-10-06 | 2026-03-31
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5329007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123875934 | Completed | 23490 | 22822 | 2025-04-28 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5336307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144747962 | Completed | 23490 | 22851 | 2025-04-10 | 2026-01-06
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5341593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106956655 | Completed | 23490 | 23400 | 2025-09-19 | 2026-03-05
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5423265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114654802 | Approved | 23490 | 0 | 2025-03-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5426151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116121512 | Completed | 23490 | 23400 | 2025-08-30 | 2026-01-07
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5427625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120710479 | Completed | 23490 | 23400 | 2025-09-03 | 2026-01-07
PATAN | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/542928 — Construction of IAY House -IAY REG. NO. MP3151276 | Completed | 15030 | 15030 | 2017-02-16 | 2018-04-01
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5430747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106681923 | Completed | 23490 | 23400 | 2025-09-03 | 2026-03-18
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5474435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116121420 | Physically Completed | 23490 | 22880 | 2025-10-23 | 2026-03-29
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5586177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118421046 | Completed | 23490 | 23400 | 2025-08-30 | 2026-01-07
PATAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/56256 — Construction of IAY House -IAY REG. NO. MP-33-003-069-004/24627061 | Deleted | 14310 | 0 | 2015-12-14
PATAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/5630080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114653437 | Approved | 23490 | 0 | 2025-03-28
PATAN | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/580333 — Construction of IAY House -IAY REG. NO. MP3162448 | Completed | 15030 | 15030 | 2017-03-09 | 2018-03-05
PATAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/59754 — Construction of IAY House -IAY REG. NO. MP-33-003-069-003/24163009 | Deleted | 14310 | 0 | 2015-12-25
PATAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/59755 — Construction of IAY House -IAY REG. NO. MP-33-003-069-003/35602888 | Deleted | 14310 | 0 | 2015-12-25
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/6192778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144741403 | Approved | 23490 | 0 | 2026-03-18
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/6200852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144746783 | Approved | 23490 | 0 | 2026-03-18
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/6208314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120710097 | Approved | 23490 | 0 | 2026-03-18
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/6210442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853560 | Approved | 23490 | 0 | 2026-03-18
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/6212306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144744419 | Approved | 23490 | 0 | 2026-03-18
PATAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733003069/IF/IAY/6215377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116853539 | Approved | 23490 | 0 | 2026-03-18
PATAN | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003069/LD/121 — जैट्रोपा पौधा रोपण कार्य जरौंद | Completed | 0 | 18350 | 2008-08-21 | 2008-01-01
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1733003069/LD/22012034240374 — med badhan suresh | Completed | 16309 | 792 | 2015-12-08 | 2016-09-18
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1733003069/LD/22012034240376 — med badhan basori lal | Completed | 32619 | 1848 | 2015-12-01 | 2016-09-18
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1733003069/LD/22012034240703 — med badhan gopal singh /tek singh | Completed | 29357 | 106 | 2015-12-23 | 2016-09-18
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1733003069/LD/22012034240704 — med badhan ram khilawan | Completed | 35000 | 104 | 2015-12-16 | 2016-09-18
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1733003069/LD/22012034240708 — med badhan govind patel | Completed | 35881 | 88 | 2015-12-16 | 2016-09-18
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1733003069/LD/22012034241479 — med badhan lokman / GANA RAM | Completed | 19571 | 106 | 2015-12-16 | 2016-09-18
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1733003069/LD/22012034241503 — khel medan | Completed | 105000 | 27687 | 2015-12-23 | 2018-08-29
PATAN | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1733003069/LD/22012034314234 — शांतिधाम निर्माण कार्य -रिछाई | Completed | 227000 | 223724.5 | 2017-05-26 | 2022-12-20
PATAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1733003069/LD/22012034602321 — LAND LEVELING AVAM SHED NIRMAN KARYA JARAUND SHANTIDHAM PARISHAR ME | Physically Completed | 338569.95 | 156230.1 | 2024-03-05 | 2026-06-15
PATAN | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003069/LD/3799401528 — Bedi LAL Thakur - Jaround | Deleted | 21000 | 0 | 2013-04-01
PATAN | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003069/LD/3799401530 — Suresh Thakur - Jaround | Deleted | 21000 | 0 | 2013-04-01
PATAN | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003069/LD/3799416865 — Jarond Santi dham Nirmand Karya | Completed | 370063 | 240693 | 2014-03-06 | 2016-08-08
PATAN | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733003069/LD/869 — खेल मैदान निर्माण व समतलीकरण कार्य जरौद | Completed | 487000 | 29042 | 2011-06-16 | 2015-07-30
PATAN | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1733003069/PG/22012034366050 — PLAY GRPUND JAROND PS | Completed | 105000 | 40608 | 2017-11-27 | 2018-08-29
PATAN | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733003069/RC/10732 — टेकराम के खेत से रामलाल के खेत तक मार्ग निमार्ण | Completed | 0 | 234993 | 2010-06-05 | 2014-12-02
PATAN | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733003069/RC/10755 — डूडी नाला से पंचायत की सीमा तक पहूच मार्ग निर्माण | Completed | 473000 | 126020 | 2011-05-22 | 2014-07-30
PATAN | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1733003069/RC/10756 — श्री राम लाल के खेत से डंडी नाला तक पहूच मार्ग | Completed | 0 | 119066 | 2011-05-08 | 2014-12-02
PATAN | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/10803 — पंचपरमेश्‍वर सी सी रोड एवं नाली निर्माण जरौद | Completed | 88473 | 62706 | 2012-03-21 | 2012-07-02
PATAN | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/10917 — 1733003069/RC/10917 | Completed | 120000 | 114660 | 2013-02-23 | 2015-09-09
PATAN | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034173786 — जगदीश झारि‍या के घर से सुरेश पटैल के मकान तक रोड | Completed | 40000 | 36148 | 2013-06-26 | 2014-07-30
PATAN | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034191409 — C.C.Road Nali Nirmand Karya Dairy Chouraha se Im | Deleted | 144662 | 0 | 2013-08-15
PATAN | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034193392 — deri choraha se imli ke ped tak or gajadar patel s | Completed | 144000 | 136310 | 2013-12-02 | 2015-07-08
PATAN | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034203777 — Panch Parmeswar C.C. 5th Phese Road Nali Nirmand | Completed | 57703 | 52218 | 2014-02-12 | 2015-02-23
PATAN | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034223783 — ramesawar patel ke ghar se suresh ke ghar tak | Completed | 57000 | 53489 | 2014-07-04 | 2015-02-23
PATAN | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034227202 — 6th part gudda ke ghar se ambika ke ghar tak | Completed | 50000 | 49040 | 2014-08-21 | 2015-02-23
PATAN | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034286229 — 7TH C.C.ROAD JAYDEV PATEL KE GHAR SE LAXMAN BASOR KE GHAR KI ARO | Completed | 36000 | 36311 | 2015-10-08 | 2016-04-25
PATAN | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733003069/RC/22012034345325 — 14VITT CC ROAD NIRMAN KARYA CHOTE PATEL KE GHAR SE SURESH PATEL KE GHAR KI OR | Completed | 444000 | 63984 | 2017-08-02 | 2019-05-14
PATAN | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034352387 — 14 वां वित्त सी सी रोड आंतरिक मार्ग प्राथमिक शाला से सामुदायिक भवन की और | Completed | 103000 | 17544 | 2017-09-06 | 2019-05-14
PATAN | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733003069/RC/22012034368921 — c c road nirmaan | Closed | 0 | 0 | 2017-04-14
PATAN | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733003069/RC/228 — Jaroda se reechi Pahuch Marag | Completed | 131000 | 143785 | 2009-06-29 | 2012-07-13
PATAN | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003069/RS/22012034486063 — nali nirman karya shayam sunder ke ghars e panchayat bhavan ki aur gram jarond 2020-21 | Completed | 34000 | 33934 | 2021-02-20 | 2026-02-01
PATAN | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1733003069/RS/22012034504128 — 15 Va vitt + SBM+ NREGA se sarvjanik Toilet nirmand Shanti dham ke pass Gram Jarond | Completed | 75000 | 43410 | 2021-02-13 | 2023-05-20
PATAN | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003069/RS/22012034665186 — SHOKPIT NIRMAN KARYA GRAM KE H.P. KE PAAS DUNDI | Completed | 3600 | 3468 | 2022-10-26 | 2023-12-26
PATAN | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1733003069/RS/22012034666295 — SAMIDAYIK NADEP NIRMAN KARYA shantidham ke pass Richai | Closed | 9600 | 0 | 2022-09-18
PATAN | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733003069/RS/22012034666297 — SAMUDAAY SHOKPIT NIRMAN KARYA GRAM KE H.P. KE PAAS RICHHAI | Completed | 3600 | 3588 | 2022-10-06 | 2023-05-04
PATAN | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1733003069/RS/22012034666298 — SAMUDAYIK NADEP NIRMAN KARYA GRAM KE PAAS DUNDI | Completed | 9600 | 8976 | 2022-10-15 | 2023-05-04
PATAN | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1733003069/RS/22012034666299 — SAMUDAYIK NADEP NIRAMAN KARYA GRAM KE PAAS RICHHAI | Completed | 9000 | 8976 | 2022-09-28 | 2023-05-04
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1733003069/RS/22012034674458 — Samudaik Bhawan Jarond Ki Putai Putti avem Sochalay me Tile lagane ka karya | Completed | 33000 | 28953 | 2024-02-28 | 2026-02-04
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003069/RS/22012034698701 — R C C nali Nirmand Rakesh Kachai ke ghar se Deri Chouraha Ki or | Completed | 27000 | 25449 | 2023-10-04 | 2024-02-02
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1733003069/RS/22012034702683 — samudayak nadep nirman karya jarond | Completed | 9600 | 6160 | 2023-09-20 | 2024-04-29
PATAN | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1733003069/RS/22012035113612 — SAMUDAYIK NADIP NIRMAN KARYA TALAB KINAARE JAROND | Completed | 9600 | 9004 | 2023-10-04 | 2024-04-29
PATAN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733003069/RS/22012035129380 — RCC nali nirman ewm cc road kodi lala k ghar se shivcharan Patel k ghar ki aor | Completed | 68000 | 35138.94 | 2024-10-03 | 2025-05-23
PATAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Road Line Plantation of Shelter Belt Trees-Comm / Road Line Plantation of Shelter Belt Trees for Community | Plantation | 1733003069/WC/22012034837976 — ROOF WATER HARVESTING SWATCHA PARISAR | Completed | 3000 | 3281 | 2022-02-09 | 2023-04-26
PATAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1733003069/WC/22012034838948 — ROOF WATTER HARVESTING AGAN BADI ME JAROUND | Closed | 3000 | 0 | 2021-08-15
PATAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1733003069/WC/22012035145914 — SAMUDAYAK KHET TALAB JARAUND | Closed | 259026.19 | 0 | 2023-04-14
PATAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1733003069/WC/22012035176673 — SAMUDAYAK KHET TALAB JARAUND SHANTIDHAM KE PASS | Ongoing | 297147.17 | 48033 | 2024-03-05
PATAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733003069/WC/22012035213355 — SOAK PIT NIRMAN KARY hand pump k pass jarond | Completed | 2000 | 1944 | 2024-08-29 | 2025-05-01
PATAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1733003069/WC/22012035213422 — ROOF WATHER HARVESTING JAROND | Completed | 2000 | 1920 | 2024-08-20 | 2025-05-23
PATAN | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1733003069/WH/22012034438966 — taalab jernodhar nirman karya gram jaround 17-18 | Physically Completed | 833000 | 52270 | 2019-03-06 | 2020-08-08
PATAN | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1733/RC/22012034609974 — REGRAVELLING जरोद से रिछाई | Completed | 553000 | 144407.4 | 2022-05-05 | 2024-07-16
PATAN | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1733/RC/22012034609975 — REGRAVELLING जरोद से डुन्डी | Completed | 553000 | 72932.1 | 2022-05-05 | 2024-07-16