## Work List
Exported on: 2026-10-20 22:59:11
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: Bhidki
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAHPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1733004012/AV/22012034639429 — शांतिधाम निर्माण कार्य भिड्की | Ongoing | 226381.46 | 0 | 2023-10-09
SHAHPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1733004012/AV/22012034650457 — उप स्वस्थ्केंद्र में बाउन्ड्री बॉल निर्माण कार्य भिड्की | Ongoing | 97700 | 0 | 2024-07-08
SHAHPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Prduction of building material (Comm) / Production of Building Material for Community | Construction of Other Community Building/Assets | 1733004012/AV/22012034666062 — CHABUTRA NIRMAN KARYA GRAM ANDIYA | New | 0 | 0 | 2025-04-15
SHAHPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1733004012/DP/22012034620736 — खेत तालाब में वृक्षारोपण निर्माण कार्य ग्राम अन्डिया समुदायक खसरा न 147 | Approved | 0 | 0 | 2024-06-01
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1733004012/IC/22012034891793 — SAHUDAHIYK KOOP NIRMAN KARYA GRAM ANDIYA | New | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1733004012/IC/22012034892435 — सार्वजनिक कूप निर्माण कार्य ग्राम अन्डिया | New | 0 | 0 | 2025-04-15
SHAHPURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733004012/IF/22012034422033 — वृक्षारोपण कार्य निजी खेत की मेढ़ पर | Ongoing | 189000 | 0 | 2018-09-19
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1733004012/IF/22012035085480 — kapildhara koop(ramkesh/ranglal) | Ongoing | 391335.16 | 0 | 2025-04-08
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Check Dam for Individual | Construction of Check Dam/Stop Dam | 1733004012/IF/22012035197972 — हितेषी कूप निर्माण कार्य संजय कुमार / राममिलन गोतिया ग्राम बिछुआ | Ongoing | 282417.57 | 0 | 2024-03-14
SHAHPURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004012/IF/22012035216196 — PONDS NIRMAN KARYA SEETARAM / PREM LAL GOUND KHASRA NUMBER 264 GRAM DABHOLA | Ongoing | 385261.22 | 0 | 2024-03-11
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1733004012/IF/22012035419467 — परषोत्तम / प्रेम लाल कूप में रिचार्ज पिट निर्माण कार्य ग्राम डभोला | Approved | 25899.46 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1733004012/IF/22012035419568 — कल्लू पटेल / सेवाराम पटेल कपिलधारा कूप में रिचार्ज पिट निर्माण ग्राम बिछुआ | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1733004012/IF/22012035419638 — रुकमणी / नत्थू सिंह पटेल के कपिलधारा कूप में रिचार्ज पिट निर्माण ग्राम बिछुआ | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1733004012/IF/22012035419790 — शिवकुमार /सूरज प्रसाद कपिलधारा कूप में रिचार्ज पिट निर्माण कार्य ग्राम भिडकी | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1733004012/IF/22012035419875 — मलखान / सेवाराम कपिलधारा कूप में रिचार्ज पिट निर्माण कार्य ग्राम बिछुआ | Approved | 25899.46 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004012/IF/22012035419987 — भगवती / सुम्मी लाल के कपिलधारा में रिचार्ज पिट निर्माण कार्य ग्राम दभोला | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1733004012/IF/22012035421296 — भगवानदास / रल्ली के कूप में रिचार्ज पिट निर्माण कार्य दभोला | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1733004012/IF/22012035421386 — नैन सिंह / चुन्नी लाल के कूप में रिचार्ज पिट निर्माण कार्य दभोला | Approved | 25899.46 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004012/IF/22012035436323 — Khet Talab Nirman karya Sardar Patel / Bhagwan Das Gram Bichhua | Ongoing | 450885.64 | 11100 | 2025-06-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004012/IF/22012035436355 — Khet Talab Nirman karya Brajesh/ Pooran Gp Bhidki | Approved | 450885.64 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1733004012/IF/22012035534032 — HITESHI KOOP NIRMAN SARDAR TAJINDAR /SARDAR UJGAR GRAM MIRGA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1733004012/IF/22012035534051 — HITESHI KOOP NIRMAN KARYA JAGDEESH / JIYA LAL GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004012/IF/22012035534126 — KHET TALAB NIRMAN KARYA SAVITRI BAI / SUKCHAIN GOUND GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004012/IF/22012035534137 — KHET TALAB NIRMAN KARYA BRAJESH / POORAN LAL GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004012/IF/22012035573335 — JGSA 2025 KHET TALAB NIRMAN KARYA SAVITRI BAI / SUKHCHAIN GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1733004012/IF/22012035573352 — KOOP NIRMAN KARYA SARDAR TAJINDAR SINGH / SARDAR UJAGAR GRAN MIRGA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1733004012/IF/22012035573358 — KOOP NIRMAN KARYA JAGDEESH / JIYA LAL GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733004012/IF/22012035585532 — एक बगिया माँ के नाम मंगो बाई/ब्रजेश सिंह | Ongoing | 143679.83 | 11100 | 2025-10-10
SHAHPURA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/3296859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5398304 | Ongoing | 27000 | 0 | 2023-07-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/3360323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4763416 | Ongoing | 27000 | 0 | 2025-09-27
SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/3646933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3512694 | Approved | 27000 | 0 | 2022-02-24
SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/3647620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5101917 | Ongoing | 27000 | 0 | 2022-03-10
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/4761802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119993720 | Approved | 27000 | 0 | 2024-09-24
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5148018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148376815 | Ongoing | 27000 | 0 | 2025-04-13
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5169082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148376904 | Approved | 27000 | 0 | 2025-03-12
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5183420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148377621 | Ongoing | 27000 | 4200 | 2026-03-17
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5240704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151196914 | Approved | 27000 | 0 | 2025-03-07
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5337760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148376547 | Completed | 23490 | 0 | 2025-06-02 | 2026-09-18
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5653561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114809542 | Ongoing | 27000 | 0 | 2026-04-03
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5655503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151196159 | Ongoing | 27000 | 0 | 2025-10-08
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5756655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148376755 | Approved | 27000 | 0 | 2024-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/5757433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148377438 | Completed | 23490 | 0 | 2025-09-27 | 2026-09-03
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004012/IF/IAY/6300766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148377465 | Approved | 27000 | 0 | 2024-09-17
SHAHPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1733004012/RC/22012034843483 — C C ROAD NIRMAN KARYA SUKCHAIN KE GHAR SE SIDDH BABA KI OR GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733004012/RS/22012035135450 — लीची पिट 3 यूनिट हैण्ड पम्प के पास | Ongoing | 15000 | 0 | 2025-02-18
SHAHPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1733004012/RS/22012035135451 — लीच पिट डभोला हैंड पंप के पास 4 यूनिट | Ongoing | 22900 | 0 | 2025-12-26
SHAHPURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1733004012/WC/22012035014114 — AMRAT SAROVAR NAVIN TALAB NIRNAD KARY GRAM DHABHOLA | Ongoing | 1811000 | 0 | 2022-11-16
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1733004012/WC/22012035308615 — NAVEEN TALAB NIRMAN KARYA GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15
SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1733004012/WC/22012035308616 — AMRAT SARVAR NIRMAN KARYA GRAM ANDIYA | Approved | 0 | 0 | 2025-04-15