## Work List
Exported on: 2026-09-11 07:55:27
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: Jamuniya Purani
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAHPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1733004057/AV/22012034658948 — Boundriy Wall Nirman kary Gram bhoutiya | New | 0 | 0 | 2024-04-17
SHAHPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1733004057/AV/22012034659447 — Pepar block nirmar kary aganwadi kendra 01 upswasth kendra ke samne Gram Jamuniya | New | 0 | 0 | 2024-04-01
SHAHPURA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1733004057/DP/22012034548195 — शासकीय भूमि चारागाह निर्माण कार्य गौशाला के पास ग्राम पिपरिया खसरा ७/१ | Ongoing | 801086.17 | 0 | 2022-04-15
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1733004057/DP/22012034606786 — शांतिधाम के पास वृक्षारोपण ग्राम जमुनिया | Ongoing | 757490.82 | 0 | 2023-09-24
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1733004057/DP/22012034607024 — मुख्यमार्ग से ग्राम पंचायत भवन तक रोड साइड दोनों और वृक्षारोपण निर्माण ग्राम जमुनिया | Ongoing | 427106.07 | 0 | 2023-09-24
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1733004057/DP/22012034607026 — मुख्यमार्ग से ग्राम भोतिया तक रोड साइड दोनों और वृक्षारोपण निर्माण ग्राम भोतिया | Ongoing | 427106.07 | 0 | 2023-09-24
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1733004057/DP/22012034607039 — वृक्षारोपण रोड साइड दोनों ओर मुख्यमार्ग से ग्राम झाँसी तक | Ongoing | 427106.07 | 0 | 2023-09-24
SHAHPURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/1708784 — Construction of IAY House -IAY REG. NO. MP2448897 | Ongoing | 27000 | 0 | 2018-07-06
SHAHPURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/1709141 — Construction of IAY House -IAY REG. NO. MP2488316 | Ongoing | 27000 | 0 | 2018-07-30
SHAHPURA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/2948236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2503656 | Approved | 27000 | 0 | 2020-11-23
SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/2950026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2599203 | Ongoing | 27000 | 0 | 2021-06-19
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4748891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114181808 | Ongoing | 27000 | 0 | 2024-11-29
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4753224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118135655 | Ongoing | 27000 | 0 | 2024-12-01
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4756526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118691596 | Ongoing | 27000 | 0 | 2024-12-01
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4758199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118593012 | Ongoing | 27000 | 0 | 2024-12-01
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4785124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129821046 | Ongoing | 27000 | 0 | 2024-11-29
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4785638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129824020 | Ongoing | 27000 | 0 | 2024-11-29
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4866469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129820934 | Ongoing | 27000 | 0 | 2025-08-12
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4880936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129820488 | Ongoing | 27000 | 0 | 2025-04-06
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/4999129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115787009 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5004268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118369859 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5019086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125452701 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5088996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129818713 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5088997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129819270 | Ongoing | 27000 | 0 | 2025-08-21
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5089000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129820838 | Ongoing | 27000 | 0 | 2025-04-06
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5214412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118592615 | Ongoing | 27000 | 0 | 2025-04-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5253391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118592353 | Ongoing | 27000 | 0 | 2025-04-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5259110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116313926 | Ongoing | 27000 | 0 | 2025-04-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5298151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119760085 | Ongoing | 27000 | 0 | 2025-04-26
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5302270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118691165 | Ongoing | 27000 | 0 | 2025-04-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5302417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129819785 | Ongoing | 27000 | 0 | 2025-04-09
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5320388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129818832 | Ongoing | 27000 | 0 | 2025-04-09
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5342939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143028281 | Ongoing | 27000 | 0 | 2025-04-09
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5397485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116664990 | Ongoing | 27000 | 0 | 2025-08-06
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5402818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119281850 | Ongoing | 27000 | 0 | 2025-09-08
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5561911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117915328 | Ongoing | 27000 | 0 | 2025-08-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5580492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119760202 | Ongoing | 27000 | 0 | 2025-09-08
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5653005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125443758 | Ongoing | 27000 | 0 | 2025-09-08
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5653006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125445630 | Ongoing | 27000 | 0 | 2025-09-08
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5653118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118124510 | Ongoing | 27000 | 0 | 2025-09-08
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5655100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115731066 | Ongoing | 27000 | 0 | 2025-09-04
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5655249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116302100 | Ongoing | 27000 | 0 | 2025-09-04
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5655258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119093987 | Ongoing | 27000 | 0 | 2025-09-04
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5655328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118691394 | Ongoing | 27000 | 0 | 2025-09-04
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5688225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129824565 | Ongoing | 27000 | 0 | 2025-09-04
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5722929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125449969 | Ongoing | 27000 | 0 | 2025-09-04
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5755001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129822887 | Ongoing | 27000 | 0 | 2025-09-04
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5803137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129819138 | Ongoing | 27000 | 0 | 2026-08-17
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5812728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119278656 | Approved | 27000 | 0 | 2025-02-25
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5819377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119281636 | Ongoing | 27000 | 0 | 2026-07-13
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5819862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114211096 | Ongoing | 27000 | 0 | 2026-06-24
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5889491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129818609 | Approved | 27000 | 0 | 2025-02-25
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5889616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119630930 | Approved | 27000 | 0 | 2025-04-07
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5889762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129820191 | Completed | 23490 | 0 | 2026-03-16 | 2026-09-03
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/5889996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118691511 | Physically Completed | 23490 | 0 | 2026-06-23 | 2026-08-23
SHAHPURA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733004057/IF/IAY/645234 — Construction of IAY House -IAY REG. NO. MP1409224 | Approved | 27000 | 0 | 2017-02-18
SHAHPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1733004057/RC/22012034823823 — Pepar block Nirmar kary Bhoutiya | Approved | 0 | 0 | 2024-04-17
SHAHPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733004057/RC/22012034840668 — Jhansi mukhya marg se muktidham pahuch marg Jhansi jamuniya purani | Ongoing | 1496234.81 | 0 | 2025-03-30
SHAHPURA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1733004057/RC/VB/22012034854436 — GRAVEL ROAD MAIN ROAD SE JAMUNIYA TOLA TAK | Approved | 0 | 0 | 2026-07-01
SHAHPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733004057/RC/YD/22012034844116 — CC ROAD RAMNATH KE GHAR SE SARDAR KE GHAR TAK | Ongoing | 71000 | 0 | 2026-02-06
SHAHPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733004057/RC/YD/22012034845419 — CC ROAD TABAL KE GHAR SE SUKHDEEN KE GHAT TAK | Ongoing | 47400 | 0 | 2026-02-07
SHAHPURA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733004057/RC/YD/22012034845421 — CC ROAD HAJJI KE GHAR SE KANJI HOUSE TAK | Ongoing | 29500 | 0 | 2026-02-07