## Work List
Exported on: 2026-10-16 20:52:51
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: Kusmi
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAHPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1733004073/DP/22012034545096 — MAA KI BAGIYA P.S.M.S.KUSMI | Ongoing | 21437.22 | 0 | 2024-03-17
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1733004073/DP/22012034589530 — Plantation Work Main road kusmi se Neemkheda ki or Gp kusmi | Ongoing | 427106.07 | 0 | 2023-09-16
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1733004073/DP/22012034610469 — Plantation jhanshighat Hanuman Mandir se Gram Neemkheda ki or Road Side | Ongoing | 427106.07 | 0 | 2023-10-07
SHAHPURA | 2023-2024 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1733004073/DP/22012034612113 — Charagah ll Go Shala Neemkheda | Ongoing | 444322.12 | 0 | 2024-03-15
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Block Plantation of Sericulture Trees for Community | Plantation | 1733004073/DP/22012034615522 — Plantation kusmi mukhy sadak samshan se Neemkheda ki or | Ongoing | 427106.07 | 0 | 2024-03-17
SHAHPURA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733004073/IF/22012034371145 — निजी खे में फलो़ान:- श्यामलाल, मुनीम | Ongoing | 407000 | 0 | 2018-04-30
SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1733004073/IF/22012035218435 — Plantation Niji khet ki Med par Sundar lal | Ongoing | 160586.73 | 0 | 2024-03-17
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1733004073/IF/22012035324268 — Pond Nirman Bharat Singh/Mastram Lodhi Neemkheda | New | 0 | 0 | 2025-04-10
SHAHPURA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/1104235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1249156 | Approved | 27000 | 0 | 2017-05-15
SHAHPURA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/2950042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2628152 | Approved | 27000 | 0 | 2020-11-06
SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/3646886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3299859 | Approved | 27000 | 0 | 2022-02-27
SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/3646889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3309951 | Ongoing | 27000 | 0 | 2022-08-24
SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/3647000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3919820 | Approved | 27000 | 0 | 2022-02-27
SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/3647990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2092364 | Ongoing | 27000 | 0 | 2022-04-11
SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/3648198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4584795 | Ongoing | 27000 | 0 | 2022-04-01
SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/3805500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115303600 | Approved | 27000 | 0 | 2022-05-04
SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/3999990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115304641 | Approved | 27000 | 0 | 2022-05-06
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4005162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120658051 | Ongoing | 27000 | 0 | 2024-06-07
SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4242918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115304727 | Approved | 27000 | 0 | 2022-06-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4762649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121035182 | Ongoing | 27000 | 3000 | 2024-12-16
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4941181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114068517 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4943835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115304037 | Ongoing | 27000 | 0 | 2025-04-07
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4943837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115304545 | Ongoing | 27000 | 2100 | 2025-03-20
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4953552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121060233 | Ongoing | 27000 | 2100 | 2025-04-07
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4953553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121060566 | Ongoing | 27000 | 0 | 2025-04-07
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4953865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120245836 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4956212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121388525 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4956221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121392981 | Ongoing | 27000 | 2100 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4956232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121398563 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4956249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121406512 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4956251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121406846 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4958484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121021892 | Ongoing | 27000 | 16800 | 2026-08-03
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4958488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121024206 | Physically Completed | 27000 | 0 | 2025-04-07 | 2026-09-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4958504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121033858 | Ongoing | 27000 | 0 | 2025-04-07
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/4958507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121034757 | Ongoing | 27000 | 900 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5102712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148725466 | Ongoing | 27000 | 2100 | 2025-03-20
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5102715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148725625 | Ongoing | 27000 | 0 | 2025-04-11
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5102760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148735675 | Physically Completed | 27000 | 900 | 2025-03-20 | 2026-10-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5102761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148736625 | Ongoing | 27000 | 0 | 2025-04-07
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5102772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148737917 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5102777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148738691 | Ongoing | 27000 | 0 | 2025-03-20
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5559812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121033967 | Ongoing | 27000 | 0 | 2026-02-09
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5565924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148738474 | Ongoing | 27000 | 0 | 2025-08-01
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5655756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148737382 | Ongoing | 27000 | 2100 | 2026-02-16
SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/5758292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148738147 | Approved | 27000 | 0 | 2024-09-24
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6123863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120235174 | Approved | 27000 | 0 | 2026-02-26
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6124891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121060398 | Ongoing | 27000 | 0 | 2026-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6125422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121571965 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6125448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120642418 | Ongoing | 27000 | 6300 | 2026-09-11
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6125711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120586612 | Ongoing | 27000 | 0 | 2026-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6127023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121028055 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6127029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121030472 | Ongoing | 27000 | 6300 | 2026-09-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6127032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121031676 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6128252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121399875 | Ongoing | 27000 | 4200 | 2026-09-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6128263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121405698 | Approved | 27000 | 0 | 2026-02-19
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6128267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121408588 | Ongoing | 27000 | 0 | 2026-09-30
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6130329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148154342 | Approved | 27000 | 0 | 2026-02-19
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6139134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121397889 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6139500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120819270 | Ongoing | 27000 | 0 | 2026-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6140464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121406969 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6143319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120235800 | Approved | 27000 | 0 | 2026-02-26
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6145258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121031863 | Ongoing | 27000 | 6300 | 2026-09-10
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6147638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115304665 | Ongoing | 27000 | 0 | 2026-09-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6147649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148735726 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6147650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148736352 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6147651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148736382 | Approved | 27000 | 0 | 2026-02-19
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6148607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148713752 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6148608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148714118 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6149476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148737519 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6149935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121021174 | Approved | 27000 | 0 | 2026-02-26
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6151056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125584322 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6151234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120645691 | Ongoing | 27000 | 6300 | 2026-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6152924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148725861 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6154380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121412749 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6156008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121402015 | Approved | 27000 | 0 | 2026-02-26
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6156259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120576088 | Approved | 27000 | 0 | 2026-02-19
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6157988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121408966 | Approved | 27000 | 0 | 2026-02-19
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6158083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121413419 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6160070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121414092 | Ongoing | 27000 | 6300 | 2026-09-10
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6160074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121031104 | Ongoing | 27000 | 6300 | 2026-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6160075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121031277 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6160886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121023670 | Ongoing | 27000 | 6300 | 2026-09-10
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6160887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121023803 | Ongoing | 27000 | 6300 | 2026-09-10
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6162453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148740229 | Ongoing | 27000 | 4200 | 2026-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6162454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148729785 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6162461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121389041 | Approved | 27000 | 0 | 2026-02-26
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6163888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115303899 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6163889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115303929 | Ongoing | 27000 | 0 | 2026-09-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6163909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120657523 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6165308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121653642 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6169807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121028430 | Approved | 27000 | 0 | 2026-02-19
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6170691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121652132 | Ongoing | 27000 | 4200 | 2026-09-15
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6171490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148713113 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6175536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121652735 | Ongoing | 27000 | 4200 | 2026-09-15
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6178687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121399154 | Ongoing | 27000 | 2100 | 2026-09-30
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6180085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128184631 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6181952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148725505 | Approved | 27000 | 0 | 2026-03-09
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6182212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121023286 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6184140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127545809 | Ongoing | 27000 | 2100 | 2026-09-29
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6184366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121021618 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6184696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121033742 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6184783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148740118 | Approved | 27000 | 0 | 2026-03-09
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6185202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148738329 | Ongoing | 27000 | 10500 | 2026-05-19
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6187882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148713155 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6188036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121023418 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6188061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121028632 | Ongoing | 27000 | 6300 | 2026-09-11
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6190168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148736713 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6195828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121395302 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6195847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120656559 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6196317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148738410 | Approved | 27000 | 0 | 2026-03-09
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6200061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148736590 | Approved | 27000 | 0 | 2026-03-02
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6203763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121549593 | Ongoing | 27000 | 6300 | 2026-09-10
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6206727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148726361 | Approved | 27000 | 0 | 2026-02-23
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6208060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148725929 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6208665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121396581 | Ongoing | 27000 | 2100 | 2026-09-30
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6209132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121030872 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6210532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148736771 | Approved | 27000 | 0 | 2026-03-09
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6212305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121395980 | Ongoing | 27000 | 2100 | 2026-09-30
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6212900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121411029 | Ongoing | 27000 | 8400 | 2026-09-10
SHAHPURA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6216577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148729756 | Ongoing | 27000 | 2100 | 2026-09-29
SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1733004073/IF/IAY/6360041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148736735 | Approved | 27000 | 0 | 2026-03-13
SHAHPURA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1733004073/RC/22012034832378 — Sudor sadak nirmaan main road se Jhansighat tola ki or | Approved | 0 | 0 | 2024-10-02