## Work List
Exported on: 2026-09-08 17:06:32
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: MOUHAS
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733005066/AV/22012034636171 — Shanti Dham Nirman Kary Belkhadu Mohas Paganer Road | Ongoing | 330972.38 | 0 | 2023-10-07
PANAGAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733005066/AV/22012034636172 — Shanti Dham Nirman Kary Mohas | Ongoing | 330972.38 | 0 | 2023-10-07
PANAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733005066/IF/22012035128892 — Plantation Kary Manoj ki badhi me mohas | Ongoing | 427106.07 | 0 | 2023-07-28
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1733005066/IF/22012035629937 — EK BAGIYA MAA KE NAAM SURILI GAUND/ Rajesh Kumar GP MOUHAS | Approved | 163420.35 | 0 | 2025-08-16
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5344230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114068564 | Ongoing | 27000 | 0 | 2025-05-11
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5345341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116878985 | Ongoing | 27000 | 0 | 2025-05-11
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5345889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148335689 | Physically Completed | 27000 | 0 | 2026-01-13 | 2026-09-06
PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5348260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114069949 | Approved | 27000 | 0 | 2025-03-27
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5348283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777141 | Ongoing | 27000 | 0 | 2025-05-11
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5349982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105987140 | Ongoing | 27000 | 0 | 2025-04-22
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5350776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119076211 | Ongoing | 27000 | 0 | 2025-08-31
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5351549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115707235 | Ongoing | 27000 | 0 | 2025-05-11
PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5353754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106001839 | Approved | 27000 | 0 | 2025-02-14
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5354419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106638733 | Ongoing | 27000 | 0 | 2025-04-22
PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5575090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106176756 | Approved | 27000 | 0 | 2025-02-14
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5596718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123800019 | Ongoing | 27000 | 0 | 2025-08-31
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5761773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113632850 | Ongoing | 27000 | 0 | 2025-09-25
PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5762099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114071998 | Approved | 27000 | 0 | 2025-02-14
PANAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5762159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106636923 | Approved | 27000 | 0 | 2025-02-14
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5762340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106063292 | Ongoing | 27000 | 0 | 2025-09-25
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5763301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113480210 | Ongoing | 27000 | 0 | 2025-09-25
PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5783067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116223689 | Ongoing | 27000 | 0 | 2026-07-21
PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/5783189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148335630 | Ongoing | 27000 | 0 | 2026-07-21
PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/6194815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114053892 | Ongoing | 27000 | 0 | 2026-07-21
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/6200195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118496764 | Approved | 27000 | 0 | 2026-03-17
PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/6205224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115707214 | Ongoing | 27000 | 0 | 2026-07-21
PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/6209960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119077861 | Ongoing | 27000 | 0 | 2026-07-21
PANAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/6211963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115777163 | Approved | 27000 | 0 | 2026-02-10
PANAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/6368974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115886078 | Approved | 27000 | 0 | 2026-08-06
PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/66363 — Construction of IAY House -IAY REG. NO. MP-33-005-066-001/80 | Approved | 27000 | 0 | 2015-12-31
PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/66367 — Construction of IAY House -IAY REG. NO. MP-33-005-066-001/83 | Approved | 27000 | 0 | 2015-12-31
PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/66368 — Construction of IAY House -IAY REG. NO. MP-33-005-066-001/88 | Approved | 27000 | 0 | 2015-12-31
PANAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733005066/IF/IAY/66369 — Construction of IAY House -IAY REG. NO. MP-33-005-066-002/120 | Approved | 27000 | 0 | 2015-12-31
PANAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005066/RC/22012034843085 — CC ROAD NIRMAN AKHILESH PATEL KE GHAR SE KHERMAI MANDIR KI OR MOHAS 15FC AND NREGA | Approved | 98000 | 0 | 2025-04-15
PANAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005066/RC/22012034843086 — CC ROAD NIRMAN NARESH CHADAR KE GHAR SE MUNNA KACHHI KI OR BAGHOD GP MOHAS NREGA AND 15FC | Approved | 49000 | 0 | 2025-04-15
PANAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733005066/RC/22012034843087 — CC ROAD NIRMAN MAIN ROAD SE RAKESH SEN KI OR MOHAS NREGA AND 15FC | Approved | 99000 | 0 | 2025-04-15
PANAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733005066/RS/22012035136718 — RCC NALI NIRMAN DHARMENDRA BASOR KE GHAR SE KARAN THAKUR NREGA AND 15FC VILLAGE AND GP MOHAS | Approved | 20000 | 0 | 2024-11-16