## Work List
Exported on: 2026-09-06 13:57:05
Filters applied:
Data source: VBGRAMG
District: JABALPUR
Block: All
Panchayat: BAMHNI (BARELA)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733006065/AV/22012034627680 — sashkiya bhavan vyayam shala evam rangmanch me boundrywall nirman karya | Ongoing | 138000 | 0 | 2023-01-16
JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1733006065/DP/22012034580814 — VRAKSHA ROPAN KARYA SHNTI DHAM AVAM SARKARI KUYE KE PAAS | Ongoing | 427106.07 | 0 | 2023-07-24
JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1733006065/DP/22012034580816 — VRAKSHA ROPAN KARYA MADHYAMIK SHALA KE PEECHE AVAM PURWA ROAD SIDE | Ongoing | 427106.07 | 0 | 2023-07-26
JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1733006065/DP/22012034584862 — amrit watika karya gram panchayt bamhani barela | Ongoing | 55847.4 | 0 | 2023-08-09
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1733006065/IF/22012035179480 — HITESHI KOOP NIRMAN KAYRA BHAGCHAND/NANHA MEHRA | Ongoing | 296962.26 | 0 | 2024-03-13
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1733006065/IF/22012035179487 — HITESHI KOOP NIRMAN KARYA DHARMA SINGH GOND/SUNDAR | Ongoing | 280342.65 | 0 | 2024-03-13
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1733006065/IF/22012035230079 — HITESHI KOOP NIRMAN KARYA MAHESH PITA DALSING GOND | Ongoing | 294981.17 | 0 | 2024-06-23
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1733006065/IF/22012035230093 — HITESHI KOOP NIRMAN KARYA KHUMAN SINGH/CHAITU SINGH GOND | Ongoing | 294981.17 | 0 | 2024-06-27
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1733006065/IF/22012035369392 — dug well recharge khuman singh gram bahmni gp bahmni barela | New | 0 | 0 | 2025-04-10
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006065/IF/IAY/2678732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5059721 | Ongoing | 27000 | 2100 | 2021-04-27
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006065/IF/IAY/361601 — Construction of IAY House -IAY REG. NO. MP1151445 | Ongoing | 27000 | 0 | 2017-07-10
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006065/IF/IAY/4712460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127136510 | Ongoing | 27000 | 0 | 2024-10-16
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006065/IF/IAY/5145842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127152248 | Ongoing | 27000 | 0 | 2025-04-10
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006065/IF/IAY/5439594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127149140 | Ongoing | 27000 | 0 | 2025-05-17
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006065/IF/IAY/5581778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113910227 | Ongoing | 27000 | 0 | 2025-05-17
JABALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006065/RC/22012034833572 — CC ROAD PRATHMIK SHALA SE MUKHYA MARG KI AUR BHIDKI | Approved | 0 | 0 | 2024-10-02
JABALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006065/RC/22012034833573 — CC ROAD PRATHMIK SHALA SE MUKHYA MARG KI AUR BHIDKI | New | 0 | 0 | 2024-10-02
JABALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006065/RC/22012034833574 — CC ROAD PRATHMIK SHALA SE MUKHYA MARG KI AUR BHIDKI | New | 0 | 0 | 2024-10-02
JABALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006065/RC/22012034833575 — CC ROAD PRATHMIK SHALA SE MUKHYA MARG KI AUR BHIDKI | New | 0 | 0 | 2024-10-02
JABALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006065/RC/22012034833576 — CC ROAD PRATHMIK SHALA SE MUKHYA MARG KI AUR BHIDKI | New | 0 | 0 | 2024-10-02
JABALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006065/RC/22012034833577 — CC ROAD PRATHMIK SHALA SE MUKHYA MARG KI AUR BHIDKI | Approved | 0 | 0 | 2024-10-02
JABALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006065/RS/22012034380097 — SOCHLYA NIRMAN KARYA RAMDEEN CHOKSE | Ongoing | 10800 | 0 | 2017-10-28
JABALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1733006065/RS/22012035138610 — rcc nali jhariya mohalla koop se manchu chakrawarti ke ghar tak | Ongoing | 45000 | 0 | 2025-11-23
JABALPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006065/WC/VB/22012035332152 — sok pit nirman karya nal ke pass bamhani | Approved | 0 | 0 | 2026-07-27
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1733006065/WH/22012034445875 — NIRMAL NEER KOOP NIRMAN KARYA BAMHANI TIRAHA | Ongoing | 470874.11 | 0 | 2021-03-24