## Work List
Exported on: 2026-10-28 03:07:03
Filters applied:
Data source: MGNREGA
District: JABALPUR
Block: All
Panchayat: AMAHINAUTA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JABALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1733006083/AV/22012034510863 — KHEL MAIDAN NIRMAN KARYA AMAHINOTA | Completed | 215276.77 | 213479.41 | 2020-06-16 | 2024-01-02
JABALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733006083/AV/22012034510959 — shantidham nirman kaarya | Closed | 194312.08 | 0 | 2020-06-09
JABALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1733006083/AV/22012034580223 — daining hall middle school amahinota | Closed | 19583.8 | 0 | 2021-04-01
JABALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1733006083/AV/22012034595670 — naadif kaarya middle school amahinota | Closed | 12630.91 | 0 | 2021-08-18
JABALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733006083/AV/22012034595675 — Soak pit high school amahinota | Completed | 14467.3 | 10615 | 2021-10-19 | 2022-05-12
JABALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1733006083/AV/22012034611919 — ps and ms school amahinota me kota and paver block karya | Completed | 85000 | 39537 | 2022-01-14 | 2024-01-02
JABALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733006083/AV/22012034652629 — muktidham nirman amahinauta | Closed | 0 | 0 | 2024-01-26
JABALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1733006083/AV/22012034652807 — Muktidham nirman Amahinouta | Ongoing | 330972.38 | 4420 | 2024-03-15
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1733006083/DP/22012034542800 — DP MAA KI BAGIYA MIDDLE SCHOOL | Closed | 0 | 0 | 2021-10-02
JABALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1733006083/DP/22012034567270 — vrachharopan nirman kary shanti dhaam evam road ke kinare | Ongoing | 410718.19 | 63446 | 2022-09-14
JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1733006083/DP/22012034581309 — SHANTI DHAM SE LEKAR KHEL MAIDAN KI AUR | Closed | 427106.07 | 0 | 2023-07-10
JABALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1733006083/DP/22012034585669 — amrit vatika vraksharopan kary amahinota | Completed | 54569.95 | 30435.99 | 2023-10-07 | 2026-05-09
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733006083/IF/22012034347326 — वृक्षारोपण कार्य शान्तिधाम से रेलवेलाइन की और | Completed | 335000 | 67878 | 2017-06-14 | 2021-09-08
JABALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034479090 — medh badhan kaarya hilya bai | Closed | 0 | 0 | 2019-05-25
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034481763 — medh bandhan kaarya pradeep patel | Completed | 20620.86 | 15010 | 2020-06-12 | 2021-02-18
JABALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034481768 — khel medan kary pradeep patel | Closed | 0 | 0 | 2019-05-25
JABALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034482043 — medh badhan kaarya pradeep patel | Closed | 0 | 0 | 2019-06-07
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034482087 — Medh badhan kaarya veerendra patel | Completed | 20105.32 | 18620 | 2020-07-08 | 2021-01-18
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034560388 — medh badhan kaarya rajkumar patel | Completed | 22956.8 | 20140 | 2020-06-04 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034560393 — medh badhan kaarya bhagwandas thakur | Completed | 21565.48 | 19000 | 2020-06-12 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034565732 — shanti dham nirman kaarya | Closed | 0 | 0 | 2020-05-09
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034565760 — med badhan kary ashok kumar k khet mein | Completed | 19617.72 | 19000 | 2020-06-12 | 2021-01-18
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034565761 — med badhan kary praveen kumar k khet mein | Completed | 27130.77 | 24130 | 2020-06-12 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034565763 — med badhan kary pradeep patel k khet mein | Completed | 21704.64 | 19000 | 2020-06-12 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034567951 — medh badhan kaarya narayan prasad patel | Completed | 11687.15 | 9880 | 2020-06-12 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034567960 — khel medan kary gram kripashankar patel | Deleted | 0 | 0 | 2020-05-09
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034567961 — medh badhan kary abhishek vishwakarma | Completed | 33391.79 | 29830 | 2020-06-15 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034567962 — medh badhan kaarya prabhu vishwakarma | Completed | 25043.84 | 23180 | 2020-06-12 | 2021-01-18
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034567964 — medh badhan karya vinod patel | Completed | 25461.23 | 20330 | 2020-06-15 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034567966 — medh badhan kaarya santosh vishwakarma | Completed | 30052.58 | 26410 | 2020-06-12 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034570615 — medh badhan kaarya jyoti tiwari | Completed | 41739.74 | 34580 | 2020-06-15 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034570622 — medh badhan kaarya jeevesh pandey | Completed | 41739.74 | 30970 | 2020-06-15 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034570646 — medh badhan kaarya kripashankar lodhhi | Completed | 23652.51 | 20330 | 2020-06-15 | 2021-02-06
JABALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034570649 — medh badhan kaarya ajay tiwari | Completed | 34783.11 | 29640 | 2020-06-15 | 2021-02-06
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034765299 — medh badhan kaarya rani bai | Completed | 33212.22 | 29336 | 2021-05-28 | 2021-09-08
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1733006083/IF/22012034765324 — medh badhan nirman kaarya amit patel | Completed | 22612.61 | 23160 | 2021-05-30 | 2021-07-31
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035196552 — VRAKSHAROPAN KARYA DASHTATH PATEL | Closed | 135212.69 | 0 | 2024-01-26
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035196554 — VRAKSHAROPAN KARYA LAXMAN CHAKRWARTI | Closed | 133212.69 | 5250 | 2024-02-21
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035196555 — VRAKSHAROPAN KARYA RAMSINGH THAKUR | Closed | 133212.69 | 6300 | 2024-02-21
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035196557 — VRAKSHAROPAN KARYA DHARMA BAI LODHI | Closed | 0 | 0 | 2024-01-26
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035196560 — VRAKSHAROPAN KARYA KRIPA SHANKAR LODHI | Ongoing | 133212.69 | 43863.04 | 2024-02-09
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035196562 — VRAKSHAROPAN KARYA BARELAL CHAKRWARTI | Closed | 0 | 0 | 2024-01-26
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035200408 — VRAKSHAROPAN KARYA TEERATH PATEL | Closed | 132769.6 | 3635 | 2024-03-15
JABALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1733006083/IF/22012035200429 — VRAKSHAROPAN KARYA JAGDEESH PRASADPATEL | Closed | 132769.6 | 140 | 2024-03-14
JABALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1733006083/IF/22012035482244 — Dug wel richarj pit jeevesh pandye k khet mein | Approved | 25899.46 | 0 | 2025-05-04
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1733006083/IF/22012035578586 — Jeevesh pande k khet mein vrachharopan kary | Approved | 0 | 0 | 2025-06-30
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1733006083/IF/22012035600066 — Ek Bagiya Maa Ke Naam TATO BAI3329266 | Approved | 170535.07 | 0 | 2025-08-01
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1343712 — Construction of IAY House -IAY REG. NO. MP3589280 | Completed | 15480 | 15660 | 2018-06-05 | 2018-12-06
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1386996 — Construction of IAY House -IAY REG. NO. MP3589885 | Completed | 15480 | 15660 | 2018-04-28 | 2019-04-08
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1432770 — Construction of IAY House -IAY REG. NO. MP3192722 | Completed | 15480 | 14964 | 2018-04-28 | 2018-09-27
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1432792 — Construction of IAY House -IAY REG. NO. MP3193673 | Approved | 23490 | 0 | 2018-03-06
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1432793 — Construction of IAY House -IAY REG. NO. MP3193690 | Completed | 15480 | 15660 | 2018-06-05 | 2019-01-06
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1432954 — Construction of IAY House -IAY REG. NO. MP3198463 | Completed | 15480 | 15636 | 2018-06-19 | 2019-04-24
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1433054 — Construction of IAY House -IAY REG. NO. MP3201816 | Completed | 15480 | 15660 | 2018-05-21 | 2018-09-09
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1434521 — Construction of IAY House -IAY REG. NO. MP3247908 | Completed | 15480 | 15660 | 2018-05-21 | 2018-09-09
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1434526 — Construction of IAY House -IAY REG. NO. MP3248057 | Completed | 15480 | 14964 | 2018-04-28 | 2018-09-27
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1434790 — Construction of IAY House -IAY REG. NO. MP3256711 | Completed | 15480 | 15660 | 2018-04-28 | 2019-01-06
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1436282 — Construction of IAY House -IAY REG. NO. MP3306693 | Completed | 15480 | 15660 | 2018-05-25 | 2018-09-12
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1436637 — Construction of IAY House -IAY REG. NO. MP3318581 | Completed | 15480 | 15660 | 2018-07-12 | 2018-11-30
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1498075 — Construction of IAY House -IAY REG. NO. MP3495411 | Completed | 15480 | 15644 | 2018-06-05 | 2019-04-11
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1498080 — Construction of IAY House -IAY REG. NO. MP3495491 | Completed | 15480 | 15648 | 2018-06-05 | 2019-05-09
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1498088 — Construction of IAY House -IAY REG. NO. MP3495648 | Completed | 15480 | 15632 | 2018-06-07 | 2019-05-09
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1498090 — Construction of IAY House -IAY REG. NO. MP3495664 | Completed | 15480 | 15312 | 2018-05-21 | 2018-09-27
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1498381 — Construction of IAY House -IAY REG. NO. MP3501217 | Completed | 15480 | 15660 | 2018-05-26 | 2018-09-08
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1501453 — Construction of IAY House -IAY REG. NO. MP3563633 | Completed | 15480 | 15660 | 2018-06-05 | 2018-09-27
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1501454 — Construction of IAY House -IAY REG. NO. MP3563644 | Completed | 15480 | 15660 | 2018-06-13 | 2018-12-19
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1503061 — Construction of IAY House -IAY REG. NO. MP3589864 | Completed | 15480 | 15660 | 2018-04-28 | 2018-11-02
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1503062 — Construction of IAY House -IAY REG. NO. MP3589894 | Completed | 15480 | 15660 | 2018-06-05 | 2018-11-02
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1510835 — Construction of IAY House -IAY REG. NO. MP3684204 | Completed | 15480 | 15660 | 2018-05-26 | 2018-09-12
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1624460 — Construction of IAY House -IAY REG. NO. MP3598201 | Completed | 15660 | 15660 | 2018-05-26 | 2019-01-06
JABALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1624463 — Construction of IAY House -IAY REG. NO. MP3620084 | Completed | 15660 | 15660 | 2018-04-28 | 2019-01-06
JABALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/1651255 — Construction of IAY House -IAY REG. NO. MP3589867 | Completed | 17100 | 15960 | 2020-11-07 | 2021-06-08
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2029305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3193600 | Completed | 17100 | 16458 | 2019-09-25 | 2021-10-16
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2057309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3589876 | Completed | 15840 | 15896 | 2019-07-24 | 2020-05-19
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2057817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3597866 | Completed | 15840 | 16036 | 2019-08-20 | 2020-05-19
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2057834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3598137 | Completed | 15840 | 16708 | 2019-11-26 | 2020-07-26
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2059245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3620039 | Completed | 15840 | 16036 | 2019-07-23 | 2020-05-19
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2059280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3620471 | Completed | 17100 | 16684 | 2019-10-19 | 2021-10-18
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2059297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3620913 | Completed | 15840 | 15924 | 2019-07-23 | 2020-05-19
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2184342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2691865 | Completed | 15840 | 15924 | 2019-08-20 | 2020-05-19
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2193038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1995567 | Completed | 17100 | 15959 | 2019-08-20 | 2022-03-03
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2195903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3283502 | Completed | 15840 | 16246 | 2019-09-25 | 2020-05-27
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2195979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3315086 | Completed | 17100 | 16036 | 2019-08-20 | 2021-05-08
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2196507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3537126 | Completed | 17100 | 16980 | 2019-08-20 | 2023-08-31
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2196730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3620257 | Completed | 17100 | 16444 | 2019-09-25 | 2023-07-22
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2196748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3628248 | Completed | 15840 | 16252 | 2019-09-25 | 2020-07-26
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2197647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3962500 | Completed | 15840 | 16036 | 2019-08-20 | 2020-05-19
JABALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2197899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3667706 | Completed | 17100 | 16027 | 2019-08-20 | 2021-11-01
JABALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2457644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3318599 | Completed | 17100 | 17112 | 2020-06-12 | 2021-10-30
JABALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2563281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3247357 | Completed | 17100 | 17100 | 2020-06-12 | 2021-01-30
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2832637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5170464 | Completed | 17100 | 17177 | 2021-04-29 | 2022-03-02
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2832862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5208992 | Completed | 17100 | 17370 | 2021-07-08 | 2021-10-15
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2833026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5240444 | Completed | 17100 | 17094 | 2021-04-29 | 2023-07-28
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2833135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5536300 | Completed | 17100 | 17177 | 2021-04-29 | 2022-02-26
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2834436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5102050 | Completed | 17100 | 17370 | 2021-04-29 | 2022-02-23
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2846429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5281985 | Completed | 17100 | 17370 | 2021-05-13 | 2022-02-24
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2848309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5568713 | Completed | 17100 | 17370 | 2021-07-08 | 2021-10-15
JABALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/2850063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5616698 | Completed | 17100 | 17098 | 2021-05-21 | 2023-07-28
JABALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/335080 — Construction of IAY House -IAY REG. NO. MP1102293 | Completed | 15030 | 14166 | 2017-01-31 | 2018-03-24
JABALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/340104 — Construction of IAY House -IAY REG. NO. MP1109748 | Completed | 15030 | 15046 | 2017-01-31 | 2017-11-08
JABALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/340215 — Construction of IAY House -IAY REG. NO. MP1109915 | Completed | 15030 | 14018 | 2017-01-31 | 2019-04-24
JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/3683914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107076534 | Completed | 18360 | 18264.8 | 2022-06-20 | 2023-07-15
JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/3715293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106235378 | Completed | 18360 | 18156 | 2022-06-04 | 2023-07-15
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/3715321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106238102 | Completed | 18360 | 18360 | 2024-11-06 | 2024-12-27
JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/3776759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126647132 | Completed | 18360 | 18316 | 2022-06-04 | 2023-07-15
JABALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/385015 — Construction of IAY House -IAY REG. NO. MP1168890 | Completed | 15030 | 14146 | 2017-01-31 | 2018-03-24
JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4116835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116215422 | Completed | 18360 | 18360 | 2022-06-04 | 2022-09-13
JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4219823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104939710 | Completed | 18360 | 18360 | 2022-12-15 | 2023-02-17
JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4363911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115126512 | Completed | 18360 | 18156 | 2022-10-27 | 2023-07-15
JABALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4369080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115008262 | Approved | 23490 | 0 | 2022-09-13
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4538064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104892203 | Completed | 21870 | 20427 | 2024-10-01 | 2026-01-28
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4554616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113768214 | Ongoing | 21870 | 14007 | 2024-10-01
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4554621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113768516 | Completed | 21870 | 20184 | 2024-10-01 | 2026-01-28
JABALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/4688000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106471053 | Completed | 21870 | 21141 | 2024-10-18 | 2026-01-28
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5112949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115126382 | Completed | 23490 | 23220 | 2025-07-08 | 2026-02-23
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5114472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114997815 | Ongoing | 23490 | 11745 | 2025-08-20
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5114478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115008221 | Completed | 23490 | 23220 | 2025-07-08 | 2025-12-12
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5114479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115008244 | Completed | 23490 | 23460 | 2025-04-23 | 2025-12-12
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5114620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116215304 | Ongoing | 23490 | 15660 | 2025-10-31
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5118494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106885923 | Ongoing | 23490 | 22944 | 2025-06-20
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5118743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106643459 | Completed | 23490 | 23490 | 2025-04-06 | 2025-12-12
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5122558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104939982 | Completed | 23490 | 23220 | 2025-04-06 | 2025-12-12
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5124685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107072416 | Completed | 23490 | 23205 | 2025-07-08 | 2026-02-23
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5126884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114997474 | Completed | 23490 | 23220 | 2025-07-08 | 2026-02-23
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5126885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114997640 | Physically Completed | 23490 | 19305 | 2025-07-08 | 2026-01-06
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5126886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114997738 | Physically Completed | 23490 | 0 | 2025-09-05 | 2026-03-22
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5127983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118218421 | Completed | 23490 | 22410 | 2025-06-20 | 2025-12-12
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5128723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126675457 | Completed | 23490 | 22950 | 2025-06-20 | 2025-12-12
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5128762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104892124 | Completed | 23490 | 23220 | 2025-06-20 | 2025-12-24
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5129116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116213764 | Completed | 23490 | 23490 | 2025-04-06 | 2025-06-06
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5130557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126611874 | Completed | 23490 | 23490 | 2025-09-05 | 2026-02-24
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5162568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115126095 | Ongoing | 23490 | 15660 | 2026-02-06
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5167756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104940290 | Physically Completed | 23490 | 22959 | 2025-07-08 | 2026-07-05
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5239967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104892163 | Ongoing | 23490 | 19305 | 2025-07-08
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5533693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116213875 | Ongoing | 23490 | 5742 | 2026-01-31
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5533783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118218497 | Completed | 23490 | 23490 | 2025-08-20 | 2026-02-23
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5541216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116215767 | Completed | 23490 | 23490 | 2025-10-11 | 2026-02-20
JABALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/555203 — Construction of IAY House -IAY REG. NO. MP3511491 | Completed | 15030 | 15428 | 2017-01-31 | 2019-05-09
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5786534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107062162 | Physically Completed | 23490 | 21402 | 2025-09-24 | 2026-07-05
JABALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5914689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123455614 | Ongoing | 23490 | 3915 | 2026-05-02
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5920178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106642257 | Approved | 23490 | 0 | 2026-02-17
JABALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5923706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107076560 | Ongoing | 23490 | 3915 | 2026-05-02
JABALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/5925244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118218567 | Approved | 23490 | 0 | 2026-02-17
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/658358 — Construction of IAY House -IAY REG. NO. MP2671958 | Completed | 15030 | 15512 | 2017-06-02 | 2019-01-06
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/658359 — Construction of IAY House -IAY REG. NO. MP2672010 | Completed | 15030 | 15512 | 2017-05-11 | 2018-06-23
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/660497 — Construction of IAY House -IAY REG. NO. MP1410302 | Completed | 15030 | 14792 | 2017-05-11 | 2018-03-24
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/662452 — Construction of IAY House -IAY REG. NO. MP1661365 | Completed | 15030 | 15480 | 2017-06-02 | 2018-05-25
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/662865 — Construction of IAY House -IAY REG. NO. MP1726015 | Completed | 15030 | 15332 | 2017-06-02 | 2018-05-28
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/664084 — Construction of IAY House -IAY REG. NO. MP1878379 | Completed | 15030 | 15536 | 2017-06-12 | 2019-05-09
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/665310 — Construction of IAY House -IAY REG. NO. MP1995533 | Completed | 15030 | 14792 | 2017-06-12 | 2018-03-24
JABALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/67499 — Construction of IAY House -IAY REG. NO. MP-33-006-083-001/89 | Approved | 23490 | 0 | 2016-01-01
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/726820 — Construction of IAY House -IAY REG. NO. MP1875290 | Completed | 15030 | 15506 | 2017-06-02 | 2019-04-25
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/729758 — Construction of IAY House -IAY REG. NO. MP1958761 | Completed | 15030 | 14792 | 2017-06-02 | 2018-03-24
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/731270 — Construction of IAY House -IAY REG. NO. MP2000628 | Completed | 15030 | 15320 | 2017-05-11 | 2018-05-28
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/731674 — Construction of IAY House -IAY REG. NO. MP2012270 | Completed | 17100 | 15772 | 2017-06-02 | 2023-08-01
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/751976 — Construction of IAY House -IAY REG. NO. MP2612130 | Completed | 15030 | 15550 | 2017-05-11 | 2019-06-13
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/752772 — Construction of IAY House -IAY REG. NO. MP2639921 | Completed | 15030 | 15510 | 2017-05-11 | 2018-12-06
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/753557 — Construction of IAY House -IAY REG. NO. MP2672676 | Completed | 15030 | 15332 | 2017-06-02 | 2018-05-28
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/753558 — Construction of IAY House -IAY REG. NO. MP2672681 | Completed | 15030 | 14992 | 2017-06-02 | 2019-01-06
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/753713 — Construction of IAY House -IAY REG. NO. MP2678982 | Completed | 15030 | 15504 | 2017-06-02 | 2019-04-25
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/765029 — Construction of IAY House -IAY REG. NO. MP3192667 | Completed | 15030 | 15336 | 2017-06-02 | 2018-06-23
JABALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/76743 — Construction of IAY House -IAY REG. NO. MP-33-006-083-001/63 | Approved | 23490 | 0 | 2016-01-05
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/881128 — Construction of IAY House -IAY REG. NO. MP1878405 | Completed | 15480 | 14294 | 2017-06-12 | 2019-09-30
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/885592 — Construction of IAY House -IAY REG. NO. MP1939078 | Completed | 15480 | 15500 | 2017-06-02 | 2018-05-14
JABALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1733006083/IF/IAY/888296 — Construction of IAY House -IAY REG. NO. MP1976146 | Completed | 15480 | 15512 | 2017-06-02 | 2018-06-23
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242218 — med bandhan sushila devi/ genda lal dubey | Completed | 29616 | 159 | 2015-12-07 | 2016-07-04
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242221 — med bandhan narendra barman/ lt channu lal | Completed | 18367 | 159 | 2015-12-07 | 2017-05-17
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242761 — med bandhan pradeep kumar/ ramesh kumar lodhi | Completed | 22958 | 159 | 2015-12-07 | 2016-07-04
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242762 — med bandhan dileep/ jagdeesh patel | Completed | 51656 | 159 | 2015-12-07 | 2016-07-04
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242764 — med bandhan kaluram/ sarju | Deleted | 26976 | 0 | 2015-11-27
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242766 — med bandhan ramesh kumar/ kaluram mishra | Completed | 30420 | 159 | 2015-12-07 | 2016-07-04
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242770 — med bandhan ashok kumar/ munnu rao | Completed | 24106 | 159 | 2015-12-07 | 2016-07-04
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/22012034242771 — med bandhan ahilya bai/ munnu ram patel | Completed | 34437 | 159 | 2015-12-07 | 2016-07-04
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1733006083/LD/22012034570034 — maidh badhan nirman kaarya khushi ram | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1733006083/LD/3799430328 — shantidham nirman karya | Completed | 602976 | 300841.75 | 2014-02-27 | 2017-02-27
JABALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1733006083/PG/9425893662 — KHEL MAIDAN NIRMAN KARYA AMAHINOUTA 2016 | Deleted | 180000 | 0 | 2016-11-01
JABALPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006083/RC/1711 — panch parmeshwar - antrik path c.c. sadak nirman karya choti bai ke ghar se shyama bai gotiya keghar | Deleted | 0 | 0 | 2012-01-26
JABALPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006083/RC/1712 — panch parmeshwar - antrik path c.c. sadak nirman karya choti bai ke ghar se shyama bai gotiya keghar | Completed | 0 | 70740 | 2012-03-15 | 2012-08-30
JABALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006083/RC/22012034161020 — panch parmeshwar - antrik path c.c. sadak nirman | Completed | 94158 | 46464 | 2013-02-26 | 2013-03-30
JABALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006083/RC/22012034170624 — cc road jagdish patel ke ghar se lekar panna patel | Completed | 95624 | 87662 | 2013-06-17 | 2014-03-01
JABALPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006083/RC/22012034229382 — cc road chhote ki dukan se vishnu barman ke ghar k | Completed | 64064 | 59664.9 | 2014-09-17 | 2015-04-15
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006083/RC/22012034369842 — C C ROAD NIRMAN KARY | Deleted | 0 | 0 | 2018-04-14
JABALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1733006083/RC/22012034438860 — CC ROAD NIRMAN KARYA | Closed | 0 | 0 | 2019-04-14
JABALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034349778 — शौचालय निर्माण कार्य नंदू बर्मन | Deleted | 10800 | 0 | 2017-10-30
JABALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034352941 — शौचालय निर्माण कार्य तुलसी ठाकुर | Deleted | 1080000000 | 0 | 2017-10-30
JABALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034360203 — shochalay nirman karya shusheel chadar | Deleted | 12000 | 0 | 2017-10-30
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034362152 — shouchalay nirman kaarya durgashankar lodhi | Completed | 12000 | 11024 | 2019-01-14 | 2021-06-01
JABALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034362531 — shouchalay nirmn kaarya praveen kumar lodhi | Closed | 12000 | 0 | 2017-08-01
JABALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034373345 — shouchalay nirman kaarya raju thakur | Deleted | 10800 | 0 | 2017-10-30
JABALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034402813 — sochalay nirman kary santosh chodhry | Closed | 12000 | 0 | 2018-03-10
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034402814 — sochalay nirman kary prem bai chuodhry | Completed | 12000 | 11404 | 2019-01-14 | 2021-06-01
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034435327 — souchalay nirman kaarya ashok kumar lodhi | Closed | 12000 | 0 | 2018-12-28
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438386 — shochalay nirman kary tikaram barman | Closed | 12000 | 0 | 2019-02-21
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438388 — shochalay nirman kary sukkoo yadav | Closed | 12000 | 0 | 2019-01-26
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438389 — shochalay nirman kary shivram patel | Closed | 12000 | 0 | 2019-02-21
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438390 — shochalay nirman kary sudarshan upadhyay | Closed | 12000 | 0 | 2019-02-21
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438391 — shochalay nirman kary nokhelal chuodhry | Closed | 12000 | 0 | 2019-02-21
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438417 — shochalay nirman kary ramdash thakur | Closed | 12000 | 0 | 2019-02-21
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438418 — shochalay nirman kary nanhelal chakrwarti | Closed | 12000 | 0 | 2019-02-21
JABALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1733006083/RS/22012034438419 — shochalay nirman kary nanndu barman | Closed | 12000 | 0 | 2019-02-21
JABALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1733006083/RS/22012034518042 — CTR soak pit nirmaan kayre gaya prasad ke ghar ke pass | Completed | 14467.3 | 10036 | 2021-06-29 | 2023-04-25
JABALPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1733006083/WC/22012034317313 — KOOP NIRMAN KARYA | Deleted | 0 | 0 | 2017-04-04
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034837742 — CTR SOAK PIT KAARYA AMIT PATEL | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Stone Spur for Community / Construction of Stone Spur for Community | Construction of Spur | 1733006083/WC/22012034837750 — CTR SOAK PIT KAARYA SUNEEL PATEL | Closed | 0 | 0 | 2021-08-10
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840244 — CTR soak pit kaarya anna chakrawarti | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840248 — CTR soak pit kaarya barelal chakrawaty | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840258 — CTR soak pit kaarya teerath prasad chakrwaraty | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840261 — CTR Soak pit kaarya hasanlal yadav | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840266 — CTR Soak pit kaarya gango bai | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840269 — Soak pit kaarya motilal gotiya | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840287 — CTR Soak pit kaarya azad vanshkar | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840290 — CTR Soak pit kaarya premlal patel | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840291 — CTR Soak pit kaarya sulli patel | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840297 — CTR Soak pit kaarya nanhelal chakrawareti | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840299 — CTR Soak pit kaarya rajesh | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840301 — CTR Soak pit kaarya kallu bai | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840303 — CTR Soak pit kaarya savitri bai | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840306 — CTR Soak pit kaarya moolchandran | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840308 — CTR Soak pit kaarya ashok | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840310 — CTR Soak pit karya prakash | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840314 — CTR Soak pit karya durgashankar | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840317 — CTR Soak pit karya satish | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/22012034840318 — CTR Soak pit karya satish | Closed | 0 | 0 | 2021-08-18
JABALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1733006083/WC/86---------05 — 86तालाब गहरीकरण आम हिताैना | Deleted | 293000 | 0 | 2008-05-21
JABALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1733006083/WC/86-----09 — 86मेड बधान राधा बाई आमाहिनोता | Deleted | 30000 | 0 | 2008-05-31
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/9993661535 — RECHARGE PIT (ps bhavan ke handpump ke pas) | Deleted | 11116 | 0 | 2015-11-27
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1733006083/WC/9993661550 — RECHARGE PIT (gaya prasad gotiya ke ghar ke baju me) | Completed | 11116 | 159 | 2015-12-07 | 2016-09-26
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1733006083/WC/9993661551 — RECHARGE PIT (swasthya kendra ke pas) | Deleted | 11116 | 0 | 2015-11-30
JABALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1733006083/WC/9993661688 — RECHARGE PIT BHG 01 | Completed | 11000 | 159 | 2015-12-18 | 2016-09-26
JABALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1733006083/WC/ भूमि विकास कार्य (कस्‍तूरबा बाई) — मेढ बधान कार्य कस्‍तूरी बाई के खेत मे आमाहिनौता | Deleted | 43000 | 0 | 2008-06-14