## Work List
Exported on: 2026-09-09 11:23:18
Filters applied:
Data source: VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: MANAKWARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHAWARPATHA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1734002074/AV/22012034392014 — पंचयत भबन सह सामुदयक भबन निर्माण कार्य -ग्राम,मनकबारा | Physically Completed | 880000 | 0 | 2018-12-02 | 2026-08-05
CHAWARPATHA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1734002074/AV/22012034665245 — 3 ROW PULIYA NIRMAN WORK VILLAGE GHATPIPARIYA MARG KE 220 METER PER | Physically Completed | 130000 | 0 | 2025-04-19 | 2026-08-05
CHAWARPATHA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1734002074/AV/22012034665246 — 3 ROW PULIYA NIRMAN WORK VILLAGE GHATPIPARIYA MARG KE 780 METER PER NO 2 | Ongoing | 130000 | 4499.6 | 2025-05-25
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4644713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141299481 | Ongoing | 27000 | 1500 | 2024-12-18
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4661768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148988610 | Ongoing | 27000 | 0 | 2025-01-24
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4699098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119353957 | Completed | 27000 | 0 | 2024-12-08 | 2026-09-04
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4724914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149283925 | Ongoing | 27000 | 0 | 2025-01-24
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4771317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124782863 | Ongoing | 27000 | 0 | 2025-02-08
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4772063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122459744 | Completed | 27000 | 0 | 2024-12-08 | 2026-09-04
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4790549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141299240 | Completed | 27000 | 0 | 2024-12-18 | 2026-09-04
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4868927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148925054 | Ongoing | 27000 | 600 | 2025-01-24
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4952800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119353531 | Ongoing | 27000 | 0 | 2025-09-03
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4954526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121901561 | Ongoing | 27000 | 0 | 2025-09-03
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4972407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141294655 | Ongoing | 27000 | 0 | 2025-07-27
CHAWARPATHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/4972408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141295233 | Ongoing | 27000 | 0 | 2026-07-27
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5104172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149283604 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5235441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123475666 | Approved | 27000 | 0 | 2025-03-20
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5423115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123807877 | Ongoing | 27000 | 0 | 2025-08-20
CHAWARPATHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5519279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122036949 | Ongoing | 27000 | 0 | 2026-07-27
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5521587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149284912 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5522822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145699785 | Approved | 27000 | 0 | 2025-03-17
CHAWARPATHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5523150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148988351 | Ongoing | 27000 | 0 | 2026-06-23
CHAWARPATHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5523151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148988414 | Physically Completed | 27000 | 0 | 2026-06-23 | 2026-08-30
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5523153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148996480 | Approved | 27000 | 0 | 2025-03-20
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5523155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148996741 | Approved | 27000 | 0 | 2025-03-20
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5524916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119352988 | Ongoing | 27000 | 0 | 2025-09-03
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5524917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119353330 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5525051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149282258 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5525052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149282687 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5525053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149282764 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5525054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149282856 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5525582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119722408 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5527496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122033862 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5528798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149334783 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5530086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149283219 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5530547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141299070 | Ongoing | 27000 | 0 | 2025-07-27
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5531928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123466675 | Approved | 27000 | 0 | 2025-03-01
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5659745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141300398 | Ongoing | 27000 | 0 | 2025-08-20
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5659749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149323429 | Approved | 27000 | 0 | 2025-04-29
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5659944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123805117 | Ongoing | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5660183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122066141 | Ongoing | 27000 | 0 | 2026-08-04
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5660341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148923780 | Approved | 27000 | 0 | 2025-05-07
CHAWARPATHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/5729791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149928812 | Approved | 27000 | 0 | 2025-03-27
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6177993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149285255 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6178602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149927796 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6178970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148988569 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6180553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149283047 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6183061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149336046 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6185195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125690039 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6185397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145716238 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6187174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149323401 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6191980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123457437 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6201641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149929692 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6202118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149283278 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6202829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124159852 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6204071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145699852 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6204327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148923537 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6204597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148996330 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6206061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148996793 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6206123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123471908 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6207436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148923864 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6209022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148996598 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6209941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123459895 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6210152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145693653 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6214079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149283406 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6215469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149283368 | Ongoing | 27000 | 0 | 2026-07-27
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6215498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123804669 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734002074/IF/IAY/6216686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149927140 | Approved | 27000 | 0 | 2026-03-13
CHAWARPATHA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734002074/RC/22012034619495 — cement concreet nali nirman govt.m.s. shala bhavan se gram ki mukhya nali tak | Completed | 119000 | 0 | 2022-11-16 | 2026-08-20
CHAWARPATHA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734002074/RC/22012034626835 — सी.सी. सडक निर्माण हरिप्रसाद सुनावत के मकान से राजकुमार विश्वाकर्मा (कजरोटा)तिराहा तक | Completed | 228000 | 0 | 2023-02-15 | 2026-08-20
CHAWARPATHA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734002074/WC/VB/22012035330281 — Roof top water harvesting work samudayak bhavan village ghatpipariya | Approved | 0 | 0 | 2026-07-31
CHAWARPATHA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734002074/WC/VB/22012035330302 — Recharge pits nirman sudarshan kourav ke ghar ke pass wale hand pump ke pass | Approved | 0 | 0 | 2026-07-31
CHAWARPATHA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734002074/WC/VB/22012035330312 — Roof top water harvesting work panchayat bhavan village manakwara | Approved | 0 | 0 | 2026-07-31