## Work List
Exported on: 2026-10-21 15:11:31
Filters applied:
Data source: VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: JIKOLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SAIKHEDA (GADARWARA) | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1734003003/DP/22012034623911 — वृक्षारोपण कार्य पंचायत भवन परिसर एवं प्राथमिक शाला में ग्राम पंचायत झिकोली | Approved | 0 | 0 | 2024-06-07
SAIKHEDA (GADARWARA) | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1734003003/DP/22012034624525 — वृक्षारोपण कार्य पंचायत भवन परिसर एवं माध्यमिक शाला परिसर ग्राम पंचायत झिकौली | Ongoing | 455063.17 | 0 | 2024-07-16
SAIKHEDA (GADARWARA) | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1734003003/DP/22012034630615 — आश्रय स्थल माॅ नर्मदा परिक्रमा पथ वृक्षारोपण कार्य ग्राम झिकोली ग्राम पंचायत झिकोली | Ongoing | 381868.55 | 0 | 2025-12-23
SAIKHEDA (GADARWARA) | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1734003003/FP/22012034641424 — CC Nali nirman karya madhyamik shala se shantidham tak JHIKOLI | New | 0 | 0 | 2024-04-14
SAIKHEDA (GADARWARA) | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1734003003/FP/22012034641425 — CC Nali nirman karya madhyamik shala se shantidham tak JHIKOLI | Approved | 0 | 0 | 2024-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734003003/IF/22012035288603 — khet Talab Nirman Karya Amarsingh Rajput / Takhat singh jhikoli | Ongoing | 280440.73 | 0 | 2025-04-17
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734003003/IF/22012035491050 — Khet Talab Nirman karya Lakhanlal thakur/ Balkishan Thakur jhikoli | Ongoing | 133646.6 | 0 | 2025-05-16
SAIKHEDA (GADARWARA) | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/297894 — Construction of IAY House -IAY REG. NO. MP1020158 | Approved | 27000 | 0 | 2016-12-28
SAIKHEDA (GADARWARA) | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/4661437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149574375 | Ongoing | 27000 | 0 | 2024-11-28
SAIKHEDA (GADARWARA) | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/4664322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149527882 | Ongoing | 27000 | 0 | 2024-10-24
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5390148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127272651 | Ongoing | 27000 | 0 | 2025-05-23
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5474303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125352462 | Ongoing | 27000 | 0 | 2025-05-01
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5474921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126464622 | Ongoing | 27000 | 0 | 2025-05-15
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5478556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127265512 | Ongoing | 27000 | 0 | 2025-05-15
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5480237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127242201 | Ongoing | 27000 | 0 | 2025-05-15
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5563283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151303217 | Ongoing | 27000 | 0 | 2025-05-15
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5968281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150011803 | Ongoing | 27000 | 9000 | 2026-05-12
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5969149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126496108 | Approved | 27000 | 0 | 2026-02-24
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/5969371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126079509 | Ongoing | 27000 | 0 | 2026-08-07
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6009688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129626550 | Ongoing | 27000 | 10800 | 2026-08-07
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6135915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125295240 | Ongoing | 27000 | 0 | 2026-08-07
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6137310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126215431 | Ongoing | 27000 | 0 | 2026-08-07
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6152822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136965368 | Approved | 27000 | 0 | 2026-02-24
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6152839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125340232 | Ongoing | 27000 | 12600 | 2026-07-31
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6153015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127317391 | Ongoing | 27000 | 18600 | 2026-06-17
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6154847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136954031 | Ongoing | 27000 | 9000 | 2026-07-31
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6154848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136956440 | Ongoing | 27000 | 7200 | 2026-05-26
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6155808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150627574 | Ongoing | 27000 | 9300 | 2026-05-19
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6161485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125341701 | Approved | 27000 | 0 | 2026-02-24
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6165875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149964038 | Ongoing | 27000 | 9000 | 2026-08-07
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6165883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150004322 | Ongoing | 27000 | 5400 | 2026-05-01
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6167538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123818955 | Ongoing | 27000 | 10800 | 2026-08-07
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6173671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151250045 | Approved | 27000 | 0 | 2026-02-24
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6267353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126901593 | Approved | 27000 | 0 | 2026-03-25
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734003003/IF/IAY/6312356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126564124 | Approved | 27000 | 0 | 2026-03-25
SAIKHEDA (GADARWARA) | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1734003003/RC/22012034843356 — Cement Concrete Sadak Nirman Karya main road se kherapati mata tak jhikoli | New | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1734003003/WC/22012035044360 — डग पौंड निर्माण कार्य ग्राम पंचायत झिकौली | Ongoing | 652151.04 | 0 | 2023-01-26
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734003003/WC/VB/YD/22012035336864 — रूफ वाटर हार्वेस्टिंग निर्माण कार्य पंचायत भवन ग्राम झिकोली ग्राम पंचायत झिकोली | Approved | 0 | 0 | 2026-10-13