## Work List
Exported on: 2026-09-09 07:33:20
Filters applied:
Data source: VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: NIWARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SAIKHEDA (GADARWARA) | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1734003029/AV/22012034668297 — shanti dhaam nirman kary/gram pondi | Ongoing | 347299.31 | 0 | 2026-02-06
SAIKHEDA (GADARWARA) | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1734003029/DP/22012034614738 — CNG nirman kary/goushala ke paas gram niwari | Ongoing | 658751.62 | 0 | 2024-03-16
SAIKHEDA (GADARWARA) | 2026-2027 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1734003029/FP/22012034642341 — undargrund pvc nali nirman kachhi tola gram niwari | Ongoing | 45000 | 0 | 2026-04-07
SAIKHEDA (GADARWARA) | 2026-2027 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1734003029/FP/22012034642342 — cemant kanktit rcc huyman pipe nali nirman kary gram pondi | Ongoing | 44000 | 14100 | 2026-07-21
SAIKHEDA (GADARWARA) | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1734003029/IF/22012035574063 — openwell recharge of send fillter/baasnt/kundan kushhwaha gram niwari | Approved | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1734003029/IF/22012035574072 — openwell recharge of send fillter/jugraj/chunnilal kushwaha | Approved | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1734003029/IF/22012035574081 — openwell recharge of send fillter/laxman/bhuvan kushwaha gram niwari | Approved | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1734003029/IF/22012035574087 — openwell recharge of send fillter/bhaiyaji/shrilal keer gram nirawi | New | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1734003029/IF/22012035574089 — openwell recharge of send fillter/bhaiyaji keer/shrilal gram niwari | Approved | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1734003029/IF/22012035574095 — openwell recharge of send fillter/vijju/lalji kushwaha gram niwari | Approved | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734003029/IF/22012035659589 — एक बगिया मां के नाम बीना तिवारी ग्राम निवारी ग्राम पंचायत निवारी | Ongoing | 184657.59 | 0 | 2026-02-04
SAIKHEDA (GADARWARA) | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734003029/IF/VB/22012035664713 — एक बगिया मॉ के नाम हेमलता चौकसे ग्राम निवारी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17
SAIKHEDA (GADARWARA) | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1734003029/LD/22012034947202 — goushala ke paas charagah vikash gram niwari gram panchayt niwari | Approved | 0 | 0 | 2024-11-30
SAIKHEDA (GADARWARA) | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1734003029/RC/22012034549211 — sudur sadak nirman kary/jhunkari bai ke makan se mukhy sadak tak | Ongoing | 1492015.84 | 0 | 2020-11-27
SAIKHEDA (GADARWARA) | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734003029/RC/22012034840044 — cc sadak suresh sen se mutta dhanak ki or gram niwari | Ongoing | 95000 | 0 | 2025-12-03
SAIKHEDA (GADARWARA) | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734003029/RC/22012034850997 — cemant kanktit rcc huyman pipe nali nirman kary gram pondi | Approved | 44000 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734003029/RC/22012034850998 — cemant kanktit rcc huyman pipe nali nirman kary gram pondi | Approved | 0 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734003029/RC/22012034852866 — undargrund pvc nali nirman kachhi tola gram niwari | Approved | 45000 | 0 | 2025-04-14
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734003029/WC/VB/22012035333451 — रुफ वाटर हार्वेस्टिंग कार्य गौशाला में शेड क्र. 01 में ग्राम निवारी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734003029/WC/VB/22012035333453 — रुफ वाटर हार्वेस्टिंग कार्य गौशाला में शेड क्र. 02 में ग्राम निवारी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734003029/WC/VB/22012035333454 — रुफ वाटर हार्वेस्टिंग कार्य सामुदायिक भवन में ग्राम निवारी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734003029/WC/VB/22012035333456 — रुफ वाटर हार्वेस्टिंग कार्य आंगनवाडी भवन में ग्राम निवारी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734003029/WC/VB/22012035333464 — सोक पिट निर्माण गौशाला में हैण्ड पंप के समीप ग्राम निवारी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734003029/WC/VB/22012035333466 — सोक पिट निर्माण कोली वाली मोहल्ला में हैण्ड पंप के समीप ग्राम निवारी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17
SAIKHEDA (GADARWARA) | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734003029/WC/VB/22012035333467 — सोक पिट निर्माण प्राथमिक शाला में हैण्ड पंप के समीप ग्राम पौडी ग्राम पंचायत निवारी | Approved | 0 | 0 | 2026-07-17