## Work List
Exported on: 2026-10-24 06:38:49
Filters applied:
Data source: VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: KHAIRY
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BABAI CHICHLI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1734004036/DP/22012034492790 — PODHROPAN KARY TALAB KINARE | Ongoing | 390851.61 | 0 | 2020-10-18
BABAI CHICHLI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1734004036/IF/22012034608275 — Falodhan karya Sandhya/Rajesh Kourav | Ongoing | 136000 | 0 | 2020-10-05
BABAI CHICHLI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Construction of Drainage Works in Waterlogged Land for Individual | Land Development | 1734004036/IF/22012034639487 — Khet talab nirman kary dhaniram/imarat | Ongoing | 332962.02 | 0 | 2021-03-02
BABAI CHICHLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Fish Drying Yards for Individual / Construction of Fish Drying Yards for Individual | Construction of Fish Drying Infrastructure | 1734004036/IF/22012035222351 — Khet talab nirman kary pradeep kourav/sahab lal kourav | Ongoing | 311562.99 | 0 | 2024-03-16
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734004036/IF/22012035583863 — Nadep nirman Urmila bai /Narayan Giri | Approved | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734004036/IF/22012035583892 — Nadep nirman Aneeta/Ramesh Thakur | Approved | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734004036/IF/22012035583898 — Nadep nirman Mankuwar /Ajay Rajak | Approved | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734004036/IF/22012035583911 — Nadep nirman Kali / Sukharam Mehra | Approved | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734004036/IF/22012035583918 — Nadep nirman Jamuna /Lal Sahab Gound | Approved | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/4723224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143099286 | Approved | 27000 | 0 | 2024-09-16
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6181192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148946325 | Ongoing | 27000 | 13800 | 2026-08-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6182354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143007053 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6182492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143016804 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6183021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143004579 | Approved | 27000 | 0 | 2026-03-12
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6183292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141963109 | Ongoing | 27000 | 12000 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6183584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143102533 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6186521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144485650 | Ongoing | 27000 | 13800 | 2026-07-17
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6186759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144487554 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6189872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144490391 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6190195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143414642 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6190998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143019379 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6195448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145640976 | Ongoing | 27000 | 13800 | 2026-08-15
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6196599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143081466 | Approved | 27000 | 0 | 2026-03-12
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6197096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144480232 | Ongoing | 27000 | 13800 | 2026-08-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6198734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143047924 | Ongoing | 27000 | 13800 | 2026-08-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6199871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148948424 | Ongoing | 27000 | 13800 | 2026-08-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6200302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143116700 | Ongoing | 27000 | 13800 | 2026-07-03
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6201453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147162150 | Ongoing | 27000 | 13800 | 2026-08-23
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6202958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143143300 | Ongoing | 27000 | 15600 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6208118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143001607 | Ongoing | 27000 | 15600 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6211064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145638867 | Ongoing | 27000 | 13800 | 2026-08-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6211655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148468857 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6213703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143109423 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6214232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143005840 | Ongoing | 27000 | 15900 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6215129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147150380 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6215781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148468907 | Ongoing | 27000 | 15600 | 2026-07-10
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6216263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148468140 | Ongoing | 27000 | 13800 | 2026-07-10
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6274681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142997148 | Approved | 27000 | 0 | 2026-03-12
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6275652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145643444 | Approved | 27000 | 0 | 2026-03-12
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6285531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143002765 | Approved | 27000 | 0 | 2026-05-19
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004036/IF/IAY/6355362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147159948 | Approved | 27000 | 0 | 2025-06-10
BABAI CHICHLI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1734004036/RS/22012035139316 — मुन्नाजी कौरव के मकान से स्वच्छतापरिषर की ओर सीसी नाली निर्माण हिरदेपुर | Approved | 38000 | 0 | 2026-02-04
BABAI CHICHLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734004036/WC/VB/22012035331607 — Rain Water Harvesting Panchayat bhavan ke pass Gram Khairi | Ongoing | 29591.38 | 16800 | 2026-08-15