## Work List
Exported on: 2026-10-27 16:14:04
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: BELKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BABAI CHICHLI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1734004072/DP/22012034584069 — सार्वाजनिक व्रछा रोपण कार्य जैधारी | Closed | 426742.09 | 0 | 2023-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734004072/IF/22012035325841 — Khet talab kary kaluram gound k khet mai | Closed | 204807.55 | 198 | 2025-05-29
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734004072/IF/22012035491044 — खेत तालाब कार्य मनोज शर्मा के खेत मै | Physically Completed | 199758.77 | 63794 | 2025-05-18 | 2026-05-31
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734004072/IF/22012035564021 — KHET TALAB NIRMAN KARYA SANJEEV /LAXMAN KOURAV KE KHET PAR BELKHEDI | Deleted | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734004072/IF/22012035564033 — KHET TALAB NIRMAN KARYA RAMKALI BAI /LAXMAN KOURAV KE KHET PAR BELKHEDI | New | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734004072/IF/22012035564035 — KHET TALAB NIRMAN KARYA RAMKALI BAI /LAXMAN KOURAV KE KHET PAR BELKHEDI | Deleted | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734004072/IF/22012035564042 — KHET TALAB NIRMAN KARYA RAKESH/RAMESH KOURAV KE KHET PAR JAITHARI | Deleted | 0 | 0 | 2025-04-14
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734004072/IF/22012035648262 — khet talab kary gopal kahar / babulal | New | 0 | 0 | 2025-10-02
BABAI CHICHLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4409131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149565872 | Closed | 19890 | 0 | 2023-07-08
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/4661404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149565997 | Ongoing | 27000 | 2100 | 2024-09-13
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/4661405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149566058 | Approved | 27000 | 0 | 2024-09-13
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4757344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118775767 | Completed | 23490 | 20844 | 2025-02-08 | 2026-04-23
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4763922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122190486 | Completed | 23490 | 21384 | 2025-02-08 | 2026-01-14
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4764444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122201600 | Completed | 23490 | 22338 | 2025-02-26 | 2026-04-01
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4764459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122211628 | Completed | 23490 | 22383 | 2025-02-26 | 2026-04-23
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4869892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118857733 | Completed | 23490 | 21627 | 2025-02-08 | 2026-01-14
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4871091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122175511 | Completed | 23490 | 21384 | 2025-02-08 | 2026-01-14
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/4871094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122210975 | Physically Completed | 23490 | 17793 | 2025-02-26 | 2026-04-12
BABAI CHICHLI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734004072/IF/IAY/5843504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122014982 | Physically Completed | 23490 | 15921 | 2026-02-01 | 2026-05-31
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6258692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121982836 | Ongoing | 27000 | 3600 | 2026-10-08
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6258698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121990888 | Approved | 27000 | 0 | 2026-04-24
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6259277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122014627 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6259389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122207811 | Ongoing | 27000 | 3600 | 2026-10-08
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6259498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122168648 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6285200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122332046 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6285827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122005048 | Approved | 27000 | 0 | 2026-04-24
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6295331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123722309 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6296478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122222866 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6300872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122174728 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6301466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122005388 | Approved | 27000 | 0 | 2026-04-24
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6301675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122326088 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6301676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122326177 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6301677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122326254 | Approved | 27000 | 0 | 2026-04-15
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6324257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121978589 | Ongoing | 27000 | 3600 | 2026-10-08
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6324430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122186710 | Approved | 27000 | 0 | 2026-04-24
BABAI CHICHLI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6324553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122167928 | Approved | 27000 | 0 | 2026-04-24
BABAI CHICHLI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734004072/IF/IAY/6389136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122326523 | Approved | 27000 | 0 | 2025-03-07
BABAI CHICHLI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1734004072/RC/22012034841582 — खेत सडक निर्माण कार्य बेलखेड़ी से भैरोपुर की ओर | Ongoing | 1769000 | 1735053.66 | 2025-05-30
BABAI CHICHLI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1734004072/WC/22012035006710 — नवीन तालाब बेलखेडी | Completed | 1464978.39 | 578098.41 | 2022-11-20 | 2026-05-24
BABAI CHICHLI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1734004072/WC/22012035078146 — Dug pond nirman jaithari | Ongoing | 507941.31 | 127296 | 2023-06-13
BABAI CHICHLI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1734004072/WC/22012035095967 — Sokta gadda nirmad 5 nag | Completed | 89531.05 | 82626 | 2023-08-12 | 2024-12-21
BABAI CHICHLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734004072/WC/VB/22012035331453 — CONTRUCTION OF ROOP TOP RAIN HARVESTING SYSTEM FOR PANCHAYAT BHAWAN BELKHEDI 1 | Approved | 0 | 0 | 2026-07-20
BABAI CHICHLI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734004072/WC/VB/22012035331455 — CONTRUCTION OF ROOP TOP RAIN HARVESTING SYSTEM FOR PANCHAYAT BHAWAN BELKHEDI 2 | Approved | 0 | 0 | 2026-07-20