## Work List
Exported on: 2026-09-07 05:04:42
Filters applied:
Data source: VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: DOKARGHAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARSIMHAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1734005040/FP/22012034640729 — पुलिया निर्माण कार्य हरिजन मोहल्ला डोकरघाट | Approved | 0 | 0 | 2024-06-12
NARSIMHAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1734005040/FP/22012034640730 — पुलिया निर्माण कार्य सिद्ध बाबा मंदिर के पास डोकरघाट | Approved | 0 | 0 | 2024-06-12
NARSIMHAPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1734005040/FP/22012034640731 — पुलिया निर्माण कार्य सीताराम कुर्मी के खेत के पास डोकरघाट | Approved | 0 | 0 | 2024-06-12
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734005040/IF/22012035264953 — खेत तालाब निर्माण कार्य शिवप्रसाद चौधरी पिता श्री लक्ष्मण के खेत में डोकरघाट | Approved | 0 | 0 | 2024-10-05
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734005040/IF/22012035264957 — खेत तालाब निर्माण कार्य मुन्नी बाई चौधरी पति श्री डब्बल के खेत में डोकरघाट | Approved | 0 | 0 | 2024-10-05
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734005040/IF/22012035264962 — खेत तालाब निर्माण कार्य रज्जो बाई ठाकुर पति स्व० श्री मोतीलाल के खेत में सेमरा | Approved | 391060.53 | 0 | 2024-10-05
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1734005040/IF/22012035266292 — खेत तालाब निर्माण कार्य हेमराज ठाकुर पिता स्व श्री टीकाराम ठाकुर के खेत में डोकरघाट | Approved | 0 | 0 | 2024-10-05
NARSIMHAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/1099354 — Construction of IAY House -IAY REG. NO. MP3852237 | Ongoing | 27000 | 0 | 2026-08-04
NARSIMHAPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/2296312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2094428 | Approved | 27000 | 0 | 2019-08-01
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/3836395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122268158 | Ongoing | 27000 | 0 | 2025-09-18
NARSIMHAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/3836425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122275488 | Approved | 27000 | 0 | 2022-05-02
NARSIMHAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/3836426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122275553 | Approved | 27000 | 0 | 2022-05-02
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/3852117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128726908 | Ongoing | 27000 | 0 | 2025-09-18
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/4679461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133189487 | Ongoing | 27000 | 0 | 2024-12-02
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/4679492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133462487 | Completed | 23490 | 0 | 2025-01-06 | 2026-08-02
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/4699140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119388547 | Completed | 23490 | 0 | 2024-12-02 | 2026-08-01
NARSIMHAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/4787702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133463933 | Completed | 23490 | 0 | 2025-01-06 | 2026-08-02
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5488648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120366159 | Completed | 23490 | 0 | 2025-04-22 | 2026-08-05
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5488816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128728145 | Ongoing | 27000 | 0 | 2025-04-22
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5595832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122266228 | Ongoing | 27000 | 0 | 2025-05-06
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5656899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120685837 | Completed | 23490 | 0 | 2025-08-18 | 2026-08-05
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5706465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132986757 | Completed | 23490 | 0 | 2025-08-18 | 2026-08-05
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5710266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122266538 | Ongoing | 27000 | 0 | 2025-08-21
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5710650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120367019 | Ongoing | 27000 | 0 | 2025-08-18
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5760749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133509060 | Ongoing | 27000 | 0 | 2025-09-18
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119292710 | Ongoing | 27000 | 0 | 2025-09-18
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128674369 | Completed | 23490 | 0 | 2025-08-28 | 2026-08-05
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133185346 | Ongoing | 27000 | 0 | 2025-08-28
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133197655 | Ongoing | 27000 | 0 | 2025-08-28
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122266388 | Ongoing | 27000 | 0 | 2025-09-18
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132984238 | Ongoing | 27000 | 0 | 2025-08-28
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122291242 | Ongoing | 27000 | 0 | 2025-09-11
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5772922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122291513 | Completed | 23490 | 0 | 2025-08-28 | 2026-07-28
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5773201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122264785 | Ongoing | 27000 | 8400 | 2025-09-18
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5773257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122275724 | Ongoing | 27000 | 0 | 2025-08-28
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5773765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119093254 | Completed | 23490 | 0 | 2025-08-28 | 2026-08-05
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5774289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119623592 | Completed | 23490 | 0 | 2025-08-28 | 2026-08-05
NARSIMHAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/5927321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119623220 | Ongoing | 27000 | 4200 | 2026-08-04
NARSIMHAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734005040/IF/IAY/6094618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133494572 | Approved | 27000 | 0 | 2026-01-28
NARSIMHAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair-maint Interlocking block/tiles roads-Comm / Repair and maintenance of Inter-locking cement block/tiles Roads for Community | Repair & maint of Road | 1734005040/RC/22012034620822 — Nali Nirman RCC Drain Tushiram ke Ghar se Bheroprasad ke Ghar ki aur | Ongoing | 27000 | 0 | 2024-03-17
NARSIMHAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1734005040/RC/22012034628749 — सी0सी0रोड नाली निर्माण बजीर खान के घर से कुक्कू चैधरी तक पंचायत डोकरघाट | Ongoing | 36000 | 0 | 2024-03-17
NARSIMHAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1734005040/RS/22012034689307 — नाली निर्माण कार्य माखन कुर्मी के घर से मुकेश सेन के घर की ओर पंचायत डोकरघाट | Ongoing | 55000 | 0 | 2023-07-12
NARSIMHAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734005040/WC/22012035203352 — तालाब विस्तारीकरण डोकरघाट | Approved | 0 | 0 | 2024-06-08
NARSIMHAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734005040/WC/22012035203363 — तालाब विस्तारीकरण सेमरा ग्राम पंचायत डोकरघाट | Approved | 0 | 0 | 2024-06-08
NARSIMHAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1734005040/WC/22012035210675 — चेक डेम -1 निर्माण कार्य डोकरघाट | Approved | 0 | 0 | 2024-06-12
NARSIMHAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1734005040/WC/22012035210683 — चेक डेम -2 निर्माण कार्य डोकरघाट | Approved | 0 | 0 | 2024-06-12