## Work List
Exported on: 2026-09-06 10:17:17
Filters applied:
Data source: VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: JANOUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KARELI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of minor Canal for Community / Repair and Maintenance of minor Canal for Community | Repair & Maint of Canal | 1734006033/IC/22012034884218 — nahar safai karya satyam ke khet se ramji ke khet ki or janour | Ongoing | 169436 | 0 | 2024-03-16
KARELI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of minor Canal for Community / Repair and Maintenance of minor Canal for Community | Repair & Maint of Canal | 1734006033/IC/22012034884219 — nahar safai karya balram kotwar ke khet se arvind ke khet ki or | Ongoing | 171686 | 0 | 2024-03-16
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734006033/IF/22012035628573 — Ek Bagiya maa ke naam vandana choudhari MP-34-006-033-001/249 | Ongoing | 182953.68 | 0 | 2025-10-29
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734006033/IF/22012035629395 — EK BAGIYA MAA KE NAAM NARAMADA SHG JANOUR LAXMI 125718017 | Ongoing | 182943.09 | 0 | 2025-10-29
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734006033/IF/22012035632188 — EK BAGIYA MAA KE NAAM SHIVAY SHG JANOUR LASHMIBAI 130106578 | Ongoing | 182943.09 | 0 | 2025-10-29
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734006033/IF/22012035632195 — EK BAGIYA MAA KE NAAM PUJA SHG MAMTA BAI KURMI 141273330 | Ongoing | 182943.09 | 0 | 2025-10-29
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734006033/IF/22012035650596 — Ek bagiya maa ke naam kala bai | Ongoing | 182924.62 | 0 | 2026-01-14
KARELI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/4242293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106011803 | Ongoing | 27000 | 0 | 2022-07-31
KARELI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/4407457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133514266 | Approved | 27000 | 0 | 2022-10-29
KARELI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/4590622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120853660 | Approved | 27000 | 0 | 2024-09-13
KARELI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/4748443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114814496 | Approved | 27000 | 0 | 2024-09-26
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/5136651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105973518 | Ongoing | 27000 | 0 | 2025-12-08
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/5140961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133432031 | Ongoing | 27000 | 0 | 2025-12-08
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/5758637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121438579 | Physically Completed | 23490 | 0 | 2025-09-02 | 2026-08-16
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/5803199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105973540 | Approved | 27000 | 0 | 2025-04-04
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/6178010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113877788 | Approved | 27000 | 0 | 2026-03-24
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/6181801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120229450 | Approved | 27000 | 0 | 2026-03-24
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/6182610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106837684 | Approved | 27000 | 0 | 2026-03-24
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/6184218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106837877 | Approved | 27000 | 0 | 2026-03-24
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/6198305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106721124 | Approved | 27000 | 0 | 2026-03-24
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1734006033/IF/IAY/6209742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106011628 | Approved | 27000 | 0 | 2026-03-24
KARELI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1734006033/RC/22012034530270 — NALI NIRMAAN KARYA NHAR SE NALE TAK KATHOTIYA PAHUCH MARG PAR JANOUR | Ongoing | 171923.19 | 0 | 2022-05-27
KARELI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1734006033/WC/22012034944087 — NALA GAHRIKARAN KARYA ANGANWADI KE PASS SE SHANTIDHAM KI OR JANOUR | Ongoing | 196490.45 | 0 | 2022-05-20
KARELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734006033/WC/VB/22012035331715 — Handpump ke pass soak pit nirman | Approved | 0 | 0 | 2026-06-26
KARELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734006033/WC/VB/22012035332315 — Handpump ke pass soak pit nirman 2 | Approved | 0 | 0 | 2026-06-26
KARELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734006033/WC/VB/22012035332316 — Handpump ke pass soak pit nirman 3 | Approved | 0 | 0 | 2026-06-26
KARELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1734006033/WC/VB/22012035332317 — Handpump ke pass soak pit nirman 4 | Approved | 0 | 0 | 2026-06-26
KARELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734006033/WC/VB/22012035332318 — Construction of Roof top Rain water harvesting work | Approved | 0 | 0 | 2026-06-26