## Work List
Exported on: 2026-10-28 23:06:16
Filters applied:
Data source: VBGRAMG
District: NARSINGHPUR
Block: All
Panchayat: KANDHRAPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KARELI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1734006044/AV/22012034628825 — आंगनवाड़ी सह बाउंड्रीबॉल निर्माण कार्य ग्राम-रहली | Physically Completed | 500000 | 0 | 2023-04-19 | 2026-07-25
KARELI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1734006044/AV/22012034629840 — आंगनवाड़ी सह बाउंड्रीबॉल निर्माण कार्य ग्राम-कंधरापुर | Ongoing | 328000 | 0 | 2023-04-19
KARELI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1734006044/IF/22012034467636 — RFR BARUREWA RIVER PUNARJIVAN NEW KHET TALAB HITGRAHI VANDANA / MAHENDRA SINGH GHOSHI | Ongoing | 288000 | 0 | 2019-03-02
KARELI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1734006044/IF/22012034593905 — निजी भूमि पर फलोद्यान कार्य रामचंद्र / विजय घोषी कंधरापुर | Ongoing | 139000 | 0 | 2020-08-15
KARELI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/1868792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3187961 | Ongoing | 27000 | 0 | 2018-08-22
KARELI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/4643298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136516829 | Ongoing | 27000 | 2100 | 2024-10-09
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/5155262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148692510 | Ongoing | 27000 | 0 | 2025-04-24
KARELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/5173608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150699465 | Ongoing | 27000 | 4200 | 2025-04-24
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6145803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106272459 | Physically Completed | 27000 | 9300 | 2026-05-08 | 2026-09-13
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6248235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106272981 | Ongoing | 27000 | 6600 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6248345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106272527 | Ongoing | 27000 | 3300 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6248347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106272584 | Ongoing | 27000 | 4500 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6256206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118810005 | Ongoing | 27000 | 3300 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6256566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118866730 | Ongoing | 27000 | 2100 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6257083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119866285 | Approved | 27000 | 0 | 2026-04-23
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6257325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119365369 | Ongoing | 27000 | 3300 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6257649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119830750 | Ongoing | 27000 | 2100 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6259349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121618539 | Ongoing | 27000 | 2100 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6277438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148855501 | Ongoing | 27000 | 2100 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6277442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148858823 | Approved | 27000 | 0 | 2026-04-23
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6300910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119352694 | Ongoing | 27000 | 6600 | 2026-10-09
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6306030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118866338 | Ongoing | 27000 | 2100 | 2026-10-08
KARELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/6306709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121593202 | Ongoing | 27000 | 6600 | 2026-10-09
KARELI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1734006044/IF/IAY/830369 — Construction of IAY House -IAY REG. NO. MP3505486 | Approved | 27000 | 0 | 2017-04-20
KARELI | 2026-2027 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1734006044/IF/VB/YD/22012035665380 — Construction of Soak Pit for 2 KANDHRAPUR | New | 0 | 0 | 2026-10-10
KARELI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1734006044/RC/22012034658894 — सी सी रोड शांतिधाम से महेंद्र घोषी के घर की ओर ग्राम कंधरापुर | Ongoing | 56000 | 0 | 2025-05-23
KARELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734006044/WC/VB/22012035332180 — Rain water Harvesting kary samudayak bhavan ke pass | Ongoing | 30496.65 | 300 | 2026-08-28
KARELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1734006044/WC/VB/YD/22012035336660 — ROOF TOP RAIN WATER HARWESTING IN PANCHAYAT BHAWAN KANDHRAPUR | Ongoing | 30496.65 | 300 | 2026-10-14