## Work List
Exported on: 2026-10-25 11:29:14
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: MADHOGARH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1735002010/DP/22012034584238 — सार्वजनिक वृक्षारोपण कार्य - तालाब किनारे कोन्ड्रा वन ग्राम | Ongoing | 629581.63 | 56820 | 2024-06-10
NARAYANGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1735002010/IF/22012035282832 — परकोलेशन टेंक निर्माण - हित. कलसिया बाई / देवी सिंह ग्राम पंचा0 माडोगढ | Ongoing | 199747.95 | 0 | 2025-02-04
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002010/IF/22012035461896 — KHET TALAB NIRMAN KARYA BISAN SINGH /KOMAL GP MADOGARH | Ongoing | 333010.72 | 0 | 2025-05-12
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002010/IF/22012035630615 — EK BAGIYA MAA KE NAM RAMI BAI / SHAMBHU SINGH PANDRAM | Ongoing | 186917.19 | 230 | 2025-10-30
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002010/IF/22012035630691 — EK BAGIYA MAA KE NAM CHANDRAWATI PARASTE / DHANNILAL | Ongoing | 283818.41 | 230 | 2025-10-30
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002010/IF/22012035633995 — MAA KI BAGIYA NIRMAN KARY MOOLWATI MARAVI | Approved | 283818.41 | 0 | 2025-10-02
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002010/IF/22012035633997 — MAA KI BAGIYA NIRMAN KARY BASANTI BAI | Approved | 283818.41 | 0 | 2025-10-02
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002010/IF/22012035633999 — EK BAGIYA MAA KE NAM ANJANA MARAVI | Approved | 283818.41 | 0 | 2025-10-02
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735002010/IF/22012035653360 — Eak Bagiya Maa Ke Nam Hiteshi Kaliya Bai / Budhhu Madogharh | New | 0 | 0 | 2025-08-15
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002010/IF/22012035656364 — Parkuleshan Tenk hit Shobhan Singh /Bakhat GP madogarh | Ongoing | 176361 | 12572.13 | 2026-02-09
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002010/IF/22012035656541 — Khet Talab Nirman karya Bharat GP Madogarh | Approved | 269377.97 | 0 | 2025-10-02
NARAYANGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735002010/IF/22012035656546 — Khet Talab Nirman karya Ramoti GP Madogarh | Approved | 0 | 0 | 2025-10-02
NARAYANGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735002010/IF/IAY/4661230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148725354 | Approved | 28500 | 0 | 2024-09-13
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individual | Construction of Check Dam/Stop Dam | 1735002010/IF/VB/YD/22012035665765 — Constr of Boulder Check Dam for 2s pahalvati ke khet ke pass | New | 0 | 0 | 2026-08-15
NARAYANGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1735002010/WC/22012035300121 — JGA DUPLICATE | Approved | 0 | 0 | 2025-04-14
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002010/WC/VB/22012035330944 — Construction Of Gabion Structure Dadri Nala Kehar Ke Khet Ke pass GP Madhogarh | Ongoing | 394632.65 | 207 | 2026-08-14
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002010/WC/VB/22012035330946 — Construction Of Gabion Structure Chhoti Dadri Nala Puran Ke Khet Ke pass GP Madhogarh | Approved | 0 | 0 | 2026-07-26
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002010/WC/VB/22012035330947 — Construction Of Gabion Structure Khandoti Nala Foulvati Ke Khet Ke pass GP Madhogarh | Approved | 0 | 0 | 2026-07-26
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002010/WC/VB/22012035330948 — Construction Of Gabion Structure Mukaddam Kol Nala Basori Ke Khet Ke pass GP Madhogarh | Approved | 0 | 0 | 2026-07-26
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735002010/WC/VB/22012035330950 — Construction Of Gabion Structure Kovakol Nala Chhotelal Ke Ghar Ke pass GP Madhogarh | Approved | 0 | 0 | 2026-07-26
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002010/WC/VB/22012035330953 — Construction Of Staggrerd Contur Trench Kova Dadri GP Madhogarh | Ongoing | 381989.61 | 125900 | 2026-09-20
NARAYANGANJ | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735002010/WC/VB/22012035330954 — Construction Of Staggrerd Contur Trench Badi Dadri GP Madhogarh | Ongoing | 456083.71 | 222571 | 2026-08-14