## Work List
Exported on: 2026-09-08 17:11:33
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: MAJHGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NIWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735003034/DP/22012034564020 — samudayik plantation shanti dham parisar jilhata | Ongoing | 408000 | 0 | 2022-08-24
NIWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1735003034/DP/22012034564021 — samudayik plantation majhgaon marg se jalashaye tak | Ongoing | 713000 | 0 | 2022-08-24
NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735003034/IF/22012035562138 — CATTLE SHED RANJEET YADAV / SANTOSHI LAL | Approved | 125753.69 | 0 | 2025-04-15
NIWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003034/IF/IAY/4791176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144177703 | Ongoing | 28500 | 0 | 2024-11-25
NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003034/IF/IAY/5208843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142256502 | Ongoing | 28500 | 0 | 2025-04-02
NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003034/IF/IAY/5593884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144178419 | Ongoing | 28500 | 0 | 2025-05-10
NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003034/IF/IAY/5651592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094721 | Ongoing | 28500 | 0 | 2025-06-06
NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003034/IF/IAY/5678290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142545290 | Ongoing | 28500 | 0 | 2025-06-24
NIWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735003034/IF/IAY/5678340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146804125 | Ongoing | 28500 | 0 | 2025-06-24
NIWAS | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1735003034/RC/22012034675678 — Gereval road | New | 0 | 0 | 2025-01-26
NIWAS | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1735003034/RC/22012034675679 — Gereval road | New | 0 | 0 | 2025-01-26
NIWAS | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1735003034/RC/22012034675680 — Gereval road | New | 0 | 0 | 2025-01-26
NIWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012034871385 — CTR construction of Stopdam nagrar nala Majhgaon | Ongoing | 1403832.1 | 0 | 2022-02-03
NIWAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1735003034/WC/22012035055429 — Sarvjanik koop nirman Khermai ke niche Majhgaon | Ongoing | 524980.32 | 0 | 2023-06-06
NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035231831 — Boldar check dem jilhta | New | 0 | 0 | 2024-12-17
NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035241684 — boldar chek dem jilhta 1 | New | 0 | 0 | 2024-07-10
NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035241689 — boldar chek dem jilhta no1 | New | 0 | 0 | 2025-01-01
NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035241702 — Boldar chek dem jilhta no. 1 | New | 0 | 0 | 2025-01-01
NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035253234 — boldar chek dem jilhta nala 6 | Approved | 0 | 0 | 2025-01-26
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735003034/WC/22012035289249 — savjanik koop majhgaon Recharge | Approved | 0 | 0 | 2025-04-28
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735003034/WC/22012035289256 — savjanik koop jilhta rechage | Approved | 0 | 0 | 2025-04-28
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1735003034/WC/22012035290528 — JGA SARVJANIK DUCKWELL NIRMAD MAJHGAON TOLA | New | 0 | 0 | 2025-04-28
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1735003034/WC/22012035301537 — JGSA 2025 Recharge Struture Sarvjanik koop Jilhta | New | 0 | 0 | 2025-05-07
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320932 — गली प्लग निर्माण कार्य बूची कगार नाला ग्राम जिल्हटा ग्राम पंचायत मझगांव। | Ongoing | 499951.36 | 5217.16 | 2026-02-27
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320933 — गली प्लग निर्माण कार्य झिगरा नाला ग्राम जिल्हटा ग्राम पंचायत मझगांव। | Approved | 0 | 0 | 2025-08-15
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320934 — बोल्डर चेकडैम निर्माण कार्य झिगरा नाला ग्राम जिल्हटा ग्राम पंचायत मझगांव। | Approved | 497723.12 | 0 | 2025-08-15
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320935 — गली प्लग निर्माण कार्य शांतिधाम नाला ग्राम जिल्हटा ग्राम पंचायत मझगांव। | Approved | 0 | 0 | 2025-08-15
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320938 — गली प्लग निर्माण कार्य पीपरपानी नाला ग्राम व ग्राम पंचायत मझगांव। | Approved | 0 | 0 | 2025-08-15
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320939 — गली प्लग निर्माण कार्य छापर नाला ग्राम व ग्राम पंचायत मझगांव। | Ongoing | 479182.63 | 430.04 | 2026-02-13
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320941 — गली प्लग निर्माण कार्य नगरार नाला ग्राम व ग्राम पंचायत मझगांव। | Approved | 0 | 0 | 2025-08-15
NIWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/22012035320942 — बोल्डर चेकडैम निर्माण कार्य नगरार नाला ग्राम व ग्राम पंचायत मझगांव। | Approved | 0 | 0 | 2025-08-15
NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/VB/22012035332334 — Constructions Of Boulder Check Dam Jilahta Nala Gram Jilahta | Approved | 0 | 0 | 2026-06-24
NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/VB/22012035332335 — Constructions Of Boulder Check Dam Majhgaon Nala Gram Majhgaon | Approved | 0 | 0 | 2026-06-24
NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/VB/22012035332336 — Constructions Of Boulder Check Dam Buchi Kagar Nala Gram Jilahta | Approved | 0 | 0 | 2026-06-24
NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/VB/22012035332812 — Bolder chek dem jilhta bhuchgagar | Approved | 0 | 0 | 2026-08-07
NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/VB/22012035332814 — Bolder chek dem jilhta nala ke pas | Approved | 0 | 0 | 2026-08-07
NIWAS | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735003034/WC/VB/22012035332815 — Bolder chek dem majhgaon shanti dham ke pas | Approved | 0 | 0 | 2026-08-07
NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1735003034/WH/22012034942377 — bolder chek dem | Approved | 0 | 0 | 2024-04-15
NIWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1735003034/WH/22012034942379 — boldar chek dem jilhta nala no1 | New | 0 | 0 | 2024-11-16