## Work List
Exported on: 2026-10-02 00:03:37
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: FULSAGAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1735004008/DP/22012034559875 — वृक्षारोपण कार्य अमृत सरोवर तलाब में पडरिया | Ongoing | 411218.19 | 9010.31 | 2022-08-09
MANDLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1735004008/DP/22012034617870 — शांतिधाम फूलसागर में वृक्षारोपण कार्य | Ongoing | 246319.07 | 16417.21 | 2024-06-26
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004008/IF/22012034595838 — CAITAL SET NIRMAN KARY RAJJO BAI / DUMARI LAL | Ongoing | 101804.91 | 0 | 2021-01-13
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004008/IF/22012034638953 — केटल शेट दुर्गा बाई / ओमकार सिंह फूलसागर | Ongoing | 63830.2 | 0 | 2021-02-03
MANDLA | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1735004008/IF/22012034944611 — 5नाडेप टेंक निर्माण कार्य ग्राम बम्होरी(श्रीरामसैयाम, संतोषयादव, विजययादव, छोटेलालयादव, राजूयादव) | Ongoing | 89350.59 | 0 | 2022-07-28
MANDLA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004008/IF/22012035107160 — केटल शेड निर्माण कार्य कमला प्रसाद/बलदेब प्रसाद यादव | Ongoing | 127046.98 | 0 | 2024-03-01
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004008/IF/22012035629153 — Ek Bagiya Maa Ke Naam chandvati /bhola gram padariya gram panchayat Fulsagar | Ongoing | 198967.77 | 4420.8 | 2025-10-29
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004008/IF/22012035629159 — Ek Bagiya Maa Ke Naam chandvati /bhola gram padariya gram panchayat Fulsagar | New | 0 | 0 | 2025-08-01
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004008/IF/22012035635980 — Ek Bagiya Maa Ke Naam sunita warkade / Hind lal warkade gram padariya gram panchayat Fulsagar | Ongoing | 268739.2 | 7111.65 | 2025-10-31
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004008/IF/22012035661476 — Khet Talab Nirman Kary Shivratan So Murari Masram | New | 0 | 0 | 2026-01-27
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004008/IF/22012035661769 — Khet Talab Nirman Kary Chainsingh /Pooran Lal Padariya | New | 0 | 0 | 2026-01-27
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004008/IF/22012035661772 — Khet Talab Nirman Kary Chainsingh /Pooran Lal Padariya | New | 0 | 0 | 2026-01-27
MANDLA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004008/IF/IAY/4089263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124825969 | Approved | 28500 | 0 | 2022-05-12
MANDLA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004008/IF/IAY/4418078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151877148 | Ongoing | 28500 | 0 | 2024-03-05
MANDLA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004008/IF/IAY/468246 — Construction of IAY House -IAY REG. NO. MP1801057 | Approved | 28500 | 0 | 2017-01-24
MANDLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004008/WC/22012034970055 — JAA स्टाप डेम निर्माण कार्य फलोद्यान के पास पडरिया | Ongoing | 1417774 | 0 | 2022-05-27
MANDLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735004008/WC/22012035177578 — Gabion structure | New | 0 | 0 | 2024-01-26
MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735004008/WC/VB/22012035335400 — GEBION STRUCTURE NIRMAN KARY JANGAL NALA ROHIT KE KHET PASS SHIJHOURI PADARIYA | Approved | 0 | 0 | 2026-08-19