## Work List
Exported on: 2026-10-01 08:58:29
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: PATPARARAIYAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735004023/DP/22012034566592 — Patpararaiyat - Block Plantion At Near of Talab Junamandla | Ongoing | 713000 | 11713 | 2022-09-06
MANDLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1735004023/DP/22012034619586 — Patparraiyat - Plantation At Junamandla | Ongoing | 99388.73 | 0 | 2024-07-13
MANDLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1735004023/DP/22012034630592 — PATPRARAIYAT ME MAA NARMADA PARIKRAMA KE ASHRYA STHAL KE PASS PALANTATION KARYA JUNAMANDLA | Ongoing | 441828.46 | 9068 | 2025-11-12
MANDLA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1735004023/FP/22012034636172 — Patparaiyat - Jal nikasi nali nirman Dindori Road Se Patparamal Tak dono said | Ongoing | 162738.99 | 0 | 2023-10-07
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004023/IF/22012034593151 — patpararaiyat cattle shed dasonda/mangal | Ongoing | 101273.16 | 0 | 2020-09-02
MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1735004023/IF/22012034594754 — patpararaiyat poltry shed uma /rajesh | Ongoing | 51554.19 | 0 | 2021-12-31
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004023/IF/22012034594758 — patpararaiyat cattle shed kamla/dhaniram | Ongoing | 101273.16 | 0 | 2020-12-19
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004023/IF/22012034594766 — patpararaiyat cattle shed gomti nareti | Ongoing | 101273.16 | 0 | 2020-12-19
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004023/IF/22012034594780 — patpararaiyat cattle shed kamalsingh/chaitu tekam | Ongoing | 63531.21 | 0 | 2021-01-02
MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004023/IF/22012034594784 — patpararaiyat cattle shed jagdish/mishrilal | Ongoing | 101273.16 | 0 | 2021-12-07
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004023/IF/22012034595012 — patpararaiyat cattle shed kishan/sudhhu | Ongoing | 63531.21 | 0 | 2020-12-01
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735004023/IF/22012034595024 — patpararaiyat cattle shed sampat/gorelal | Ongoing | 101273.16 | 0 | 2020-11-19
MANDLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004023/IF/22012035266105 — Khet Talab Sukru / Kanhaiya Patpraraiyat | New | 0 | 0 | 2024-10-18
MANDLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004023/IF/22012035282176 — Khet Talab Kiran / Kaliram Patpraraiyat | Approved | 0 | 0 | 2024-10-18
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004023/IF/22012035305540 — Khet Talab Panchulal / Baisakhu Patpraraiyat | Ongoing | 446272.88 | 0 | 2025-04-26
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004023/IF/22012035423933 — Khet Talab Devki bai / Shivcaran Patpraraiyat | Ongoing | 431677.04 | 0 | 2025-05-13
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004023/IF/22012035423963 — Khet Talab Nanhelal / Subhecha Patpraraiyat | New | 0 | 0 | 2025-04-20
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735004023/IF/22012035521586 — khet talab nirman kar pusu/nirottam | Ongoing | 470772.42 | 0 | 2025-05-17
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004023/IF/22012035628020 — EK Bagiya maa ke Name khamahariya premvati /sukal shingh | New | 0 | 0 | 2025-10-02
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004023/IF/22012035628027 — EK Bagiya maa ke Name khamahariya premvati /sukal shingh | Ongoing | 173110.03 | 0 | 2025-10-28
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735004023/IF/22012035658223 — Ek Bagiya Maa Ke Naam Vidhiya bai/suddhu singh gram panchayat Patpara rayat | Ongoing | 170144.04 | 0 | 2026-01-22
MANDLA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/1544917 — Construction of IAY House -IAY REG. NO. MP3971080 | Ongoing | 28500 | 0 | 2018-06-01
MANDLA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/3151783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4088594 | Approved | 28500 | 0 | 2020-11-11
MANDLA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/3425062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5040245 | Approved | 28500 | 0 | 2021-11-30
MANDLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/4631897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128626091 | Ongoing | 28500 | 0 | 2024-11-07
MANDLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/4780400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128619796 | Ongoing | 28500 | 2100 | 2024-11-07
MANDLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/4910205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123892762 | Ongoing | 28500 | 5400 | 2025-03-11
MANDLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/4911628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125554126 | Physically Completed | 28500 | 600 | 2025-03-11 | 2026-09-13
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/4911634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125560674 | Ongoing | 28500 | 2400 | 2025-06-14
MANDLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/4911979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128626843 | Ongoing | 28500 | 0 | 2025-02-27
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/5087785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128624592 | Ongoing | 28500 | 1200 | 2025-07-28
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/5577602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121783232 | Ongoing | 28500 | 5100 | 2025-05-17
MANDLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735004023/IF/IAY/5872647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123169693 | Ongoing | 28500 | 7200 | 2026-02-17
MANDLA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1735004023/RS/22012034645229 — Patpararaiyat SLMW Indidual Soak pit 05 Kodulal, Mansing, Pulsing, Parwat, | Ongoing | 52056.07 | 0 | 2022-04-11
MANDLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735004023/WC/22012035020242 — JAA Patpararaiyat - Contour Trench Junamandla Pahadi mai Part 2 | Ongoing | 236168.77 | 0 | 2022-12-04
MANDLA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004023/WC/22012035177521 — SEMRA GHAT NALA MEN BOULDER CHEK DEM | New | 0 | 0 | 2024-01-26
MANDLA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1735004023/WC/22012035306570 — patpararaiyat dugwell recharege structure sarv janik koop nala ke pass | Ongoing | 25899.46 | 0 | 2025-05-17
MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735004023/WC/VB/22012035332520 — Gabion structure nirman karya rani chiriya k pass juna mandla | Approved | 0 | 0 | 2026-04-15
MANDLA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735004023/WC/VB/22012035332971 — boulder chack dam nirman karya khail madan junamandla | Approved | 0 | 0 | 2026-07-18