## Work List
Exported on: 2026-09-11 20:44:16
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: MADHOPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1735005044/DP/22012034618795 — प्राथमिक स्वास्थ्य केंद्र माधोपुर वृक्ष रोपण कार्या | Ongoing | 313189.07 | 0 | 2024-07-21
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1735005044/DP/22012034618796 — सरकारी तालाब माधोपुर वृक्ष रोपण कार्या | Ongoing | 309689.07 | 0 | 2024-07-21
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1735005044/DP/22012034629830 — Vriksharopan Kary Balak Chatrawas Madhopur | Deleted | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1735005044/DP/22012034629831 — Vriksharopan Kary Viklaang Chatrawas Madhopur | Deleted | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1735005044/DP/22012034629832 — Vriksharopan Kary Girls Middle School Madhopur | Deleted | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1735005044/DP/22012034629833 — Vriksharopan Kary Boys Middle School Madhopur | Deleted | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1735005044/DP/22012034629834 — Vriksharopan Kary Higher Secoundry School Madhopur | Deleted | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1735005044/DP/22012034629835 — Vriksharopan Kary Neher Kinare Muktidham Madhopur | Deleted | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Grass Land Development and Silvi-pasture / Development of Silvipasture Grassslands for Community | Grass Land Development | 1735005044/DP/22012034629837 — Vriksharopan Kary Pashu Charagah Madhopur | Deleted | 0 | 0 | 2025-04-12
BICHHIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735005044/IF/22012034624640 — pashu shed nirman kary AHILYA/ASHOK GP MADHOPUR | Ongoing | 63830.2 | 0 | 2020-11-12
BICHHIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735005044/IF/22012035242282 — Pashu Shed Nirmaan Karya Geetanjli Patel / Dhaneshwar Patel | Approved | 0 | 0 | 2024-06-19
BICHHIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735005044/IF/22012035242287 — Pashu Shed Nirmaan Karya Aasish Patel/ Radhe Lal | Approved | 0 | 0 | 2024-06-19
BICHHIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735005044/IF/22012035242296 — Pashu Shed Nirmaan Karya Puniya Bai/ Ganesh | Approved | 0 | 0 | 2024-06-19
BICHHIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735005044/IF/22012035242302 — Pashu Shed Nirmaan Karya Manka Bhanwre/Gendu lal | Approved | 0 | 0 | 2024-06-19
BICHHIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735005044/IF/22012035242304 — Pashu Shed Nirmaan Karya Brijlal Jhangela/ Pyare lal | Approved | 0 | 0 | 2024-06-19
BICHHIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1735005044/IF/22012035242306 — Pashu Shed Nirmaan Karya Roshni Bai / Ramkumar | Approved | 0 | 0 | 2024-06-19
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735005044/IF/22012035408090 — खेत तालाब निर्माण कार्य रामकृष्ण/कुंजबिहारी कार्तिकेय | Physically Completed | 236028.18 | 0 | 2025-05-17 | 2026-09-09
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1735005044/IF/22012035408263 — Recharge Structure Kapildhara Koop Gulso Bai Patel | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1735005044/IF/22012035408286 — Recharge Structure Kapildhara Koop Balkishor Markam | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1735005044/IF/22012035408316 — Recharge Structure Kapildhara Koop Laxman Barkade | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1735005044/IF/22012035408325 — Recharge Structure Kapildhara Koop Aghan Lal | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1735005044/IF/22012035434819 — Recharge Structure Kapildhara Koop Santosh Kachhwaha/ Kaliram | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735005044/IF/22012035651327 — Khet Talab Nirmaan Karya Savita Patel/ Mohan Patel | New | 0 | 0 | 2025-07-15
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735005044/IF/22012035659613 — Khet Talab Nirman Karya Laxman Warkade/ Thunu | Physically Completed | 198708.45 | 0 | 2026-02-03 | 2026-09-09
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735005044/IF/22012035661518 — खेत तालाब निर्माण कार्य रमेश धुर्वे/ रंजोर धुर्वे | Approved | 0 | 0 | 2026-02-07
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735005044/IF/22012035661520 — खेत तालाब निर्माण कार्य बलराम नागवंशी/ मुरारी | Approved | 0 | 0 | 2026-02-07
BICHHIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/3421706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4919982 | Ongoing | 28500 | 0 | 2022-03-10
BICHHIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/3424261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5024726 | Ongoing | 28500 | 0 | 2022-03-10
BICHHIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/3440673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5578678 | Ongoing | 28500 | 0 | 2023-09-20
BICHHIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/3450134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1296637 | Ongoing | 28500 | 0 | 2022-08-24
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/3646255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5441865 | Ongoing | 28500 | 7320 | 2026-01-10
BICHHIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/3749534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123561411 | Ongoing | 28500 | 0 | 2022-06-04
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/4586073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119885801 | Ongoing | 28500 | 0 | 2025-08-09
BICHHIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/5908983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123221355 | Ongoing | 28500 | 0 | 2026-04-16
BICHHIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/5914122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119533936 | Physically Completed | 24795 | 0 | 2026-04-02 | 2026-08-23
BICHHIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/5919348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119455710 | Approved | 28500 | 0 | 2025-01-25
BICHHIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735005044/IF/IAY/5928315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125316689 | Ongoing | 28500 | 0 | 2026-02-28
BICHHIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1735005044/RC/22012034827144 — Gravel Sadak Nirman Kary Madhopur Se Kosiyaritola | Ongoing | 1834192.39 | 0 | 2025-02-21
BICHHIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1735005044/RC/22012034827902 — Filing Kary Bypass Se Gulab Singh Bhalavi Ke Ghar Tak Jaitatola Gp Madhopur | Approved | 0 | 0 | 2024-06-19
BICHHIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1735005044/RS/22012034488592 — Nadep nirman kary sankhya 20 Gp Madhopur | Ongoing | 248248.32 | 0 | 2020-09-03
BICHHIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maintenance of Earthen Spur for Community / Repair and Maintenance of Earthen Spur for Community | Repair & maint of Water Harvesting Structures | 1735005044/WC/22012035195429 — Kachi Nali Nirman Kary Main Neher Se Samsan Set Tak | New | 0 | 0 | 2024-02-26
BICHHIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair and Maint of Boulder Anicutfor Community / Repair and Maintenance of Boulder Check Dam for Community | Repair & maint of Water Harvesting Structures | 1735005044/WC/22012035195440 — Boldar Chek Dem Nirmaan Kary 20 | New | 0 | 0 | 2024-02-26
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035205950 — Namami Gange Abhiyan Talab Safai Kary Madhopur | Approved | 0 | 0 | 2024-04-01
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035205964 — Namami Gange Abhiyan Check Dam Safai Kary Madhopur | Approved | 0 | 0 | 2024-04-01
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035214436 — Gabion stracher nirman karya Faggo Bai ke khet ke pass Madhopur | Approved | 0 | 0 | 2024-06-18
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035214439 — Gabion stracher nirman karya Pipar nala Sumantri Bai ke khet ke pass Madhopur | Approved | 0 | 0 | 2024-06-18
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035214440 — Gabion stracher nirman karya Mukti Dhaam ke pass Madhopur | Approved | 0 | 0 | 2024-06-18
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035220137 — Kachhi Nali Nirmaan Kary Hostal Ground Se Sanju Patel Ke Khet Tak Madhopur | Approved | 0 | 0 | 2024-08-28
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035220138 — Kachi Nali Nirman Kary Bhagwan Das Patel Ke Ghar Se Ganesh Bagde Ke Khet Tak Madhopur | Approved | 0 | 0 | 2024-08-28
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035220139 — Kachi Nali Nirman Kary Kamal Ke Ghar Se Roshan Ke Ghar Tak Jaitatola | Approved | 0 | 0 | 2024-08-28
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035220140 — Kachi Nali Nirman Kary Chandrwati Ke Ghar Se Sheela Yadav Ke Ghar Tak Marartola | Approved | 0 | 0 | 2024-08-28
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035232736 — Bolder Chek Dem Nirman Karya Buiya Nala Koshiyari Tola | Approved | 0 | 0 | 2024-08-27
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035232741 — Bolder Chek Dem Nirman Karya Ittu Ke Khet Ke Pass Koshiyari Tola Madhopur | Approved | 0 | 0 | 2024-08-27
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035232742 — Bolder Chek Dem Nirman Karya Manglo Ke Ghar Ke Pass Koshiyari Tola | Approved | 0 | 0 | 2024-08-27
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035232743 — Bolder Chek Dem Nirman Karya Mangal Ke Khet Ke Pass Koshiyari Tola | Approved | 0 | 0 | 2024-08-27
BICHHIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035232745 — Bolder Chek Dem Nirman Karya Khushi Bhanware Ke Ghar Ke Pass Koshiyari Tola | Approved | 0 | 0 | 2024-08-27
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286586 — Roof Water Harvesting Panchayat Bhawan Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286594 — Roof Water Harvesting Primary Hospital Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286599 — Roof Water Harvesting Boys Primary School Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286602 — Roof Water Harvesting Girls Primary School Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286604 — Roof Water Harvesting Boys Middle School Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286607 — Roof Water Harvesting Girls Middle School Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286611 — Roof Water Harvesting Boys Primary School Koshiyari Tola | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286615 — Roof Water Harvesting Higher Secondary School Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1735005044/WC/22012035286620 — Roof Water Harvesting Primary School Jaitatola Madhopur | Approved | 0 | 0 | 2025-04-12
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035318498 — Bolder Chek Dem Nirman Karya Rajesh Maravi Ke khet Ke Pass 6 Unit | Approved | 0 | 0 | 2025-06-26
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035318499 — Bolder Chek Dem Nirman Karya Bhuiya Nala 6 Unit | Approved | 0 | 0 | 2025-06-26
BICHHIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735005044/WC/22012035318500 — Bolder Chek Dem Nirman Karya Pipar Nala 6 Unit | Approved | 0 | 0 | 2025-06-26
BICHHIYA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1735005/DP/22012034560314 — शहतूत वृक्षारोपण कार्य-01 एकड़ (श्री जवाहर लाल/गोविन्द) माधोपुर | Ongoing | 120000 | 0 | 2022-08-03