## Work List
Exported on: 2026-10-11 20:16:08
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: BIJEGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034668730 — Bijegoan PS Bulding Mohgaon Me Play Graound Nirman Kary | Approved | 877347.33 | 0 | 2025-10-02
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034668731 — Bijegaon Ps Buillding Me Play Ground Nirman Kary | New | 0 | 0 | 2025-12-26
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034668879 — Bijegaon Durga Mandir Parisar Me Play Ground Nirman | Ongoing | 562406.01 | 0 | 2026-02-13
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034668955 — Bijegaon Ke Mohgaon Me Prathmik Shala Me Play Ground Nirman Kary | Approved | 892417.37 | 0 | 2025-12-26
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034669222 — BijegaonMulakachar Resthouse Ke Samne Play Ground Nirman Kary | New | 0 | 0 | 2026-01-26
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034669226 — बीजेगांव प्राथमिक शाला मुलाकाछर स्कूल आंगनवाड़ी एवं रेस्टहाउस के पास खेल मैदान निर्माण कार्य | Ongoing | 528768.41 | 0 | 2026-02-27
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034669283 — Bijegaon Ke Dungariya Me Rupram Ke Ghar Ke Pas Khel Medan Nirman Kary | New | 0 | 0 | 2026-01-26
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1735006006/AV/22012034669287 — Bijegaon Ke Dungariya Ke Prathmik Shala Ke Pas Khel Medan Nirman Kary | New | 0 | 0 | 2026-01-26
NAINPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Shelter Belt Trees-Comm / Avenue Plantation for Community | Plantation | 1735006006/DP/22012034490138 — beejegoan ke mohgoan se madhiyatola marg par vrakcharopan kary | Ongoing | 390826.48 | 99840 | 2020-07-31
NAINPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1735006006/DP/22012034563377 — CLF GP BIJEGAON MOHGAON SE GOLIPATH TALAB KE DONO AUR PALNTION | Ongoing | 282000 | 0 | 2022-08-23
NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Shelter Belt Trees-Comm / Avenue Plantation for Community | Plantation | 1735006006/DP/22012034618507 — Khermai Parisar Evam Rode Ke Dono Oor Vrakcharopan Kary | Ongoing | 118873.76 | 0 | 2024-07-12
NAINPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1735006006/IF/22012034515725 — Kapil dhara sah khet talab nirman Samlu/ amar singh | Ongoing | 234458.62 | 0 | 2019-12-30
NAINPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735006006/IF/22012034550045 — बीजेगाव के मुरारी में कपिल धारा कूप निर्माण कार्य कार्य सुम्मी पिता दादूराम | Ongoing | 242453.87 | 0 | 2020-06-20
NAINPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individual | Construction of Check Dam/Stop Dam | 1735006006/IF/22012035201355 — Bijegoan Kapil dhara koop karan / Naval | New | 0 | 0 | 2024-01-26
NAINPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735006006/IF/22012035552639 — Bijegaon Ke Dungariya Me Kapil Dhara Koop Nirman Basant / Premi | Ongoing | 383258.04 | 0 | 2025-05-31
NAINPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735006006/IF/22012035633135 — बीजेगांव एक बगिया माँ का नाम लक्ष्मण / झाड़ू लाल | New | 0 | 0 | 2025-10-02
NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735006006/IF/IAY/5117884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126484370 | Ongoing | 28500 | 0 | 2025-03-28
NAINPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735006006/IF/IAY/6398090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126496971 | Approved | 28500 | 0 | 2025-02-10
NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1735006006/LD/22012034950794 — Bijegaon Mogoan Ke Goliptah Medan Me Dharam Ke Khet Ke Paas Peripferal Bund Nirman | Ongoing | 251081.04 | 0 | 2026-02-20
NAINPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1735006006/RC/22012034675993 — Bijegoan Ke DUNGARIYA PATPATTOLA ME BARAATOLA MARG PAR SUDUR RODE NIRMAN | New | 0 | 0 | 2024-01-26
NAINPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1735006006/RS/22012035137104 — GP Bijegaon Ke Mohgaon Me CSC Nirman Kary | Approved | 0 | 0 | 2025-01-26
NAINPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1735006006/RS/22012035137105 — GP Bijegaon Ke Mohgaon Me CSC Nirman Kary | Approved | 0 | 0 | 2025-01-26
NAINPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1735006006/RS/22012035137107 — GP Bijegaon Ke Mohgaon Me CSC Nirman Kary | Approved | 0 | 0 | 2025-01-26
NAINPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1735006006/RS/22012035137150 — GP Bijegaon Ke Mohgaon Me CSC Nirman Kary | Approved | 0 | 0 | 2025-01-26
NAINPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1735006006/RS/22012035137151 — GP Bijegaon Ke Mohgaon Me CSC Nirman Kary | Ongoing | 43700 | 0 | 2025-04-05
NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735006006/WC/22012035164104 — Bijegoan Sarvjanik Peyjal Koop Nirman Kary Mohgoan Mantar ke Ghar Ke Paas | New | 0 | 0 | 2024-04-26
NAINPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735006006/WC/22012035164110 — Bijegoan Ke Resthause Ke Pass Talab Gahreekaran Kary | New | 0 | 0 | 2024-01-26
NAINPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1735006006/WC/22012035164113 — Bijegoan Ke Dungariya Mohgoav Rod Ke Talab Gahreekaran Kary | New | 0 | 0 | 2024-01-26
NAINPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Gully Plug for Community | Construction of Check Dam/Stop Dam | 1735006006/WC/22012035164121 — Bijegoan naveen talab nirman kary dungariya | New | 0 | 0 | 2024-01-26
NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735006006/WC/22012035210469 — Bijegoan Talab Tola Nala Me Chek Dam Nirman Kary Mohgoan | Approved | 0 | 0 | 2024-06-08
NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735006006/WC/22012035212216 — Bijegoan Boldar Chek Dam Nirman Mohgav Sukha Talab Nala Me | Approved | 31918.19 | 0 | 2024-06-12
NAINPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1735006006/WC/22012035242584 — Bijegaon Ke Muraree Talab Me Best veyar Nirman Kary | Approved | 0 | 0 | 2024-10-02
NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1735006006/WC/22012035260359 — Bijegaon Sarvjanik Dugwell Dem Ke Neeche Me Recharge Pit Nirman | Approved | 0 | 0 | 2025-04-01
NAINPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1735006006/WC/22012035311582 — Bijegaon Kapildhara Koop Nirman Samudaiek Sabal Ke Ghar Ke Pass | Approved | 0 | 0 | 2025-04-15
NAINPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735006006/WC/VB/22012035334566 — Dungariya Koop Ke Paas Coutour Trench Nirman Kary | Approved | 0 | 0 | 2026-08-16
NAINPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1735006006/WC/VB/YD/22012035335604 — Contour Trench Dungariya Sarvjanik Koop Ke Paas | Approved | 0 | 0 | 2026-08-17