## Work List
Exported on: 2026-10-15 03:55:02
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: KHODAKHUDRA N
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735007035/DP/22012034562418 — PLANTATION PRAPOSED AMRIT SAROUR KE PASS KHODAKHUDRA N | Ongoing | 713000 | 0 | 2022-08-20
GHUGHRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012034567439 — RFR/BUDNER NADI /FLODHYAN TULSIRAM/SEKHU KHODA KHUDRA | Ongoing | 111599 | 0 | 2020-07-23
GHUGHRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012034567441 — RFR/BUDNER NADI /FLODHYAN MANNUSING/FAGU KHODA KHUDRA N | Ongoing | 111599 | 0 | 2020-07-23
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035273359 — Khet Talab Nirmad Kary Ramparsad/Fundi Lal Khoda.N | Approved | 0 | 0 | 2024-11-13
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292097 — फेरीफेरल स्टोन बन्ड कसेरिन/दुख्खू सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292107 — फेरीफेरल स्टोन बन्ड फगनू सिह /साधू सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292109 — फेरीफेरल स्टोन बन्ड जय सिह /सरजु सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292124 — फेरीफेरल स्टोन बन्डधन सिह /जन्नू सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292137 — फेरीफेरल स्टोन बन्ड कोमल सिह /गुहा सिह | Approved | 199022.41 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292147 — फेरीफेरल स्टोन बन्ड कारे लाल /दुमरा सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292156 — फेरीफेरल स्टोन बन्ड परसोतम /अक्कल सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292164 — फेरीफेरल स्टोन बन्ड पच्चे सिह /छोतु सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292186 — फेरीफेरल स्टोन बन्ड सुखराम /मादू सिह | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1735007035/IF/22012035292605 — फेरीफेरल स्टोन बन्ड सह्बे बाई /गेंद्लाल | Approved | 0 | 0 | 2025-01-10
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035613707 — एक बगिया मा के नाम/रुपन्ती बाई/कमलेश कुमार | Ongoing | 150491.98 | 6356.1 | 2025-09-13
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035613728 — एक बगिया मा के नाम/सुकरती बाई/भगत सिह | Ongoing | 174896.46 | 4971.12 | 2025-09-20
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035613733 — एक बगिया मा के नाम/कुशुम बाई/बुधसिह | Ongoing | 174896.46 | 16543 | 2025-09-20
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035613746 — एक बगिया मा के नाम/राजकुमारी/जेतू सिह | Ongoing | 174896.46 | 12487.36 | 2025-09-15
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035613756 — एक बगिया मा के नाम/पूर्णिमा/भुनेश्वर | Ongoing | 270536.27 | 22449 | 2025-09-15
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035613780 — एक बगिया मा के नाम/दानकिशोरी/मांदू | Ongoing | 270536.27 | 0 | 2025-09-20
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035613783 — एक बगिया मा के नाम/झामी बाई/रती राम | Ongoing | 150491.98 | 16431.42 | 2025-09-11
GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735007035/IF/22012035640204 — एक बगिया मा के नाम/अमरतो/रज्जू सिह | Ongoing | 266578.64 | 0 | 2026-04-18
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035644437 — Feri Feral Ston Band Sukhram/Mandu | Approved | 0 | 0 | 2025-09-30
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035645009 — Feree Feral Ston Band komal singh/Guha Singh | New | 0 | 0 | 2025-09-30
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035645046 — Feri Feral Ston Band Komal Singh /Guha Singh | Approved | 0 | 0 | 2025-09-30
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735007035/IF/22012035651872 — खेत तालाब निर्माण कार्य बिर सिह/बाबा सिह | Approved | 0 | 0 | 2025-12-07
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035658198 — पेरी फेरल स्टोन बड कार्य बिरझू लाल/मांदु लाल | Physically Completed | 177836.83 | 0 | 2026-02-14 | 2026-07-21
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035658681 — पेरी फेरल स्टोन बड कार्य जोहन लाल/नन्द्लाल | Approved | 0 | 0 | 2025-09-30
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035658688 — पेरी फेरल स्टोन बड कार्य बुधई/रातू | Approved | 0 | 0 | 2025-09-30
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035658690 — पेरी फेरल स्टोन बड कार्य बाल सिह/भगलू सिह | Approved | 0 | 0 | 2025-09-30
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1735007035/IF/22012035658694 — पेरी फेरल स्टोन बड कार्य साहजू सिह/सुमारी लाल | Approved | 0 | 0 | 2025-09-30
GHUGHRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/106665 — Construction of IAY House -IAY REG. NO. MP-35-007-035-001/62 | Approved | 28500 | 0 | 2015-10-30
GHUGHRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/106666 — Construction of IAY House -IAY REG. NO. MP-35-007-035-001/77 | Approved | 28500 | 0 | 2015-10-30
GHUGHRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/106667 — Construction of IAY House -IAY REG. NO. MP-35-007-035-002/06 | Approved | 28500 | 0 | 2015-10-30
GHUGHRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/106668 — Construction of IAY House -IAY REG. NO. MP-35-007-035-002/29 | Approved | 28500 | 0 | 2015-10-30
GHUGHRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/106669 — Construction of IAY House -IAY REG. NO. MP-35-007-035-002/43 | Approved | 28500 | 0 | 2015-10-30
GHUGHRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/51288 — Construction of IAY House -IAY REG. NO. MP-35-007-035-001/21 | Approved | 28500 | 0 | 2015-12-08
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/5563157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121691272 | Approved | 28500 | 0 | 2025-02-27
GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/5959429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145366821 | Approved | 28500 | 0 | 2025-02-27
GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007035/IF/IAY/6301567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152074983 | Approved | 28500 | 0 | 2026-02-17
GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1735007035/WC/22012035021917 — AMRAT SAROWAR NIRMAN BAHERA NALA KHODAKHUDRA N | Ongoing | 2277000 | 0 | 2022-12-26
GHUGHRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1735007035/WC/22012035164691 — Gebiyan Nirmad Kary Khudadi Nala Khodakhudra n | New | 0 | 0 | 2024-01-29
GHUGHRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1735007035/WC/22012035164695 — gebiyan nirmad kary Chhivlahi Nala Khoda n. | New | 0 | 0 | 2024-01-29
GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735007035/WC/VB/22012035330228 — kantur tench kulhan bhadi khodakhudra n | Ongoing | 216095.8 | 38382.86 | 2026-08-11
GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735007035/WC/VB/22012035330236 — kantur tench Semar bhadi mahali | Ongoing | 216095.8 | 0 | 2026-10-01
GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735007035/WC/VB/22012035330241 — kantur tench katara bhadi khodakhudra n | Ongoing | 218475.82 | 0 | 2026-10-05
GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735007035/WC/VB/22012035330245 — boldar chek dem ramlal nala mahali | Approved | 0 | 0 | 2026-07-09
GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735007035/WC/VB/22012035330248 — boldar chek dem kirghi nala | Approved | 0 | 0 | 2026-07-09
GHUGHRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1735007035/WC/VB/22012035330252 — boldar chek dem Semar nala mahali | Approved | 0 | 0 | 2026-07-09