## Work List
Exported on: 2026-09-09 02:02:56
Filters applied:
Data source: VBGRAMG
District: MANDLA
Block: All
Panchayat: BODASILLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MOHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1735008032/AV/22012034614892 — Rajiv gandhi seva kendra (panchayat bhawan)nirman karya | Ongoing | 1000000 | 0 | 2022-03-09
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1735008032/DP/22012034445669 — sarvjanik kup nirman kary vard kramak 07 bodhasilli | Ongoing | 445000 | 0 | 2025-06-14
MOHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1735008032/DP/22012034552904 — Ma Ki Bagiya NPS BhoiTola | Ongoing | 33182.06 | 0 | 2022-04-29
MOHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1735008032/DP/22012034552905 — Ma Ki Bagiya NMS Bodasilli | Ongoing | 33182.06 | 0 | 2022-04-30
MOHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012034575953 — faloudhyan-sonulal/arjun | Ongoing | 142000 | 0 | 2020-07-18
MOHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1735008032/IF/22012034874274 — faloudhyan-tihari/guha | Ongoing | 112000 | 0 | 2022-03-01
MOHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735008032/IF/22012035007172 — Falouddhyan - Mulchand / Panchu | Ongoing | 109000 | 0 | 2022-11-26
MOHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735008032/IF/22012035007182 — Falouddhyan-Ramliya bai/jewan | Ongoing | 109000 | 0 | 2022-08-24
MOHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735008032/IF/22012035007216 — falouddhyan-chandar/ramsevak | Ongoing | 109000 | 0 | 2023-08-24
MOHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735008032/IF/22012035007226 — falouddhyan-shankar/panku | Ongoing | 109000 | 0 | 2022-08-19
MOHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735008032/IF/22012035007230 — falouddhyan-Kanti bai/kabul chand | Ongoing | 109000 | 0 | 2022-12-03
MOHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1735008032/IF/22012035007231 — falouddhyan-mithhthhu/mangal | Ongoing | 109000 | 0 | 2022-10-14
MOHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1735008032/IF/22012035199911 — Hiteshi Koop Mahendra/Ramlal | New | 0 | 0 | 2024-02-02
MOHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035270883 — Khet Talab :- Sanjay Kumar / Hariprasad | Approved | 0 | 0 | 2024-08-27
MOHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035275164 — Khet Talab :- Dhobisingh / Dumar | New | 0 | 0 | 2024-08-27
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035332297 — Khet Talab :- Batasiya / Radhelal | Approved | 0 | 0 | 2025-04-01
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035357831 — Khet Talab :- Harilal / Ramlal | Ongoing | 357905.65 | 0 | 2025-05-13
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035357920 — Khet Talab :- Kailash / Maniram | Ongoing | 358505.88 | 0 | 2026-02-07
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035515439 — Khet Talab :- Dalpat / Chamra | Approved | 356921.65 | 0 | 2025-04-01
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1735008032/IF/22012035540975 — Kapil Dhara Koop :- Shivcharan / Santadhar | Ongoing | 364000.91 | 0 | 2026-01-14
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1735008032/IF/22012035568141 — Kapil Dhara Koop :- Devlal / Mansingh | Approved | 0 | 0 | 2025-04-01
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035568147 — Khet Talab :- Kamlesh / Binde | Approved | 193580.41 | 0 | 2025-04-01
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012035608781 — Ek Bagiya Maa Ke Naam :- Phoolkari Dhurwey Gram Patadei | Ongoing | 177384.47 | 0 | 2025-12-02
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012035613407 — Ek Bagiya Maa Ke Naam :- Shankari Bai Gram Patadei | Ongoing | 178324.3 | 0 | 2025-09-10
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012035614335 — Ek Bagiya Maa Ke Naam :- Sumantri Bai Maravi Gram Patadei | Ongoing | 178038.02 | 0 | 2025-09-10
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012035625906 — Ek Bagiya Maa Ke Naam :- TiharoBai Gram Patadei | Ongoing | 178038.02 | 0 | 2025-10-30
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012035625910 — Ek Bagiya Maa Ke Naam :- Kaisabai / Shrichand Gram Patadei | Ongoing | 178038.02 | 0 | 2025-10-30
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012035626169 — Ek Bagiya Maa Ke Naam :- Guntibai / Bhaglu Singh Gram Bodasilli | Ongoing | 178038.02 | 9135 | 2025-10-30
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735008032/IF/22012035626179 — Ek Bagiya Maa Ke Naam :- Saroj Bai / Kamal Gram Bodasilli | Ongoing | 178038.02 | 0 | 2025-10-29
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035656562 — Khet Talab :- Anilkumar / Balju GP Bodasilli | Approved | 195548.41 | 0 | 2025-04-01
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035656564 — Khet Talab :- Chaitibai / Ramesh GP Bodasilli | Approved | 195548.41 | 0 | 2025-04-01
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035657369 — Khet Talab :- Fagnibai / Nanda GP Bodasilli | Approved | 194564.41 | 0 | 2025-04-01
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035661380 — Khet Talab :- Chhange / Chamar GP Bodasilli | Approved | 0 | 0 | 2026-01-26
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035661536 — Khet Talab :- Samaru / Gorelal GP Bodasilli | Approved | 0 | 0 | 2026-01-26
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035661663 — Khet Talab :- Buddhusingh / Ramu GP Bodasilli | Approved | 0 | 0 | 2026-01-26
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735008032/IF/22012035661974 — Khet Talab :- Rajesh / Fundilal GP Bodasilli | Approved | 199964.52 | 0 | 2026-01-26
MOHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735008032/IF/IAY/3138583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4334720 | Ongoing | 28500 | 0 | 2023-06-25
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735008032/IF/IAY/5396979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131373832 | Ongoing | 28500 | 0 | 2025-12-06
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735008032/IF/IAY/5400253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127482848 | Physically Completed | 24795 | 0 | 2025-09-18 | 2026-08-02
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735008032/IF/IAY/5954974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152083472 | Approved | 28500 | 0 | 2026-02-10
MOHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735008032/IF/IAY/6087437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126223865 | Approved | 28500 | 0 | 2026-02-06
MOHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1735008032/WC/22012035064311 — Gabion Nirman Laliya Ke Khet Pass | Ongoing | 274213.35 | 0 | 2023-10-07