## Work List
Exported on: 2026-09-06 10:09:45
Filters applied:
Data source: MGNREGA
District: CHHINDWARA
Block: All
Panchayat: DHANORA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHAURAI | 2023-2024 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1736004002/AV/22012034652385 — moxdham nirman kary dhanora | Ongoing | 226381.46 | 205246.43 | 2024-03-12
CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Groups / Construction of Irrigation Open Well for Groups | Construction of Well | 1736004002/DP/22012034441667 — nirmal neer | Closed | 0 | 0 | 2019-01-26
CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736004002/DP/22012034481852 — Dhanora Plantation School Campus | Closed | 0 | 0 | 2019-08-15
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736004002/DP/22012034488828 — Plantation work Khailmaidan parisar Dhanora | Closed | 0 | 0 | 2020-04-01
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736004002/DP/22012034488829 — Plantation Road side Dhanora | Closed | 0 | 0 | 2020-04-01
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736004002/DP/22012034490992 — धनोरा वृक्षारोपण कार्य प्राथमिक शाला परिसर | Physically Completed | 372000 | 152003 | 2020-10-31 | 2026-06-29
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736004002/DP/22012034490994 — धनोरा वृक्षारोपण बाज़ार चौक | Closed | 372000 | 0 | 2020-05-25
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1736004002/DP/22012034588209 — वसुधा वंदन अमृत वाटिका बाजार चौक के सामने शास कूप के पास धनौरा ग्राम पंचायत धनौरा | Closed | 55852.42 | 0 | 2023-06-30
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1736004002/IF/22012035303834 — Kantur Tranch Dhanora F T L Line Ke Pass | New | 0 | 0 | 2025-01-24
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004002/IF/9926738469 — धनौरा मवेशी शेड भुवन पितरु अहीर मढुआढाना | Deleted | 48500 | 0 | 2014-01-27
CHAURAI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004002/IF/9926738471 — धनौरा मवेशी शेड मेमवती घूडो डेहरिया मढुआढाना | Completed | 84000 | 74358 | 2014-07-21 | 2016-04-13
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004002/IF/9926738472 — धनौरा मवेशी शेड नब्‍बू रेखन डेहरिया | Deleted | 48500 | 0 | 2014-01-27
CHAURAI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004002/IF/9926740101 — धनौरा पशु शेड मानकी श्‍याम डेहरिया मढुआढाना | Completed | 48500 | 45224 | 2014-06-04 | 2014-08-18
CHAURAI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004002/IF/9993656187 — Dhanora (Maveshi shed Ganji S/O Jhadu jati Lodhi) Dhanora | Completed | 85000 | 64596 | 2014-09-21 | 2015-08-25
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/107448 — Construction of IAY House -IAY REG. NO. MP-36-004-002-001/26 | Completed | 15105 | 14330 | 2019-07-05 | 2021-12-14
CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/1875288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1381968 | Completed | 18050 | 17779 | 2018-10-31 | 2024-09-24
CHAURAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/1875362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2699185 | Deleted | 0 | 0 | 2017-02-04
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2508316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4454398 | Completed | 18050 | 11508 | 2020-12-27 | 2024-08-22
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2545471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5193322 | Completed | 18050 | 16400 | 2020-12-27 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2940693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1490209 | Completed | 18050 | 17914 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2940696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2754921 | Completed | 18050 | 15912 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2940697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2755466 | Completed | 18050 | 17816 | 2021-06-11 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2940742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4117959 | Completed | 18050 | 16843 | 2021-06-03 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2940745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4458754 | Completed | 18050 | 17901 | 2021-06-16 | 2024-06-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2940746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4537458 | Completed | 18050 | 17949 | 2021-06-03 | 2022-09-20
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2940747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4540752 | Completed | 18050 | 17699 | 2021-06-03 | 2023-07-22
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4540842 | Completed | 18050 | 17934 | 2021-06-16 | 2023-01-30
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4540845 | Completed | 18050 | 17871 | 2021-06-03 | 2023-06-06
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4547710 | Completed | 18050 | 16929 | 2021-06-03 | 2023-06-28
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4554755 | Completed | 18050 | 17961 | 2021-06-03 | 2023-06-28
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4554783 | Completed | 18050 | 18015 | 2021-06-16 | 2023-05-30
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4554811 | Completed | 18050 | 17926 | 2022-05-01 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4558636 | Completed | 18050 | 17949 | 2021-06-03 | 2023-01-30
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4558827 | Completed | 18050 | 17949 | 2021-06-03 | 2023-01-30
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4558856 | Completed | 18050 | 17940 | 2021-06-16 | 2024-12-15
CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4559832 | Completed | 18050 | 17945.2 | 2023-07-15 | 2023-11-09
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4565239 | Completed | 18050 | 17977 | 2021-06-16 | 2024-06-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4592339 | Completed | 18050 | 18005 | 2021-06-03 | 2024-08-16
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4592400 | Completed | 18050 | 16998 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4592596 | Completed | 18050 | 17238 | 2021-06-16 | 2023-08-22
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4594120 | Completed | 18050 | 17440 | 2021-06-16 | 2023-07-22
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4607869 | Completed | 18050 | 17949 | 2021-06-03 | 2022-11-22
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4608142 | Completed | 18050 | 17888 | 2021-06-16 | 2024-06-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4624393 | Completed | 18050 | 17201 | 2021-06-03 | 2023-07-22
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4624646 | Completed | 18050 | 17442 | 2021-06-16 | 2023-07-22
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4652400 | Completed | 18050 | 16755 | 2021-06-03 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4664260 | Completed | 18050 | 17982 | 2021-06-16 | 2024-07-12
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4667390 | Completed | 18050 | 17884 | 2021-06-16 | 2023-07-22
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4672833 | Completed | 18050 | 17882 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4706664 | Completed | 18050 | 16268 | 2021-06-16 | 2023-06-28
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5229914 | Completed | 18050 | 17901 | 2021-06-16 | 2024-09-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5473605 | Completed | 18050 | 17117 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5493880 | Completed | 18050 | 17884 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5498822 | Completed | 18050 | 17901 | 2021-06-16 | 2023-09-15
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5502130 | Completed | 18050 | 17949 | 2021-06-03 | 2023-01-30
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5520655 | Completed | 18050 | 17859 | 2021-06-16 | 2024-05-14
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2941714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5537193 | Completed | 18050 | 16975 | 2022-05-01 | 2023-11-09
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/2942267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5546635 | Completed | 18050 | 17949 | 2021-06-16 | 2022-09-30
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1603594 | Completed | 18335 | 17756 | 2021-06-03 | 2023-02-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4542029 | Completed | 18335 | 17459 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4584107 | Completed | 18335 | 16809 | 2021-06-16 | 2023-06-28
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4589418 | Completed | 18335 | 17572.4 | 2021-06-16 | 2023-11-09
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4664453 | Completed | 18335 | 18254 | 2021-06-16 | 2024-06-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4678425 | Completed | 18335 | 18118 | 2021-06-16 | 2023-09-11
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4683102 | Completed | 18335 | 18186.7 | 2021-06-16 | 2024-07-12
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4683860 | Completed | 18335 | 16911 | 2021-06-16 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3008053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5479313 | Completed | 18335 | 16855 | 2021-06-03 | 2023-08-02
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3068236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1491036 | Completed | 18335 | 16420 | 2021-06-16 | 2023-06-28
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3252598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1400315 | Completed | 18335 | 17768 | 2022-08-20 | 2023-11-09
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3255329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2699194 | Completed | 18335 | 17127 | 2022-07-11 | 2023-06-28
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3255347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2706079 | Completed | 18335 | 18123 | 2022-08-20 | 2024-06-24
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3259448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3908314 | Completed | 18335 | 18122 | 2023-03-04 | 2024-08-29
CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3265054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4592346 | Completed | 18335 | 18207 | 2023-04-15 | 2023-08-02
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004002/IF/IAY/3278241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5522041 | Completed | 18335 | 18165 | 2023-02-16 | 2024-06-24
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1736004002/LD/22012034942320 — Dhanora plantation karya F.T.L. line ke pas dem ke pas Dhanora | Physically Completed | 404435.97 | 147147.14 | 2024-07-09 | 2026-06-30
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1736004002/LD/22012034942399 — Dhanora C.P.T. nirman Kary school parisar or khel maidan ke pas Dhanora | Physically Completed | 146618 | 125928 | 2025-01-16 | 2026-05-06
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034169009 — धनौरा पीसीसी प्रताप के घर से स्‍कूल तकसडक निर्माण | Completed | 124000 | 80651 | 2013-06-01 | 2013-12-17
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004002/RC/22012034173260 — धनौरा जीएसबी सडक निमार्ण एवं पुलिया निर्माण लंबाई | Completed | 1731000 | 1641756 | 2013-07-29 | 2015-03-30
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034189725 — धनौरा पीसीसी गोविंद के घर से दूजाबाई के घर तक 120 | Completed | 142000 | 74458 | 2013-10-25 | 2014-04-23
CHAURAI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034227829 — धनौरा पंचपरमेश्‍वर सी.सी. राेड मढुआप्रताप के घर से कमोद के घर तक 100 मी. | Completed | 53000 | 52257 | 2014-08-23 | 2014-12-11
CHAURAI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004002/RC/22012034303146 — Dhanora GSB road | Closed | 0 | 0 | 2016-01-26
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034547832 — cc road Munish verma ke makan se Ramsing ke ghar tak 155 mtr. | Completed | 59000 | 58900 | 2020-11-21 | 2022-02-25
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034580352 — cc road Chandan Patel ke Ghar se Khaleel mansoori ke ghar tak 270 Mtr. Dhanora | Completed | 103000 | 102942 | 2021-09-09 | 2021-10-18
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034583420 — cc road sitaram ke ghar se Vijay sing satnami ke ghar tak Dhanora | Closed | 10000 | 0 | 2021-04-01
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034584101 — cc road 90 mtr seetaram ke ghar se vijay satnami ke ghar tak part 2 Dhanora | Completed | 30000 | 30000 | 2021-10-19 | 2021-11-14
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004002/RC/22012034606861 — C C rode nirmad karya makbul ke ghar tak 100 meetar | Closed | 0 | 0 | 2022-01-26
CHAURAI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004002/RC/71 — test | Deleted | 0 | 0 | 2008-04-01
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1736004002/RS/22012034593846 — SAMUDAIK SWCHHTA PARISAR DHANORA | Completed | 44000 | 43896 | 2021-10-21 | 2021-11-26
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1736004002/WC/22012035140644 — Nalapadopchar prtikshalaye ke samne gp dhanora | Completed | 486940.14 | 389170 | 2023-12-27 | 2024-09-04
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1736004002/WC/22012035140700 — Dhanora Nala Padopchar Karya Pratikchhalay ke samne bala nala | Closed | 0 | 0 | 2023-10-02
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1736004002/WC/22012035151059 — Dhanora CTR Box Trach Nirman Kary Talab ke Kinare F.T.L. line se 1 km. | Completed | 531249 | 411898 | 2024-01-10 | 2024-08-26
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1736004002/WC/22012035155510 — Dhanora samudayik kup nirman kary yatri pratikchhalay ke samne Dhanora | Closed | 0 | 0 | 2023-10-02
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1736004002/WC/22012035155512 — Dhanora samudayik kup nirman kary Ashik ke ghar pichhe Dhanora | Closed | 0 | 0 | 2023-10-02
CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1736004002/WC/22012035162669 — Dhanora Nala Padopchar Karya Santram Verma ke ghar ke samne bala nala | New | 0 | 0 | 2023-01-26
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004002/WC/22012035165805 — prtikshalay ke samne bala nala me boldar chek | Completed | 273445.76 | 191280 | 2024-04-02 | 2024-07-23
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004002/WC/22012035167748 — samudaiyk kup ashik ke ghar ke piche | Closed | 0 | 0 | 2023-10-02
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1736004002/WC/22012035167755 — samudaik kup nirman prtikshalya ke samne | Closed | 0 | 0 | 2023-10-02
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1736004002/WC/22012035167756 — samudaik kup nirman prtikshalya ke samne | Closed | 0 | 0 | 2023-10-02
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1736004002/WC/22012035181001 — Dhanora samudayik kup nirman kary filtar plant ke pas | Closed | 623407.16 | 0 | 2024-01-24
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1736004002/WC/22012035251275 — Parkolesin Tenk Ramavtar Ke Khet Ke Pass | Closed | 199169.36 | 522 | 2025-04-24
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736004002/WC/22012035251278 — Kantur Tranch Dhanora F T L Line Ke Pass | Physically Completed | 545886.86 | 377547 | 2025-03-15 | 2026-05-31
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004002/WC/22012035280066 — Dugwell Recharge pit samudaik koop ke paas dhanora | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736004002/WC/22012035280080 — Dugwell Recharge pit samudaik koop filtar plant ke paas dhanora | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004002/WC/22012035282497 — Dugwell Recharge pit samudaik koop talab ke pas dhanora | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004002/WC/22012035282507 — Dugwell Recharge pit samudaik koop filtar plant ke pas dhanora | Approved | 0 | 0 | 2025-04-01