## Work List
Exported on: 2026-09-04 04:26:20
Filters applied:
Data source: VBGRAMG
District: CHHINDWARA
Block: All
Panchayat: RAJALWADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1736004036/AV/22012034660505 — cc nali nirma kary raju sahu ke dukan se sudher raghuwanshi ke ghar tak 200 m | New | 0 | 0 | 2024-08-15
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1736004036/DP/22012034628244 — plantation school ground rajlawadi | Ongoing | 453563.17 | 6900 | 2024-11-20
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1736004036/IF/22012035197506 — shivkumar kavreti | New | 0 | 0 | 2024-01-25
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1736004036/IF/22012035197508 — med bandhan shivdyal | New | 0 | 0 | 2024-01-25
CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1736004036/IF/22012035197509 — med bandhan ompraksh | New | 0 | 0 | 2024-01-25
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1736004036/IF/22012035197510 — med bandhan jagdesh | New | 0 | 0 | 2024-01-25
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1736004036/IF/22012035311192 — GOAT SHELTER SEEMA UIKEY/PARMAL GRAM RAJALWADI GRAM PANCH | Approved | 0 | 0 | 2025-03-21
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1736004036/IF/22012035311314 — GOAT SHELTER SEEMA UIKEY/PARMAL GRAM RAJALWADI GRAM PANCHYAT RAJALWADI | Approved | 0 | 0 | 2025-03-21
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1736004036/IF/22012035311316 — GOAT SHELTER SEEMA UIKEY/PARMAL GRAM RAJALWADI GRAM PANCHYAT RAJALWADI | Approved | 61355.2 | 0 | 2025-03-21
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1736004036/IF/22012035311319 — GOAT SHELTER PRAMILA SALLAM GRAM RAJALWADI GRAM PANCHYAT RAJALWADI | Approved | 61039.22 | 0 | 2025-03-21
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004036/IF/22012035311327 — CATTLE SHELTER RAJKIRAN UIKEY/JAGDEESH UIKEY GRAM RAJALWADI | Approved | 100310.06 | 0 | 2025-03-21
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004036/IF/22012035311338 — OPEN WELL SUBECHAND UIKEY/DEEPCHAND UIKEY KAPILDHARA KOOP GRAM RAJALWADI | Approved | 0 | 0 | 2025-03-21
CHAURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1736004036/IF/22012035322324 — SAMUDAIK SHOK PIT NIRMAN KARY RAJALWADI | New | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736004036/IF/22012035385058 — Rechage pit dugwell jagatraam nagotiya ke koop ke pass khutiya | Approved | 0 | 0 | 2025-04-16
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736004036/IF/22012035402956 — Rechage pit dugwell rambharosh/malkhan singh ke koop ke pass rajalwadi | Approved | 0 | 0 | 2025-04-16
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004036/IF/22012035607088 — Ek bagiya ma ke naam Aanar dehriya RAJALWADI | Ongoing | 158294.68 | 0 | 2025-09-02
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1736004036/IF/22012035648833 — Ek Bagiya Maa ke Name kusum ivnati liladhar rajlwadi | Ongoing | 165387.17 | 0 | 2026-02-16
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004036/IF/IAY/4629366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128481077 | Approved | 28500 | 0 | 2024-09-19
CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004036/RC/22012034674560 — khet sadk khutiya | New | 0 | 0 | 2024-01-25
CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004036/RC/22012034674561 — khet sadk khutiya | New | 0 | 0 | 2024-01-25
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004036/RC/22012034827063 — NALI NIRMAN KARY RAJALWADI RAJU SAHU KE GHAR SE SUDHEER RAGHUWANSHI KE GHAR TAK 200M | New | 0 | 0 | 2024-07-24
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004036/RC/22012034827187 — CC Nali nirman kary raju sahu ke ghar Sudheer raghuwanshi ke ghar tak rajalwadi | New | 0 | 0 | 2024-09-19
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004036/RC/22012034827191 — cc road raju sahu ke ghar sesudher raghuwanshi ke ghar thak 200 m | Approved | 0 | 0 | 2024-08-16
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004036/RC/22012034827192 — cc road raju sahu ke ghar sesudher raghuwanshi ke ghar thak 200 m | Approved | 0 | 0 | 2024-08-16
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004036/RC/22012034827193 — cc road raju sahu ke ghar sesudher raghuwanshi ke ghar thak 200 m | Approved | 79000 | 0 | 2024-07-19
CHAURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1736004036/RS/22012035137208 — SAMUDAIK SHOK PIT NIRMAN KARY RAJALWADI | Approved | 41809.45 | 0 | 2025-04-01
CHAURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1736004036/RS/22012035137209 — SAMUDAIK SHOK PIT NIRMAN KARY KHUTIYA | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1736004036/RS/22012035137217 — SOAK PIT NIRMAN KARY HENDPUMP KE PASS KHUTIYA | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1736004036/WC/22012035160481 — sokta dadda | New | 0 | 0 | 2024-01-25
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004036/WC/22012035268225 — DRAGWELL NIRMAN KARY SAMUDAIK KOOP RAJALWADI | Approved | 0 | 0 | 2025-04-16
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736004036/WC/22012035316473 — samudaik shokpit hend pump ke pass khutiya | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736004036/WC/22012035319502 — samudaik shokpit khuutiya hendpump ke paas | Approved | 0 | 0 | 2025-08-17