## Work List
Exported on: 2026-09-11 14:05:19
Filters applied:
Data source: MGNREGA
District: CHHINDWARA
Block: All
Panchayat: MORKHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHAURAI | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736004040/AV/22012034374320 — ANGANWADI BHAWAN NIRMAN KARYA( KHURCHADHANA) MORKHA | Completed | 312000 | 310184 | 2019-10-16 | 2020-11-06
CHAURAI | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736004040/AV/22012034393260 — ANGANWADI BHAVAN NIRMAN | Closed | 0 | 0 | 2017-10-02
CHAURAI | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736004040/AV/22012034393261 — ANGANWADI BHAWAN NIRMAN | Deleted | 0 | 0 | 2017-10-02
CHAURAI | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736004040/AV/22012034393473 — Aganwadi Bhavan nirman karya Morkha | Completed | 312000 | 311010 | 2019-01-21 | 2019-11-26
CHAURAI | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736004040/AV/22012034467141 — Anganwadi Bhavan Nirman kary Morkha | Closed | 180000 | 0 | 2018-08-15
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1736004040/AV/22012034516002 — Nadep Nirman kary Panchayat bhavan ke pass | Closed | 0 | 0 | 2020-04-14
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1736004040/AV/22012034516003 — Nadep Nirman kary khirka mohalla kalamanch ke side me | Closed | 0 | 0 | 2020-04-14
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1736004040/AV/22012034516005 — Nadep Nirman kary primary school ke pass | Closed | 0 | 0 | 2020-04-14
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1736004040/AV/22012034545061 — boundry wall middle school parisar morkha 150 mtr | Completed | 89000 | 67006 | 2020-12-14 | 2024-02-25
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736004040/AV/22012034579746 — डाइनिंग टेबल कार्य प्राथमिक शाला कुरचा ढाना | Closed | 16093.2 | 0 | 2021-04-01
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1736004040/AV/22012034587499 — Moxdham shed nirman Morkha | Completed | 196981.11 | 172532.72 | 2021-09-05 | 2025-08-01
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1736004040/AV/22012034591500 — Moxdham shed nirman kurchadhana | Closed | 196981.11 | 0 | 2021-04-01
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1736004040/AV/22012034658463 — Boxtranch Nirman kary Ramnandan Ke Ghar se bhaisasur Baba Chourai Main Road Tak | New | 0 | 0 | 2024-06-05
CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004040/DP/113 — मोरखा /वृक्षारोपण/उर्जा वन की स्‍थापना क्र. 1365 (20हे. ) कूरचाढाना /कूरचाढाना | Completed | 499000 | 178488 | 2009-04-06 | 2013-01-31
CHAURAI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004040/DP/22012034241957 — Plantation Morkha m s school play ground | Deleted | 165500 | 0 | 2017-06-12
CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736004040/DP/22012034481845 — Morkha Plantation sarvjanik parisar | Completed | 381899.79 | 122393 | 2019-10-03 | 2024-06-18
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1736004040/DP/22012034488902 — plantation moxdham Morkha morkha | Closed | 0 | 0 | 2020-04-01
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1736004040/DP/22012034489871 — Naino Archid (Fhaldar Braxharopan) Laxman/Amar Chandrawanshi | Closed | 0 | 0 | 2020-04-14
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1736004040/DP/22012034489872 — Naino Archid Sukko/Jeevan Dehareya | Closed | 0 | 0 | 2020-04-14
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1736004040/DP/22012034587314 — वसुधा वंदन (अमृत वाटिका ) निस्तारी तालाब मिडिल स्कूल के पीछे मो रखा | Physically Completed | 54564.94 | 52663 | 2023-09-25 | 2026-05-06
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1736004040/DP/22012034587319 — वसुधा वंदन (अमृत वाटिका ) निस्तारी तालाब मिडिल स्कूल के पीछे मो रखा | Deleted | 0 | 0 | 2023-04-14
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1736004040/DP/22012034621610 — Plantation Moxdham morkha | Ongoing | 1097092.56 | 183476.8 | 2024-07-29
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1736004040/DP/22012034621635 — Plantation Middle School Morkha ke Peeche CPT Me | Ongoing | 453563.17 | 105998.99 | 2024-07-29
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1736004040/DP/22012034625079 — PLANTATION CPT MIDDLE SCHOOL KE PEECHE MORKHA | Approved | 453563.17 | 0 | 2024-06-05
CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1736004040/DP/40/1 — मोरखा/मिश्रित रोपण कार्य1365(20 हेक्‍टेयर)/मोरखा | Completed | 1090000 | 191592 | 2007-06-24 | 2013-01-31
CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004040/DP/40/2 — मोरखा/वृक्षारोवण निर्माण कार्य/शमशान घाट/मोरखा | Completed | 100000 | 56708 | 2007-07-24 | 2013-01-31
CHAURAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004040/DP/68 — मोरखा / जेट्रोफा प्‍लान्‍टेशन कार्य /देत बाबा झिरिया के पास भू‍मि मे/ मोरखा | Completed | 254000 | 46594 | 2008-08-25 | 2013-01-31
CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1736004040/DP/70 — नंदन फलउधान/ तिलोकी रूपी ग्राम मोरखा | Deleted | 0 | 0 | 2008-01-26
CHAURAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004040/DP/71 — मोरखा / नन्‍दन फलोद्यान योजना के अंतगर्त पौधरोपण कार्य/ तिलोखी/रूपी गौली/मोरखा | Completed | 90000 | 9282 | 2008-10-13 | 2013-01-31
CHAURAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1736004040/DP/94 — मोरखा /नन्‍दनफलोद्यान योजना / दशरथ /तेजलाल गोंड/मोरखा | Completed | 90000 | 8736 | 2008-10-16 | 2013-01-31
CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1736004040/DW/22012034353872 — Morkha samudayik koop nirman karya | Closed | 0 | 0 | 2017-10-02
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of water courses Canal for Community / Lining of water courses Canal for Community | Lining of Canal | 1736004040/IC/22012034885097 — PLANTATION CPT MIDDLE SCHOOL KE PEECHE MORKHA | New | 0 | 0 | 2024-06-05
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000009686 — मोरखा मेढ बंधान कार्य रामऔतार पिता बुद्धू | Completed | 23400 | 18688 | 2013-05-03 | 2013-05-25
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000053276 — Morkha Dhana Rooplal s/o bakaram med bandhan | Deleted | 0 | 0 | 2013-08-15
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000054564 — Morkha Dhana Medbandhan Rooplal S/O Bakaram Gaund | Deleted | 0 | 0 | 2013-08-15
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000054586 — morkha/ medbandhan karya rooplal/bakaram gond mork | Completed | 123000 | 118932 | 2013-12-09 | 2015-01-06
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000054589 — morkha/ medbandhan karya vinod/Sopat gond morkha d | Completed | 69000 | 60303 | 2013-12-30 | 2015-01-06
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000058422 — morkha dhana madbandha karya vinod/sopat gond | Deleted | 0 | 0 | 2013-10-02
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000058439 — morkhadhana med bandhan kary vinod sopat gond | Deleted | 69000 | 0 | 2013-10-02
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/1000061568 — Morkha Dhana Med-Bandhan ChandaniyaH/O Buddhu | Completed | 68000 | 64532 | 2014-01-07 | 2015-01-01
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004040/IF/1000068708 — Morkha girjabhai / dhashrath gond cattle shed morkha | Deleted | 48000 | 0 | 2013-10-02
CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004040/IF/1000068715 — Morkha Ruplal/Bakaram gond Cattle Shed Morkhadhana | Deleted | 48000 | 0 | 2013-10-02
CHAURAI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1736004040/IF/22012034306227 — morkha vermi com pit shankar/prem gond | Deleted | 17000 | 0 | 2016-12-27
CHAURAI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Soak Pits / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1736004040/IF/22012034306228 — Morkha vermi com pit sukdayal /kevlsi | Deleted | 17000 | 0 | 2016-12-12
CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736004040/IF/22012034353431 — Plantation play ground M S school Morkha | Completed | 168090 | 112622 | 2017-06-22 | 2020-05-03
CHAURAI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Recharge Pits / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1736004040/IF/22012034371225 — Plantation devre main road se kurchadhana | Closed | 0 | 0 | 2017-04-14
CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1736004040/IF/22012034447899 — Rupvati /shanker med bandhan | Completed | 77000 | 76386 | 2019-01-21 | 2019-03-30
CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1736004040/IF/22012034447904 — Shanker/pream.med bandhan | Completed | 38000 | 37410 | 2019-02-18 | 2019-03-30
CHAURAI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1736004040/IF/22012034458331 — med bandhan | Closed | 0 | 0 | 2018-01-26
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736004040/IF/22012034481037 — 104 | Physically Completed | 61028.25 | 50310 | 2019-07-01 | 2020-06-30
CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004040/IF/22012034489235 — Med bandhan kary Sevak/Kevalse Gond | Closed | 0 | 0 | 2019-04-14
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Wasteland Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736004040/IF/22012034489236 — Med bandhan karya Sevak/Kevalsi Gond | Physically Completed | 97677.85 | 66548 | 2020-03-09 | 2021-12-14
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1736004040/IF/22012034490057 — Plantation Chourai Seras Marg Mokha Nala se Forest Takme | Closed | 0 | 0 | 2019-04-14
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736004040/IF/22012034578131 — nab Laxman/Amar morkha | Completed | 60000 | 36825 | 2020-07-27 | 2023-07-19
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736004040/IF/22012034578133 — nab Sukko Bai /Jeevan morkha | Completed | 60000 | 39186 | 2020-07-27 | 2023-08-07
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736004040/IF/22012034578137 — nab Girja Bai/Dashrath morkha | Completed | 60000 | 40353 | 2020-07-27 | 2023-08-07
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736004040/IF/22012034578139 — nab Dasrath/Tejlal morkha | Completed | 60000 | 39186 | 2020-07-27 | 2023-08-19
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736004040/IF/22012034578141 — nab Santoshi/Sumer morkha | Completed | 60000 | 38833 | 2020-07-27 | 2023-08-19
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004040/IF/22012034593665 — Pasu Sed Santram/kaliram | Closed | 0 | 0 | 2020-04-14
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1736004040/IF/22012034940393 — Medbandhan kary Laxman /Amar Morkha | Closed | 0 | 0 | 2022-01-26
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012034940459 — kapil dhara kup rajesh | Closed | 0 | 0 | 2022-04-01
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035310726 — Kapildhara koop Nirman kary Chandravati/Brajlal sareyam | New | 0 | 0 | 2025-01-24
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035310760 — Kapildhara koop Nirman kary Chandravati/Brajlal sareyam | Ongoing | 317966.35 | 133699.2 | 2025-04-08
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035310798 — Kapildhara koop Nirman kary Dinesh/shankarlal dhurve | Approved | 0 | 0 | 2025-01-24
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035310817 — Kapildhara koop Nirman kary Laxman/Amar Gouli | Approved | 0 | 0 | 2025-01-24
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035310833 — Kapildhara koop Nirman kary Budhiya/Mehatri Verma | Approved | 0 | 0 | 2025-01-24
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/22012035319834 — KHET TALAB SHYAMA PATI KAMLESH DUHURVE MORKHA | New | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/22012035319849 — KHET TALAB SHYAMA PATI KAMLESH DUHURVE MORKHA | Physically Completed | 308009.65 | 288990.26 | 2025-04-21 | 2026-04-11
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/22012035319867 — KHET TALAB SANTOSHI SUMER DHURVE MORKHA | Physically Completed | 308009.65 | 287425.92 | 2025-04-21 | 2026-04-11
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035327861 — Kapildhara koop Nirman kary Dinesh/shankarlal dhurve MORKHA | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035327889 — Kapildhara koop Nirman kary Budhiya/Mehatri Verma MORKHA | Ongoing | 304090.23 | 94044.79 | 2025-05-12
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035327918 — Kapildhara koop Nirman kary Laxman/Amar Gouli MORKHA | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/22012035327950 — KHET TALAB SHYAMA PATI KAMLESH DUHURVE MORKHA | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/22012035327984 — Hitgrahi Mulak khet Tala SANTOSHI BAI SUMER DHURVE MORKHA | Approved | 0 | 0 | 2025-04-01
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736004040/IF/22012035336300 — Recharge Pit Nirman Kary Mamta Bai Kapildharara Koop Ke Pass GP Morkha | Physically Completed | 25177.32 | 24837.91 | 2025-04-23 | 2026-04-10
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1736004040/IF/22012035387450 — Recharge pit Stractur Saraswati/Jagan kapildhara koop ke pass morkha | Deleted | 0 | 0 | 2025-04-16
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736004040/IF/22012035387560 — Recharge pit Stractur Saraswati/Jagan kapildhara koop ke pass morkha | Physically Completed | 25177.32 | 24670.78 | 2025-04-28 | 2026-04-10
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736004040/IF/22012035387702 — Recharge pit Stractur Dinesh/Sopat kapildhara koop ke pass kurchadhana GP. Morkha | Physically Completed | 25177.32 | 24888.66 | 2025-04-25 | 2026-04-10
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736004040/IF/22012035389457 — रिचार्ज पिट निर्माण मेहतरी वर्मा के कपिलधारा कूप के पास मोरखा | Physically Completed | 25177.32 | 25085.17 | 2025-04-25 | 2026-04-10
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/22012035449262 — Khet Talab Nirman Kary Mehatri Verma Morkha | Physically Completed | 313187.61 | 284504.44 | 2025-05-03 | 2026-04-11
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004040/IF/22012035455625 — खेत तालाब राजा /ब्रजलाल सरेयाम मोरखा ढाना | Physically Completed | 313687.61 | 290179.6 | 2025-05-12 | 2026-04-11
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736004040/IF/22012035591026 — Ek Bagiya Maa Ke Naam Reeta/Sunil Verma Morkha | Ongoing | 283200.24 | 173080.48 | 2025-09-02
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004040/IF/22012035607852 — Ek Bagiya Maa Ke Naam Ramdhara/Ruplal Uikey Kurchadhana GP Morkha | Deleted | 0 | 0 | 2025-08-16
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1736004040/IF/22012035608048 — Ek Bagiya Maa Ke Naam Ramdhara/Ruplal Uikey Kurchadhana GP Morkha | Deleted | 0 | 0 | 2025-08-16
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736004040/IF/22012035608079 — Ek Bagiya Maa Ke Naam Ramdhara/Ruplal Uikey Kurchadhana GP Morkha | Ongoing | 283594.39 | 77936 | 2025-09-03
CHAURAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/107509 — Construction of IAY House -IAY REG. NO. MP-36-004-040-001/76 | Completed | 15105 | 15226 | 2016-11-07 | 2018-05-10
CHAURAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/107510 — Construction of IAY House -IAY REG. NO. MP-36-004-040-001/92 | Completed | 15105 | 14947 | 2016-10-24 | 2018-05-15
CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/1707934 — Construction of IAY House -IAY REG. NO. MP2327314 | Completed | 16530 | 16530 | 2018-07-02 | 2018-10-23
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2110497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4333678 | Completed | 18050 | 16092 | 2019-07-17 | 2022-05-26
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2112128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4367775 | Completed | 16720 | 16556 | 2019-07-15 | 2020-05-26
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2127976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4735292 | Completed | 16720 | 17007.6 | 2019-07-15 | 2020-05-09
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2130583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4777914 | Completed | 16720 | 16908 | 2019-07-17 | 2020-05-26
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2130585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4777956 | Completed | 16720 | 15136 | 2019-07-17 | 2019-11-14
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2151490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5305256 | Completed | 18050 | 12288 | 2019-08-19 | 2023-01-15
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2151606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5306982 | Completed | 16720 | 16720 | 2019-07-17 | 2020-05-26
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2153406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5345205 | Completed | 16720 | 16544 | 2019-07-15 | 2020-06-05
CHAURAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/230819 — Construction of IAY House -IAY REG. NO. MP1320501 | Completed | 15865 | 15590 | 2017-03-25 | 2018-05-01
CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2360912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4097444 | Completed | 18050 | 15200 | 2020-05-11 | 2023-01-15
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2730947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4406691 | Completed | 18050 | 18335 | 2021-05-03 | 2021-12-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2730963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4408327 | Completed | 18050 | 17949 | 2021-05-31 | 2021-11-26
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2753384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5340718 | Completed | 18050 | 18335 | 2021-05-24 | 2021-11-26
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2753469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5351013 | Completed | 18050 | 18335 | 2021-05-03 | 2021-12-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2754982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4116619 | Completed | 18050 | 8646 | 2021-05-31 | 2023-02-03
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2755452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5340725 | Completed | 18050 | 18278 | 2021-05-24 | 2021-12-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2756662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5358018 | Completed | 18050 | 18335 | 2021-05-24 | 2021-12-24
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/2757449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5422848 | Completed | 18050 | 17949 | 2021-05-24 | 2021-11-26
CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/3118313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5636466 | Completed | 18335 | 18335 | 2021-08-10 | 2021-12-24
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/3683373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105977995 | Completed | 19380 | 12400 | 2022-08-01 | 2023-01-15
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/3755384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127165078 | Completed | 19380 | 18723 | 2022-10-27 | 2023-06-18
CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/419573 — Construction of IAY House -IAY REG. NO. MP1323995 | Completed | 15865 | 15516 | 2017-05-22 | 2018-05-10
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4308354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127134116 | Completed | 19380 | 18787 | 2022-08-09 | 2023-10-21
CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4310073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128036821 | Completed | 19380 | 18564 | 2022-08-09 | 2023-08-02
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4540952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105977783 | Completed | 23085 | 22599 | 2024-10-21 | 2025-01-20
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4540953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105977874 | Completed | 23085 | 23085 | 2024-10-21 | 2025-01-11
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4541073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105994433 | Completed | 23085 | 23085 | 2024-10-21 | 2025-01-20
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4961962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126040368 | Completed | 24795 | 22341 | 2025-03-24 | 2025-08-25
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4986479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103585607 | Completed | 24795 | 23229 | 2025-04-04 | 2025-07-15
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4987666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102895850 | Completed | 24795 | 24669 | 2025-03-24 | 2025-07-14
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4990700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105977933 | Completed | 24795 | 10701 | 2025-04-04 | 2025-06-12
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4990701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105978086 | Completed | 24795 | 23130 | 2025-03-24 | 2025-07-15
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/4990710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105994033 | Completed | 24795 | 20802 | 2025-03-24 | 2025-08-25
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/5084666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127164214 | Completed | 24795 | 24534 | 2025-04-08 | 2025-07-15
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/5085209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127322839 | Completed | 24795 | 23490 | 2025-04-04 | 2025-07-07
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/5085212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127324340 | Completed | 24795 | 23832 | 2025-04-04 | 2025-07-07
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/5634825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102454212 | Completed | 24795 | 24534 | 2025-07-31 | 2025-09-14
CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/847691 — Construction of IAY House -IAY REG. NO. MP1460588 | Completed | 16340 | 15136 | 2017-07-03 | 2018-04-14
CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/847722 — Construction of IAY House -IAY REG. NO. MP1460959 | Completed | 16340 | 16512 | 2017-07-03 | 2018-01-24
CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004040/IF/IAY/876969 — Construction of IAY House -IAY REG. NO. MP1822428 | Completed | 16340 | 15590 | 2017-05-11 | 2018-05-01
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/1258 — मोरखा/ मेढ बंधान निर्माण कार्य (संतोषी/ सुमेर)मोरखा | Completed | 1870 | 24888 | 2012-02-09 | 2012-03-24
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/1259 — मोरखा/ मेढ बंधान निर्माण कार्य (सुखदयाल/केवलसी )मोरखा | Completed | 23400 | 23250 | 2012-02-09 | 2012-05-30
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/1260 — मोरखा/ मेढ बंधान निर्माण कार्य (सुक्‍कोबाई/ जीवन )मोरखा | Completed | 23400 | 23792 | 2012-02-17 | 2012-05-19
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/1261 — मोरखा/ मेढ बंधान निर्माण कार्य (तिलोखी/ कुबल )मोरखा | Completed | 23400 | 70232 | 2012-02-17 | 2013-04-15
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/1262 — मोरखा/ मेढ बंधान निर्माण कार्य (केशराम/ बुध्‍दु )मोरखा | Completed | 44400 | 30866 | 2012-02-17 | 2012-03-23
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/1638 — मोरखा/ मेढ बंधान निर्माण कार्य (तिलोखी/रूपीगोली)मोरखा | Deleted | 14000 | 0 | 2011-04-14
CHAURAI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/1639 — मोरखा/ मेढ बंधान निर्माण कार्य/रफीक/ रहीम/मोरखा | Completed | 18700 | 16764 | 2013-01-07 | 2013-04-15
CHAURAI | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1736004040/LD/22012034306175 — Morkha shantidham kurchadhana | Deleted | 180000 | 0 | 2017-10-02
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736004040/LD/22012034952068 — Hitgrahi Mulak khet Tala SANTOSHI BAI SUMER DHURVE MORKHA | Approved | 0 | 0 | 2025-01-24
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736004040/LD/22012034952074 — Hitgrahi Mulak khet Tala Shyama/Kamlesh DHURVE MORKHA | Approved | 0 | 0 | 2025-01-24
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1736004040/LD/3799407250 — मोरखा खेल मैदान समतलीकरण माध्‍यमिक शाला के सामने | Deleted | 0 | 0 | 2013-04-14
CHAURAI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/3799407251 — मोरखा खेल मैदान समतलीकरण कार्य माध्‍यमिक शाला के स | Completed | 499000 | 432393 | 2013-09-30 | 2016-05-30
CHAURAI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/3799410175 — मोरखा शान्‍तीधाम शमशान घाट मोरखा | Deleted | 453000 | 0 | 2013-08-03
CHAURAI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/3799410259 — मोरखा शांतीधाम निर्मण कार्य | Completed | 453000 | 289988 | 2013-10-14 | 2016-12-22
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1736004040/LD/3799413927 — Morkha Rooplal/Bakaram ST Madbandhan Morkha | Deleted | 0 | 0 | 2013-08-15
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/502 — मोरखा /मेढ बंधान कार्य/नरेश/सोपत/ मोरखा | Deleted | 0 | 0 | 2010-04-01
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/503 — मोरखा/मेढ बंधान कार्य/दशरथ/तेजलाल/मोरखा | Completed | 17000 | 17200 | 2010-04-19 | 2010-05-23
CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/504 — मोरखा/मेढ बंधान कार्य/दिनेश/सेापत/मोरखा | Completed | 17000 | 15000 | 2010-03-29 | 2010-05-15
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/505 — मोरखा/मेढ बंधान कार्य/नरेश/सोपत/मोरखा | Completed | 17000 | 16975 | 2010-04-22 | 2010-04-25
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/527 — मोरखा/ मेढ बंधान कार्य (नरेश/सोपत)मोरखा | Completed | 19000 | 8500 | 2010-05-03 | 2010-05-15
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/544 — मोरखा/ मेढ बंधान कार्य( सरस्‍वती/ जगन मेहरा (मोरखा) | Completed | 17000 | 15900 | 2010-05-03 | 2010-05-23
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/576 — मोरखा/ मेढ बंधान कार्य( बसोडीलाल/ बुध्‍दु) मोरखा | Completed | 17000 | 11446 | 2010-06-14 | 2013-04-15
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/770 — मोरख / मेढ बंधान कार्य निर्माण (दादूराम/ व्रजलाल)मोरखा | Completed | 23400 | 24034 | 2011-06-13 | 2011-06-29
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/771 — मोरख / मेढ बंधान कार्य निर्माण (सुरेश/ सोपत )मोरखा | Completed | 37400 | 35472 | 2011-06-06 | 2012-05-26
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/772 — मोरख / मेढ बंधान कार्य निर्माण (महेश/ बेनी )मोरखा | Completed | 18700 | 17446 | 2011-06-06 | 2012-03-17
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/773 — मोरख / मेढ बंधान कार्य निर्माण (डालसिंग/ मंगल )मोरखा | Completed | 23400 | 24522 | 2011-06-06 | 2012-03-06
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/774 — मोरख / मेढ बंधान कार्य निर्माण (दयाराम/ भोपत )मोरखा | Completed | 70000 | 69548 | 2011-06-06 | 2012-05-24
CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004040/LD/902 — मोरखा/ मेढ बंधान कार्य निर्माण (सकाराम/भोपत) | Completed | 23400 | 57840 | 2011-06-13 | 2013-04-15
CHAURAI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004040/RC/116 — मोरखा / द्वितीय श्रेणी मार्ग निर्माण भगडा से खुरचाढाना 1कि मी | Completed | 467000 | 436702 | 2008-07-14 | 2010-01-20
CHAURAI | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004040/RC/118 — द्वितीय श्रेणी मार्ग निर्माण मोरखा ढाना से मोरखा तक 1 कि मी | Deleted | 0 | 0 | 2007-11-30
CHAURAI | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004040/RC/119 — द्वितीय श्रेणी मार्ग निर्माण मोरखा ढाना से मोरखा तक 1 कि मी | Completed | 481000 | 368574 | 2008-01-28 | 2010-01-20
CHAURAI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/177 — मोरख /सी.सी.रोड निमार्ण कार्य/सुरेश के घर से नारायण के घर तक/कुरचाढाना | Deleted | 54600 | 18060 | 2008-12-20
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034175064 — मोरखा पंचपरमेश्‍वर सीसी सडक रिक्‍खीराम वर्मा के घ | Completed | 96000 | 71716 | 2013-07-15 | 2013-09-08
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034180299 — मोरखा पंचपरमेश्‍वर सीसी सडक निर्माण कार्य गंगाराम | Completed | 96000 | 77476.4 | 2013-09-16 | 2015-01-06
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034190042 — मोरख सी0सी0 सडक नान्‍हीबाई के घर से पीरू घर तक 100 मी0 | Deleted | 0 | 0 | 2013-10-02
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034190043 — मोरखा सी0सी0 सडक नान्‍ही के घर से पीरू के घर तक | Completed | 116000 | 62283 | 2013-10-14 | 2015-01-01
CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004040/RC/22012034190047 — मोरख द्ध‍ितीय श्रेणी मार्ग मोरखा से हसनपुर | Completed | 447000 | 430953 | 2013-10-14 | 2016-05-31
CHAURAI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736004040/RC/22012034229697 — GSB Road Morkha to Pipariyalakkha | Completed | 1443000 | 1077375.57 | 2014-09-29 | 2019-06-30
CHAURAI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004040/RC/22012034302740 — Morkha Khet sadak | Deleted | 0 | 0 | 2016-01-26
CHAURAI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034310665 — Morkha Panchparmeswar anup chandrawanshi ke ghar se middle school tak 100 m | Completed | 67000 | 60937 | 2016-05-04 | 2017-12-11
CHAURAI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004040/RC/22012034312687 — Morkha Main road se Kurchadhana Nala sah 3 Puliya Nirman | Completed | 1397000 | 1111522.9 | 2016-05-17 | 2019-06-30
CHAURAI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034480961 — c.c.Road nirman bhagwati ke ghar se balakram choudhari ke ghar tak 85.00meter | Completed | 32600 | 32384 | 2019-10-07 | 2019-11-22
CHAURAI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736004040/RC/22012034521206 — moksha dham marg | Closed | 0 | 0 | 2020-01-26
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004040/RC/22012034525061 — Murmikaran Road Ruplal ke ghar se Patwari mohalla tak | Closed | 0 | 0 | 2020-04-01
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1736004040/RC/22012034525198 — Morkha se Moxdham tak Murmikaran Road | Closed | 0 | 0 | 2020-04-14
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034543755 — C C. Road Nirman kary Sankardas Ke ghar se RamNath Verma ke ghar Tak | Completed | 27000 | 26980 | 2020-10-12 | 2020-11-30
CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034543760 — Nali Nirman kary CC. 240M | Closed | 20000 | 0 | 2020-08-15
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1736004040/RC/22012034826764 — cc road purusottam verma ke ghar se nakl ke ghar tak 150 m | Approved | 0 | 0 | 2024-08-16
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034826831 — CC Road Prusottam Verma Ke Ghar se Nakal Verma Ke Ghar Tak 150 Met | New | 0 | 0 | 2024-08-16
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034826836 — CC Road Prusottam Verma Ke Ghar se Nakal Verma Ke Ghar Tak 150 Met | New | 0 | 0 | 2024-08-16
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004040/RC/22012034826869 — cc road purushottam keghar se nakal verma ke ghar tak 150 mtr | Completed | 78000 | 74358 | 2024-10-08 | 2026-01-22
CHAURAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004040/RC/389 — मोरखा/ सी.सी.सडक निर्माण कार्य | Completed | 133000 | 46108 | 2010-11-29 | 2011-03-25
CHAURAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004040/RC/390 — मोरखा/द्धितीय श्रैणी मार्ग कार्य चौरई मुख्‍य मार्ग से नन्‍दनढाना तक 1कि.मी | Completed | 458000 | 501801 | 2010-12-22 | 2013-04-15
CHAURAI | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004040/RC/40/1 — मोरखा/द्वितीय श्रेणी मार्ग/मोरखा से पिपरिया मार्ग/मोरखा | Completed | 481000 | 437783.25 | 2007-05-22 | 2010-01-20
CHAURAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004040/RC/505 — मोरखा/ सी.सी.सडक निर्माण कार्य (कुरचाढाना) | Deleted | 33000 | 0 | 2011-01-10
CHAURAI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004040/RC/602 — मोरखा/सी. सी .सडक निर्माण नली कार्य पचंपरमेशवर व | Completed | 143000 | 87616 | 2012-08-27 | 2015-01-01
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1736004040/RS/22012034644992 — Maa ki bagiya nirman karya Madhyamik shala Morkha | Closed | 8002.93 | 0 | 2021-10-02
CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1736004040/RS/22012034646915 — ma ki bagiya nirman karya prathmik shala kurchadhana Morkha | Closed | 0 | 0 | 2021-10-02
CHAURAI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004040/WC/22012034317883 — nirmal neer Devi mandir ke pas kurcha Dhana Morkha | Closed | 445000 | 0 | 2016-10-02
CHAURAI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1736004040/WC/22012034448174 — nirmal neer mokha | Closed | 445000 | 0 | 2019-01-26
CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004040/WC/22012034466241 — Kantrul Tench Morkhadhana Bagdev pahadi par | Completed | 240854 | 229831 | 2020-03-09 | 2021-04-01
CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736004040/WC/22012034543676 — nala pdopchar morkha | Closed | 0 | 0 | 2020-01-26
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1736004040/WC/22012034559791 — Nala Check dam Golanghant Morkha | Completed | 304671.36 | 216257 | 2020-06-22 | 2024-07-14
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1736004040/WC/22012034559793 — New Talab Nirman kary middle school ke peeche chohkabare | Closed | 0 | 0 | 2020-04-01
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1736004040/WC/22012034559796 — Kantrul Tench Bagdev pahadi Part-2 kurchadhana | Completed | 206057.96 | 177320 | 2020-06-22 | 2023-03-30
CHAURAI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/22012034699564 — Boldor ball Nistari Talab ke pass Morkha | Completed | 109062.07 | 98516 | 2021-05-24 | 2023-01-04
CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004040/WC/22012034890842 — box trench nirman Nandan tola se sani mandir tak 1 km | Completed | 713550.66 | 623610 | 2022-05-27 | 2024-02-25
CHAURAI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736004040/WC/22012034907131 — Boxtrench Daityajhiriya wali road morkha se kurchadhana road 1 km | Completed | 563216.17 | 498326 | 2022-03-02 | 2023-01-04
CHAURAI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736004040/WC/22012034907134 — Boxtrench Daityajhiriya wali road morkha se kurchadhana road 1 km | Closed | 0 | 0 | 2021-10-26
CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004040/WC/22012034934452 — cantoor trench nirman bagdev pahadi kurchadhana part 3 | Closed | 0 | 0 | 2022-04-01
CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004040/WC/22012034958610 — cantoor trench nirman bagdev pahadi kurchadhana part 3 gp morkha | Completed | 350739.05 | 298232 | 2022-05-16 | 2023-01-04
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004040/WC/22012035028633 — cantoor trench nirman kurchdhana pahadi | Completed | 956788.02 | 790024 | 2023-07-03 | 2024-02-25
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004040/WC/22012035031974 — CPT WORK MOXDHAM MORKHA 750 MTR. | Completed | 419744.61 | 367104.4 | 2023-08-21 | 2026-01-22
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736004040/WC/22012035141983 — Samudaek khet Talab Daitay jhiriya ke pass Morkha | Physically Completed | 489864.85 | 433228.87 | 2024-02-12 | 2026-04-16
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736004040/WC/22012035141986 — Samudaek khet Talab Daitay jhiriya ke pass Morkha | Physically Completed | 490064.64 | 452653.24 | 2024-07-08 | 2026-06-09
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736004040/WC/22012035142024 — Samudaki Khet Talab Bell bali pahadi ke pass kurchadhana Morkha | Completed | 489864.85 | 354484 | 2023-10-08 | 2024-05-31
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1736004040/WC/22012035156299 — Hitgrahi mulak Khet Talab | Closed | 0 | 0 | 2023-06-19
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1736004040/WC/22012035156300 — Hitgrahi mulak Khet Talab | Completed | 336144.58 | 276214.75 | 2024-03-18 | 2026-02-17
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1736004040/WC/22012035160524 — Contoor Trench | New | 0 | 0 | 2024-01-24
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1736004040/WC/22012035160527 — Boxtrench Nirman Kary | New | 0 | 0 | 2024-01-24
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1736004040/WC/22012035160528 — Boxtrench Nirman Kary | New | 0 | 0 | 2024-01-24
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Block Plantation of Biodrainage Trees in fields for Community | Plantation | 1736004040/WC/22012035172111 — C.P.T. Nirman Kary | New | 0 | 0 | 2024-01-24
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1736004040/WC/22012035184918 — Boldor Ball Nirman Kary Kurchadhana Nala ke Pass | New | 0 | 0 | 2024-01-24
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1736004040/WC/22012035184920 — Boldor Ball Nirman Kary Kurchadhana Nala ke Pass | New | 0 | 0 | 2024-01-24
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1736004040/WC/22012035184938 — CPT. Nirman kary Middle ke Peeche | New | 0 | 0 | 2024-01-24
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/22012035186543 — Boldor Ball Nirman Kary Kurchadhana Nala ke Pass | Completed | 702110.19 | 653079.1 | 2024-03-18 | 2024-12-20
CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736004040/WC/22012035186549 — CPT. Nirman Kary Middle ke Peeche Morkha | Completed | 605025 | 531754.65 | 2024-03-18 | 2024-12-20
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1736004040/WC/22012035200113 — Talab Jirnoddhar Golanghant Nala ke pass wala Talab Morkha | Approved | 0 | 0 | 2024-06-01
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736004040/WC/22012035216839 — Boxtranch Nirman kary Ramnandan Ke Ghar se bhaisasur Baba Chourai Main Road Tak | Completed | 623225.43 | 548881.6 | 2024-09-23 | 2025-05-01
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004040/WC/22012035261965 — Recharge Pit Hanuman Mandir ke Pass Wala Samudaik Koop Ke Pass Morkha | Physically Completed | 25177.32 | 24637.82 | 2025-04-23 | 2026-04-14
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004040/WC/22012035261979 — Recharge Pit Nirman Kary Ramesh soni Ji ke Ghar Ke Samne Wala Samudaik Koop Ke Pass Morkha | Physically Completed | 25177.32 | 24889.38 | 2025-04-23 | 2026-04-14
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004040/WC/22012035262000 — Recharge Pit Nirman Kary Kurchadhana Samudaik Koop Ke Pass GP Morkha | Physically Completed | 25177.32 | 24893.59 | 2025-04-23 | 2026-04-14
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1736004040/WC/22012035277710 — Recharge Stracture Kapildhara Koop Saraswati/Jagan Dehariya Morkha | Deleted | 0 | 0 | 2025-04-16
CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/40/1 — मोरखा/कूप निमार्ण कार्य/मोरखा ढाना | Completed | 135000 | 108521 | 2007-05-21 | 2009-03-25
CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/40/2 — मोरखा/कपिलधारा कूप निर्माण/त्रिलोकी/रूपी/ मोरखा | Completed | 100000 | 153075 | 2007-11-26 | 2009-11-20
CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/40/3 — मोरखा/कपिलधारा कूप निर्माण/सरस्‍वती/ जगन/ मोरखा | Completed | 100000 | 169812.78 | 2007-11-26 | 2009-11-20
CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/40/4 — मोरखा/कूप निर्माण कार्य/पेयजल व्‍यवस्‍था हेतु/मोरखा | Completed | 135000 | 277570.56 | 2007-12-04 | 2009-11-20
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1736004040/WC/75483 — मोखरा/ कपिल धारा कूप निर्माण / रामऔतार / बुध्‍दु) मौरखा | Completed | 100000 | 128998 | 2010-04-06 | 2013-04-15
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1736004040/WC/75484 — मोखरा/ कपिल धारा कूप निर्माण / दिनेश/ सोपत) मौरखा | Completed | 158000 | 16172 | 2010-04-06 | 2016-06-17
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1736004040/WC/75485 — मोखरा/ कपिल धारा कूप निर्माण / बसोडीलाल/ बुध्‍दु) | Completed | 140000 | 156387 | 2010-04-06 | 2015-01-06
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1736004040/WC/75486 — मोरखा/ कपिल धारा कूप निर्माण कार्य ( अ. जाहिद/ कल | Completed | 230000 | 276923 | 2010-04-07 | 2017-02-01
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/75487 — मोरखा/ कपिल धारा कूप निर्माण कार्य (ममताबाई/ नन्‍दकिशोर गोली) मोरखा | Completed | 142000 | 228500 | 2010-04-12 | 2010-04-25
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/75488 — मोरखा/ कपिल धारा कूप निर्माण कार्य (गलीचंद/ पन्‍न | Completed | 230000 | 144525 | 2010-04-07 | 2016-08-30
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/75530 — मोरखा/ सामुदायिक कूप निर्माण कार्य ( मोरखाढाना) | Completed | 228000 | 10290 | 2010-04-12 | 2010-03-02
CHAURAI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004040/WC/76117 — मोरखा/कंन्‍टूर टेरच निर्माण कार्य शा भवन के पीछे/मोरखा | Deleted | 45000 | 0 | 2012-04-14
CHAURAI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736004040/WH/19960443 — Talab jirdodhr Marmat Morkha | Completed | 256000 | 230648 | 2017-05-22 | 2019-07-30
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1736004040/WH/22012034444487 — Chota Talab Vistarikaran kary Morkha | Completed | 431099.32 | 322982 | 2021-03-10 | 2024-02-25
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736004040/WH/22012034939531 — Talab Jirnoddhar bagdev Pahadi ke pass wala Talab Kurchadhana Morkha | Approved | 0 | 0 | 2024-04-14
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736004040/WH/22012034939532 — Talab Jirnoddhar Daitya Baba ke pass wala Talab Morkha | Approved | 0 | 0 | 2024-04-14
CHAURAI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004073/DP/22012034241953 — Plantation Morkha m s school play ground | Deleted | 165900 | 0 | 2017-05-17
CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1736004/DP/167 — क्षिरिया निर्माण कार्य कक्ष क्रमाक 1365 मोरखा ts 301 | Completed | 1800 | 10400 | 2010-04-05 | 2013-01-31
CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1736/WC/22012034569236 — Nistari talab nirman karya Morkha,g.p morkha | Completed | 4780000 | 4034797.26 | 2020-11-04 | 2024-05-02