## Work List
Exported on: 2026-10-22 06:40:23
Filters applied:
Data source: VBGRAMG
District: CHHINDWARA
Block: All
Panchayat: JAMTARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736004091/IF/22012035289928 — Kapil Dhara Kup Nirman Karya Kamal/Santulal Uikey Kumbhpani | Physically Completed | 266004.76 | 0 | 2025-02-20 | 2026-09-29
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736004091/IF/22012035297642 — Kapil Dhara Kup Nirman Karya Sehtu/Nanho Kavreti Kumbhpani | Ongoing | 265504.76 | 0 | 2025-03-19
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736004091/IF/22012035303575 — Khet Talab Nirman Karya Sangeet/Ramsing UIkey Kumbhpani | Ongoing | 299306.87 | 0 | 2025-03-09
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736004091/IF/22012035303579 — Khet Talab Nirman Karya Champa/Ramu Kumre Kumbhpani | New | 0 | 0 | 2025-01-24
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736004091/IF/22012035306442 — Khet Talab Nirman Karya Devendra/Chunaram Uikey Kumbhpani | Physically Completed | 341597.26 | 0 | 2025-03-19 | 2026-09-29
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736004091/IF/22012035306445 — Khet Talab Nirman Karya Shivcharan/Janagalsing Uikey Kumbhpani | Ongoing | 341597.26 | 0 | 2025-03-19
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736004091/IF/22012035306446 — Khet Talab Nirman Karya Ishwariprasad/Battulal Uikey Kumbhpani | Ongoing | 341597.26 | 0 | 2025-03-19
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736004091/IF/22012035306447 — Khet Talab Nirman Karya Santosh/Bansa Uikey Kumbhpani | Approved | 341597.26 | 0 | 2025-01-25
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736004091/IF/22012035306527 — Kapil Dhara Kup Nirman Karya Mehanglal/Lakhan Dhurve Kumbhpani | Ongoing | 393613.84 | 0 | 2025-03-15
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736004091/IF/22012035306548 — Khet Talab Nirman Karya Surajvati/Brajlal Kavreti Kumbhpani | Physically Completed | 341597.26 | 0 | 2025-03-19 | 2026-09-29
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736004091/IF/22012035307395 — Kapil Dhara Kup Nirman Karya Indarsing/Dhupi Inwati Kumbhpani | Ongoing | 292206.56 | 0 | 2025-03-15
CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736004091/IF/22012035307397 — Kapil Dhara Kup Nirman Karya Sahu/Janglu Uikey Kumbhpani | Ongoing | 386937.84 | 0 | 2025-03-16
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004091/IF/22012035608025 — Ek Bagiya Ma Name Munni/Mehtu Avthare Jamtara | New | 0 | 0 | 2025-06-05
CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004091/IF/22012035608290 — Ek Bagiya Ma Ke Name Munni/Mehtu Avthare Jamtara | Ongoing | 284386.03 | 10200 | 2025-09-05
CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736004091/IF/IAY/2199618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5353418 | Approved | 28500 | 0 | 2019-07-01
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1736004091/RC/22012034835868 — Nali Nirman Ruplal KeGhar Se Tilya Ke Ghar Tak Jamtatra | Approved | 0 | 0 | 2024-08-16
CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1736004091/RC/22012034837117 — Nali Nirman Ruplal KeGhar Se Tilya Ke Ghar Tak Jamtatra | New | 0 | 0 | 2024-08-16
CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1736004091/RS/22012035122718 — Jamtara Nadep Nirman Bajar Chouk Jamtara | New | 0 | 0 | 2024-01-24
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1736004091/WC/22012035226600 — Talab nirman percolation tenk kary Jamtara | Approved | 0 | 0 | 2024-10-02
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1736004091/WC/22012035226622 — Talab Nirman Parcolation Tank Karya Jamtara | Approved | 0 | 0 | 2024-10-02
CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1736004091/WC/22012035242895 — Parcolation Tank Nirman Karya Jamtara | Approved | 0 | 0 | 2025-01-14
CHAURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736004091/WC/22012035277514 — RECHARGE PIT NIRMAN Nirmal Nir Ghumadsing Mandekar Ke Ghar Pas Jamtara | Ongoing | 25899.46 | 0 | 2025-04-23
CHAURAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736004091/WC/VB/YD/22012035336135 — cantoor trench paryatan pahadi jamtara | Deleted | 0 | 0 | 2026-08-19
CHAURAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736004091/WC/VB/YD/22012035336138 — Cantoor Tench Nirman Mokshdham pahadi Jamtara | Deleted | 0 | 0 | 2026-08-19
CHAURAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736004091/WC/VB/YD/22012035336484 — Cantoor Tench Nirman Paryatan Pahadi Jamtara | Approved | 827837.06 | 0 | 2026-08-19
CHAURAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736004091/WC/VB/YD/22012035336485 — Cantoor Tench Nirman Mokshdham Pahadi Jamtara | Approved | 887017.15 | 0 | 2026-08-19