## Work List
Exported on: 2026-09-03 08:13:26
Filters applied:
Data source: VBGRAMG
District: CHHINDWARA
Block: All
Panchayat: GOPH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JAMAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736005011/DP/22012034553807 — Nirmal Neer koop nirmad kary bhimkund | Physically Completed | 489496.27 | 0 | 2023-04-17 | 2026-07-08
JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1736005011/DP/22012034623397 — व़क्षारोपण कार्य खेडादाई के पास भौराखापा ग्राम पंचायत गोप | Approved | 812728.34 | 0 | 2024-06-17
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736005011/IF/22012035327653 — Kapil Dhara Nirman Karya Shree Bisarlal Pita Horilal Bhaura khapa | Ongoing | 327116.44 | 0 | 2025-05-10
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736005011/IF/22012035456937 — KHET TALAB NIRMAN KARYA SHREE BHAGLAL PITA MANLAL GRAM GOP | Physically Completed | 199916.98 | 0 | 2025-06-03 | 2026-07-06
JAMAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5827806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146638496 | Approved | 28500 | 0 | 2025-03-03
JAMAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5843684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146853406 | Ongoing | 28500 | 0 | 2026-08-05
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5844293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146939176 | Ongoing | 28500 | 3900 | 2026-02-11
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5844342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146619798 | Ongoing | 28500 | 0 | 2025-11-24
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5844786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149501452 | Ongoing | 28500 | 2600 | 2026-02-11
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5845374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147216672 | Ongoing | 28500 | 0 | 2026-02-11
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5845669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146845939 | Ongoing | 28500 | 1300 | 2026-02-16
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5845856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146432880 | Ongoing | 28500 | 1300 | 2025-10-27
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5846078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146808602 | Ongoing | 28500 | 0 | 2025-11-24
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736005011/IF/IAY/5846115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146420346 | Ongoing | 28500 | 0 | 2026-03-12
JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1736005011/LD/22012034942436 — वृक्ष रोपण कार्य गोप पंचायत भवन के पास | Approved | 453563.17 | 0 | 2024-06-10
JAMAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736005011/RC/22012034679398 — पुलिया निर्माड कार्य दुली दोधार नाला जमुनडोंगा में ग्रा. पंचायत गोप | Ongoing | 1154049.69 | 0 | 2024-10-09
JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005011/WC/22012035140605 — लूज बोल्डर चेक डेम गोप ग्राम पचायत गोप भाग 3 | Ongoing | 400109.52 | 0 | 2024-12-23
JAMAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736005011/WC/22012035250257 — निस्तारी तालाब निर्माण कार्य कोट नाला भौराखापा | Ongoing | 1436996.97 | 13200 | 2025-04-01
JAMAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736005011/WC/22012035254693 — TALAB NISTARI TALAB CHURANAPANI GP GOP | Ongoing | 1470996.44 | 59100 | 2025-04-01
JAMAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736005011/WC/22012035324386 — निस्‍तारी तालाब निर्माण कार्य गोप | Approved | 1470552.84 | 0 | 2025-04-14
JAMAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1736/WC/22012035153989 — Naveen Nistari Talab Belbala jhil gram Gop | Ongoing | 5901000 | 0 | 2024-02-05