## Work List
Exported on: 2026-10-23 19:52:45
Filters applied:
Data source: VBGRAMG
District: CHHINDWARA
Block: All
Panchayat: PINDRAIKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1736005053/DP/22012034622589 — Vraksharopan Karya Road Kinare Gram Pindraikala | Ongoing | 812728.34 | 5132 | 2024-07-29
JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1736005053/DP/22012034622592 — Vraksharopan Karya Road Kinare Gram Bakatawa | Ongoing | 812728.34 | 0 | 2024-07-29
JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of water course Canal for Community / Repair and Maintenance of water course Canal for Community | Repair & Maint of Canal | 1736005053/IC/22012034883375 — निर्मल नीर शिवचरण के खेत के पास पिन्डरईकला | Ongoing | 490862.37 | 0 | 2024-12-02
JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of water course Canal for Community / Repair and Maintenance of water course Canal for Community | Repair & Maint of Canal | 1736005053/IC/22012034883376 — निर्मल नीर नंदा के खेत के पास पिन्डरईकला | Ongoing | 490862.37 | 0 | 2024-12-02
JAMAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1736005053/IF/22012034601255 — NAB-वक्षा रोपण कार्य | Ongoing | 400000 | 0 | 2020-09-14
JAMAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1736005053/IF/22012034601269 — NAB-वक्षा रोपण कार्य | Ongoing | 400000 | 0 | 2020-09-14
JAMAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1736005053/IF/22012034601449 — NAB VRAKSHA ROPAN | Ongoing | 400000 | 0 | 2020-09-14
JAMAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1736005053/IF/22012034601468 — NAB वृक्षा रोपण निर्माण कार्य पधार वन ग्राम | Ongoing | 400000 | 0 | 2020-09-14
JAMAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1736005053/IF/22012034601876 — NAB वृक्षा रोपण निर्माण कार्य बाकातवां | Ongoing | 400000 | 0 | 2020-09-14
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736005053/IF/22012035292725 — कपिलधारा कूूपनिर्माण कार्य समलू मोजी के खेत में पिंडरईकला | Ongoing | 295000.39 | 0 | 2025-04-24
JAMAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736005053/IF/22012035292729 — कपिलधारा कूप अभीराम यदुवंशी के खेत में ग्राम बाकातबा | Approved | 295000.39 | 0 | 2024-10-02
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736005053/IF/22012035333780 — Kapildhara koop nirman kary Laxman sheelu gram bakatawa gp pindraikala | Ongoing | 324810.51 | 0 | 2025-05-17
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736005053/IF/22012035333791 — Kapildhara koop nirman kary Fhoolabai sheelu gram padar van gram gp pindraikala | Ongoing | 324810.51 | 0 | 2025-05-10
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736005053/IF/22012035333800 — Kapildhara koop nirman kary rammo mousi gram pader van gram gp pindraikala | Ongoing | 324810.51 | 0 | 2025-04-24
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736005053/IF/22012035333808 — Kapildhara koop nirman kary Peetamlal sheelu gram pader van gram gp pindraikala | Ongoing | 324810.51 | 0 | 2025-04-24
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736005053/IF/22012035405071 — Khet talab nirman kary Gorelal Lobo ke khet per gram padar van gram gp pindraikala | Ongoing | 199448.71 | 0 | 2025-05-10
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736005053/IF/22012035405585 — Khet talab nirman kary Sakarlal kayda ke khet per gram pindraikala gp pindraikala | New | 0 | 0 | 2025-04-01
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736005053/IF/22012035593775 — Ek Bagiya Maa Ke Naam vatiya darshma | Ongoing | 269386.03 | 2891.04 | 2025-09-08
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736005053/IF/22012035593798 — Ek Bagiya Maa Ke Naam Ku kiran Lobo | Ongoing | 269386.03 | 3771 | 2025-09-08
JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736005053/IF/22012035593822 — Ek Bagiya Maa Ke Naam Asha Shilu | Ongoing | 269386.03 | 3268 | 2025-09-09
JAMAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1736005053/RC/22012034635306 — रपटा निर्माण कार्य शम्भूलाल के घर के सामने | Ongoing | 1255695.14 | 0 | 2023-06-19
JAMAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1736005053/WC/22012035032692 — stop dem nirman karya sukkan ke khet ke pas | Ongoing | 913999.58 | 0 | 2023-10-05
JAMAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1736005053/WC/22012035304608 — Nistari Talab Nirman Karya Foolwati Darshma Ke Khet Ke Pas Gram Pindraikala | Ongoing | 1438074.22 | 0 | 2026-02-27