## Work List
Exported on: 2026-10-02 03:43:54
Filters applied:
Data source: MGNREGA
District: CHHINDWARA
Block: All
Panchayat: PAUNAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736007011/AV/22012034582710 — DiningTable HS Pounar Dhana | Deleted | 0 | 0 | 2021-01-28
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736007011/AV/22012034582711 — DiningTable HS Pounar Dhana | Deleted | 0 | 0 | 2021-01-28
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736007011/AV/22012034582712 — DiningTable PS Pounar Dhana | Closed | 0 | 0 | 2021-01-28
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736007011/AV/22012034582713 — DININGTABLE HS POUNAR | Closed | 0 | 0 | 2021-01-28
MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1736007011/AV/22012034635610 — Puliya NIrman Kary Tigai Road Chhoti Nadi Ponar | Completed | 1497687.84 | 1493542.21 | 2023-06-24 | 2024-10-16
MOHKHED | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007011/DP/22012034233237 — Plantation Road Side - पंचायत भवन से करलाकला, ग्रा-पं. पौनार | Completed | 257000 | 54921 | 2016-07-23 | 2020-09-09
MOHKHED | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1736007011/DP/22012034423705 — Plantation Road Line - Rampyari ke ghar pass se Tighara Road | Completed | 342000 | 121621 | 2018-07-28 | 2021-06-15
MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1736007011/DP/22012034445862 — Nirmal Neer Kup NIRMAN VARD NO 12 HARANAKHEDI ROAD, Pounar | Completed | 445000 | 444428 | 2019-03-12 | 2021-06-28
MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007011/DP/22012034488855 — (Contour Trench Golahari | Completed | 497012.46 | 431219 | 2020-07-25 | 2024-06-21
MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007011/DP/22012034492438 — Plantation-Shanti Dham Pounar | Deleted | 0 | 0 | 2020-04-15
MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736007011/DP/22012034492847 — Plantation RSP- Shanti Dham Pounar | Completed | 390826.48 | 202366 | 2020-10-03 | 2022-07-19
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736007011/DP/22012034530357 — Plantation RSP - POunar Dhana School Ke Samne | Completed | 394489.84 | 205192 | 2021-07-10 | 2025-10-16
MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736007011/DP/22012034567498 — Plantation work at Pataniya Road Ponar | Completed | 409999.57 | 184636 | 2022-09-24 | 2026-04-27
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1736007011/DP/22012034585013 — Vacsharopan Kary Talab Ke Pass Pounar 75 Poudha | Completed | 55847.4 | 28697 | 2023-09-16 | 2025-10-16
MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736007011/DP/22012034615090 — CNG Vasudha Vandan Amrit Vatika Tigai Road Talab Ke Pass Pounar | Ongoing | 988687.99 | 464452.88 | 2024-08-24
MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007011/DP/22012034622754 — Plantation at Gohalari Pahadi contur trnch Ponar 625 | Ongoing | 853685.12 | 74373 | 2024-08-10
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007011/DP/पौनर///420 — व्रक्षारोपण कार्य पौनार | Completed | 100000 | 18004 | 2007-07-24 | 2011-08-06
MOHKHED | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/1000035158 — क‍पील धारा रामदास पिता फग्‍गू | Completed | 276000 | 170657.15 | 2013-09-14 | 2014-09-10
MOHKHED | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/1000035531 — वर्मी कम्‍पोट दशरथ पिता पुरण | Deleted | 13061 | 0 | 2013-08-15
MOHKHED | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/1000037814 — MED BANDHAN KHEMCHAND / SADUA | Completed | 115000 | 25248 | 2013-09-28 | 2014-02-07
MOHKHED | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/1000038491 — मेढबंधान कार्य सन्तु/गुरदी पौनार | Completed | 141000 | 10508 | 2013-09-28 | 2014-02-07
MOHKHED | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007011/IF/1000038502 — भूमि शिल्प रूपचंद /सदुआ | Completed | 123000 | 20248 | 2013-09-28 | 2014-02-07
MOHKHED | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/1000040846 — मेंढ बंधान धनवती / बैसाकू | Deleted | 122400 | 0 | 2013-08-15
MOHKHED | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/1000040853 — मेंढ बंधान रूपवती / बैसाकू | Deleted | 79300 | 0 | 2013-08-15
MOHKHED | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1736007011/IF/1000044425 — GOAD SHELTER JETHU /KHEMCHAND | Deleted | 49514 | 0 | 2014-06-28
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012034297433 — Nandan Faloudhyan - Kachra Bai / Likkhu | Deleted | 0 | 0 | 2016-05-10
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012034297437 — Nandan Faloudhyan - Kachra Bai / Likkhu | Deleted | 0 | 0 | 2016-05-10
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012034297454 — Nandan Faloudhyan - Kachra Bai / Likkhu | Completed | 121000 | 54533 | 2016-08-20 | 2019-09-11
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012034297461 — Nandan Faloudhyan - manoj / ramdayal | Completed | 121000 | 39105 | 2016-08-20 | 2019-09-11
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012034302516 — KHET TALAB NIRMAN MANOJ / RAMDAYAL | Completed | 357000 | 353825 | 2016-11-05 | 2017-10-10
MOHKHED | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Cross Bund / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1736007011/IF/22012034315470 — KHET TALAB RUPCHAND / SADUA | Deleted | 0 | 0 | 2017-01-26
MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012034315474 — NADEP CHAMPLAL / PHAGGU | Deleted | 0 | 0 | 2017-01-26
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034334873 — FRA KAPILDHARA KUP BISANLAL/GHSITHA | Completed | 230000 | 223830 | 2017-04-22 | 2018-05-25
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012034339925 — Plantation RSP- Pounar to Suresh ke ghar tak | Completed | 335000 | 179299 | 2017-05-27 | 2021-06-15
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012034343324 — Plantation RSP- Prahlad ke ghar se banjari mail tak | Completed | 335000 | 193281 | 2017-05-27 | 2021-06-15
MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034385244 — Kapildhara kup Heeralal/Chintu | Completed | 210000 | 207234 | 2018-05-12 | 2019-10-04
MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034385245 — KAPILDHARA KOOP NIRMAN GANESHPRASAD/MAROTI | Completed | 210000 | 203698 | 2018-05-12 | 2020-05-04
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034385246 — Kapildhara With Farm Pond | Deleted | 0 | 0 | 2017-11-01
MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1736007011/IF/22012034385278 — Plantation Farm Bund -Tutu, Ganesh, Hiralal, Jangannath, Rajesh and Sahasram, POUNAR | Completed | 188000 | 118884 | 2018-09-01 | 2020-11-02
MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012034450096 — KHET TALAB BABULAL / MADAN | Completed | 91000 | 62156 | 2019-01-12 | 2020-08-12
MOHKHED | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1736007011/IF/22012034457152 — Med Bandhan (Boldar) | Deleted | 0 | 0 | 2018-10-02
MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034470879 — Kapildhara Kup MIRMAN JAGDISH/PARTAP, Paunar | Completed | 210000 | 145550 | 2019-03-16 | 2021-11-10
MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034470897 — Kapildhara Kup NIRMAN SHRIRAM/JAGDISH, Paunar | Completed | 210000 | 207726 | 2019-03-16 | 2021-06-18
MOHKHED | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012034471011 — NADEP SHED NIRMAN RAMDAS/PHAGGU, Paunar | Completed | 11000 | 10979.76 | 2019-03-16 | 2020-09-26
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034510697 — KAPILDHARA KUP NIRMAN JAGANATAH / RAMCHAND | Deleted | 0 | 0 | 2019-10-02
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007011/IF/22012034510698 — MED BANDHAN SHRIRAM/ JAGDESH | Deleted | 0 | 0 | 2019-10-02
MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1736007011/IF/22012034546872 — Med Bandham - Tejiram / Bhuvan | Completed | 148152.33 | 86188 | 2020-05-10 | 2021-06-18
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012034568417 — Mitti Med Bandhan Dannu / Ramchand | Completed | 101349.53 | 75220 | 2020-06-14 | 2020-08-25
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579075 — Neno Archid Falodhyan Sirpat / Tutu Pawar | Completed | 58286 | 46517 | 2020-07-18 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579086 — Neno Archid Falodhyan Pandari / Bhaiyalal | Completed | 58286 | 45412 | 2020-07-18 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579096 — Neno Archid Falodhyan Ramdas / Phaggu | Completed | 58286 | 35066 | 2020-07-18 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579104 — Neno Archid Falodhyan Ramdayal / Kisan | Completed | 58286 | 36927 | 2020-09-05 | 2023-11-03
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579118 — Neno Archid Falodhyan Kuvarlal / Umendra | Completed | 58286 | 34199 | 2020-07-25 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579347 — Neno Archid Falodhyan Ganaram / Mahu | Completed | 58286 | 32445 | 2020-07-18 | 2023-11-03
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579350 — Neno Archid Falodhayan Narayan / Pitru | Completed | 58286 | 39060 | 2020-08-08 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579351 — Neno Archid Falodhyan Sukhram / Saharu | Completed | 45912386 | 46156 | 2020-07-25 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034579353 — Neno Archid Falodhayan Shriram / Jagdish | Completed | 58286 | 40021 | 2020-07-18 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034581168 — Neno Archid Faloyadhan Rasmani/ Pritam | Completed | 58286 | 45916 | 2020-08-01 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034581547 — Neno Archid Falodhayan Kushmani / Gumansing | Completed | 58286 | 46800 | 2020-09-16 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034581549 — Neno Archid Faloyadhan Kashi /Bisanlal | Completed | 58286 | 40191 | 2020-07-18 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034581551 — Neno Archid Faloyadhan Devka / Ganpat | Completed | 58286 | 37794 | 2020-07-18 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034581552 — Neno Archid Faloyadhan Yamuna / Eshavar Dayal | Completed | 58286 | 43080 | 2020-07-18 | 2022-11-06
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034581553 — Neno Archid Faloyadhan Vidhya / Sukhdayal | Completed | 58286 | 33032 | 2020-09-16 | 2023-06-01
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034581578 — Neno Archid Faloyadhan Genda / Tekchand | Completed | 58286 | 39750 | 2020-07-18 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1736007011/IF/22012034593243 — Poultry Shet - Shivaji / heera Bhojkar | Deleted | 0 | 0 | 2020-04-15
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1736007011/IF/22012034593591 — Poultry Shet - Shivaji / Heera Bhojkar | Deleted | 0 | 0 | 2020-04-15
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034593756 — Neno Archid Faloyadhan Koushaliya / champalal | Completed | 58296 | 37466 | 2020-08-08 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034593803 — Neno Archid Faloyadhan Dulari / Ramaprasad | Completed | 58296 | 45889 | 2020-09-05 | 2022-12-10
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034593805 — Neno Archid Faloyadhan Kusum / Antaram | Completed | 58296 | 43542 | 2020-09-12 | 2023-06-01
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034593807 — Neno Archid Faloyadhan Kriti / Dinesh | Completed | 58296 | 41478 | 2020-08-08 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007011/IF/22012034596158 — Cattle Shelter - Dinesh / hanslal | Completed | 101273.16 | 83958.28 | 2020-11-20 | 2021-06-08
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007011/IF/22012034598034 — Cattale shaid-Pandhari/Bhaiyalal | Completed | 101273.16 | 97290.24 | 2020-12-26 | 2022-04-05
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007011/IF/22012034600175 — Cattle Shelter- Devchand / Kamalsing | Completed | 101273.16 | 98100 | 2021-02-06 | 2021-07-02
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1736007011/IF/22012034606379 — Neno Archid Falodhyan.Devchandra/Kamalsing | Deleted | 0 | 0 | 2020-08-15
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007011/IF/22012034612966 — Cattle Shelter - Pappu / Bhuvan | Closed | 0 | 0 | 2020-04-15
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012034613591 — Neno Archid Faloyadhan Devchand / Kamalsing | Completed | 58300 | 33735 | 2020-09-28 | 2022-11-12
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007011/IF/22012034621831 — Cattle Shelter - Sukhvati / Biharilal | Closed | 0 | 0 | 2020-04-15
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1736007011/IF/22012034621837 — Poultry Shelter - Munna / Ghusiya | Closed | 0 | 0 | 2020-10-02
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034621839 — MED BANDHAN - MUNNA / GHUSIYA | Completed | 68833.24 | 57560 | 2021-04-24 | 2021-06-08
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034640241 — Kapil dhara Dhannu/Ram hand Pawar | Completed | 228682.41 | 215647.39 | 2021-05-08 | 2022-12-22
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012034731885 — KAPILDHARA KUP NIRMAN BHOLARAM / RAGHUNANDAN PAWAR | Deleted | 0 | 0 | 2021-01-26
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012034731901 — Med Bandhan Kushmani / Gumansing | Completed | 62834.54 | 47794 | 2021-06-12 | 2021-12-23
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034900742 — Kapil Dhara Kup Nirman Jagannath / Ramchand Pawar | Completed | 247641.81 | 231103.86 | 2022-04-16 | 2023-07-28
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034915655 — Kapildhara Kup Nirman Bholaram / Raghunandan | Completed | 249980 | 228459.86 | 2022-02-23 | 2022-12-22
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034939065 — Kapil Dhara Kup Nirman Ashok / Mohanlal Pawar | Deleted | 0 | 0 | 2022-01-26
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012034956448 — Kapildhara Kup Tutu / Bhalatyaji | Deleted | 0 | 0 | 2022-01-24
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012035008188 — Nadap Nirman Kary Rameshwar / Punaji Pawar | Closed | 15784.89 | 0 | 2022-01-27
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012035008194 — Nadap Nirman Kary Kushmani / Gumansing | Closed | 0 | 0 | 2022-01-27
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012035008198 — Nadap Nirman Kary Kuvarlal / Umendra | Closed | 15978.27 | 0 | 2022-01-27
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012035023090 — Naino Archid Faloyadhan Munna / Ghusiya Pawar | Completed | 61085 | 51346 | 2023-12-16 | 2026-03-31
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012035023093 — Naino Archid Faloyadhan Shivaji / Hira Bhojkar | Completed | 61085 | 51150 | 2023-12-16 | 2026-03-31
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012035023095 — Naino Archid Faloyadhan Mayaram / Shivcharan | Completed | 61085 | 43634 | 2023-12-16 | 2026-04-15
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012035023096 — Naino Archid Faloyadhan Dulari / Hunnilal | Completed | 61085 | 43473 | 2023-12-30 | 2026-05-31
MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012035030356 — Nadep Nirman kary Jagannath / Ramchand Pawar | Deleted | 0 | 0 | 2022-08-16
MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012035048610 — Nadep Nirman kary Jagannath / Ramchand Pawar | Closed | 0 | 0 | 2022-08-16
MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007011/IF/22012035048613 — Nadep Nirman kary Dhannu / Ramchand Pawar | Closed | 0 | 0 | 2022-08-16
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035064985 — Kapil Dhara Kup Nirman Durgesh / Komal | Completed | 262338.5 | 260953.05 | 2023-10-07 | 2025-09-09
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035064989 — Kapil Dhara Kup Nirman Nanakram / Chaitram Pawar | Deleted | 0 | 0 | 2023-01-24
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012035066737 — Naino Archid Falodhayan Nisha / Jagannath | Completed | 61085 | 51440 | 2023-12-16 | 2026-03-31
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007011/IF/22012035066744 — Naino Archid Falodhayan Kesar / Kanhaiya | Completed | 61085 | 42374 | 2023-12-30 | 2026-07-07
MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1736007011/IF/22012035074019 — Shok Pit Hitgrahi Chaitram, Dilip, Rajendra, Santosh, Manoj, Muniya, Laxman, Kesar, Indravati, Revam | Completed | 144019.13 | 119299 | 2023-07-15 | 2024-11-11
MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1736007011/IF/22012035074021 — Souk Pit - Supchand, Suresh, Rambharos, Shankar, Pandari, Harishchand, Revaram, Ratanlal, Manak,Gopa | Deleted | 0 | 0 | 2023-02-11
MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1736007011/IF/22012035074022 — Souk Pit - Rajesh, Kumer, Raghuveer, Baldev, Dhanlal | Deleted | 0 | 0 | 2023-02-11
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035085793 — Kapil Dhara Kup Nierman Ashok / Mohanlal Pawar | Completed | 257820.89 | 257161.08 | 2023-12-12 | 2025-09-09
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035085796 — Kapil Dhara Kup Nierman Nanakram / Chaitram Pawar | Ongoing | 259820.29 | 188028.16 | 2023-05-30
MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1736007011/IF/22012035100540 — Shok Pit ( Supchand Suresh Rambharosh Shankar Pandhari Harishchand Revaram Ratanlal Manak Gopal) | Completed | 108818.86 | 106258.4 | 2023-10-07 | 2025-04-28
MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1736007011/IF/22012035100544 — Shok Pit (Dhanlal Baldev Raghuveer Kumer Rajesh) | Completed | 56106.8 | 55702 | 2023-10-07 | 2024-11-11
MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012035101900 — Khet Talab NIrman Kary Shyamrao kundlik bhojker Ponar | Closed | 222820.73 | 0 | 2023-04-14
MOHKHED | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1736007011/IF/22012035222513 — कपिलधारा कूप निमाण रामप॒साद | Physically Completed | 270164.5 | 235775.44 | 2024-11-16 | 2026-06-02
MOHKHED | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1736007011/IF/22012035222518 — कपिलधारा कूप निमाण प्रवीण | Closed | 272950.76 | 2430 | 2025-03-01
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035313067 — Kapil Dhara Kup Somvati / Budhhman | Deleted | 0 | 0 | 2025-01-24
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035320226 — Kapildhara Kup Nirman Umesh / Heera Bhojkar | Ongoing | 283201.39 | 178414.55 | 2025-05-05
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035323159 — Kapildhara Kup Nirman Somavati / Budhhman Chouriya | Ongoing | 288266.14 | 109302.8 | 2025-05-24
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035369134 — Dugwell Recharge Pit Kapildhara Yashpal Pawar | Approved | 25899.46 | 0 | 2025-04-14
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035369247 — Dugwell Recharge Pit kapildhara Bholram Pawar | Deleted | 0 | 0 | 2025-04-14
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012035369279 — Dugwell Recharge Pit kapildhara Bholaram Pawar | Approved | 25899.46 | 0 | 2025-04-14
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012035369301 — Dugwell Recharge Pit Kapildhara Jagannath Pawar | Approved | 25899.46 | 0 | 2025-04-14
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007011/IF/22012035428867 — Dugwell Recharge Pit Jagannath / Ramchand Pawar | Physically Completed | 25899.46 | 25327.32 | 2025-05-05 | 2026-01-21
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007011/IF/22012035428902 — Dugwell Recharge Pit Bholaram / Raguunandan Pawar | Physically Completed | 25899.46 | 25593.32 | 2025-05-01 | 2026-01-21
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007011/IF/22012035428940 — Dugwell Recharge Pit Dhannu / Ranchand Pawar | Physically Completed | 25899.46 | 25387.32 | 2025-05-05 | 2026-01-21
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007011/IF/22012035483456 — Dugwell Recharge Pit Jagdish / Pratap Mahadule | Deleted | 0 | 0 | 2025-04-14
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012035489278 — Khet talab nirman karya Rajesh baby chohan ponar | Physically Completed | 185441.45 | 147453.77 | 2025-05-10 | 2026-02-15
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012035584625 — Ek Bagiya Maa Ke Sushila Pawar MP36007011001 180 | Closed | 266577.25 | 260.71 | 2025-09-06
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007011/IF/22012035584662 — Ek Bagiya Maa Ke Chhaya Pawar MP36007011001 119A | Approved | 266577.25 | 0 | 2025-08-01
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/9993747551 — खेत तालाब देवका / गनपत | Deleted | 67000 | 0 | 2016-06-25
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2108401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4306989 | Completed | 16720 | 16720 | 2019-07-20 | 2019-11-04
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2140038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5019071 | Completed | 16720 | 16720 | 2019-07-27 | 2020-02-09
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2140041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5019155 | Completed | 18050 | 16720 | 2019-08-03 | 2021-02-17
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2141276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5052715 | Completed | 18050 | 16720 | 2019-07-27 | 2020-09-28
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2167616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5714440 | Completed | 16720 | 16720 | 2019-07-27 | 2019-12-16
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2219792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2908794 | Completed | 16720 | 16720 | 2019-11-02 | 2020-06-03
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2427273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5023854 | Completed | 18050 | 18050 | 2020-05-06 | 2020-08-25
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2656986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2243995 | Completed | 18050 | 17949 | 2021-06-19 | 2021-12-02
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2663518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3974306 | Completed | 18050 | 17949 | 2021-06-05 | 2021-12-02
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/2686701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4754435 | Completed | 18050 | 18335 | 2021-04-03 | 2021-11-23
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/295749 — Construction of IAY House -IAY REG. NO. MP1012182 | Completed | 15865 | 15326 | 2017-03-18 | 2018-02-01
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/3163884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5663501 | Completed | 18335 | 18275 | 2022-03-22 | 2022-08-10
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/362286 — Construction of IAY House -IAY REG. NO. MP1152648 | Completed | 15865 | 15016 | 2017-03-11 | 2017-09-27
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/3773545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127454665 | Completed | 19380 | 19380 | 2022-08-20 | 2023-01-23
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/3867713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145083349 | Completed | 19380 | 19380 | 2022-08-06 | 2023-01-10
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/3873753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141339164 | Completed | 19380 | 19176 | 2022-08-20 | 2022-11-22
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/3874916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141451910 | Completed | 19380 | 19380 | 2022-07-09 | 2023-02-09
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/3917663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127996960 | Completed | 19380 | 19380 | 2022-07-16 | 2022-08-30
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/3918847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128046012 | Completed | 19380 | 19380 | 2022-10-26 | 2023-03-28
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/4339984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114947761 | Completed | 19380 | 19380 | 2022-09-17 | 2022-12-15
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/4548154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106704250 | Completed | 23085 | 23085 | 2024-10-26 | 2025-01-31
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/4628448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127463705 | Completed | 23085 | 23085 | 2024-11-16 | 2025-02-28
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/4628482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127468710 | Completed | 23085 | 23085 | 2024-10-26 | 2025-01-31
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/4652564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146409916 | Completed | 24795 | 22842 | 2024-10-26 | 2025-04-22
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5361010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141451936 | Completed | 24795 | 24795 | 2025-09-13 | 2026-04-15
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5361794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145063119 | Completed | 24795 | 24795 | 2025-04-12 | 2025-05-20
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5363966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127927889 | Completed | 24795 | 24795 | 2025-08-16 | 2025-12-22
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5365123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127941447 | Ongoing | 24795 | 19053 | 2025-07-05
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5366985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146412020 | Completed | 24795 | 24795 | 2025-04-12 | 2025-11-17
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5368462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127273750 | Completed | 24795 | 24795 | 2025-08-09 | 2026-02-13
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5587573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106883583 | Completed | 24795 | 24795 | 2025-07-05 | 2025-08-11
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5814690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114947797 | Completed | 24795 | 24795 | 2025-09-20 | 2025-10-12
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5814777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147159328 | Completed | 24795 | 24795 | 2025-09-20 | 2025-10-18
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5814805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128617613 | Approved | 24795 | 0 | 2025-02-14
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5814806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128618121 | Completed | 24795 | 24795 | 2026-01-31 | 2026-03-31
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5815003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106883499 | Completed | 24795 | 24795 | 2025-09-20 | 2025-10-12
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5815140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127943186 | Completed | 24795 | 24795 | 2025-11-15 | 2026-01-24
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5815141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127944158 | Completed | 24795 | 24795 | 2025-09-20 | 2025-10-18
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5815514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127445214 | Completed | 24795 | 24795 | 2025-09-20 | 2025-10-18
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5815785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127939288 | Completed | 24795 | 24795 | 2025-09-20 | 2025-10-18
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5936213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146393078 | Ongoing | 24795 | 12006 | 2026-03-12
MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5936214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146396126 | Ongoing | 24795 | 2349 | 2026-05-30
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5941233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145067197 | Ongoing | 24795 | 7830 | 2026-03-12
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5941464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145246413 | Completed | 24795 | 24795 | 2026-03-14 | 2026-06-19
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/76270 — Construction of IAY House -IAY REG. NO. MP-36-007-011-001/01 | Completed | 15105 | 15030 | 2016-12-03 | 2017-03-25
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/913885 — Construction of IAY House -IAY REG. NO. MP2331110 | Completed | 16340 | 15480 | 2017-05-27 | 2018-02-01
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/920221 — Construction of IAY House -IAY REG. NO. MP2424008 | Completed | 16340 | 15136 | 2017-06-24 | 2017-12-15
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/920237 — Construction of IAY House -IAY REG. NO. MP2424190 | Completed | 16340 | 14964 | 2017-07-01 | 2018-02-01
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/947931 — Construction of IAY House -IAY REG. NO. MP2993031 | Completed | 16340 | 15136 | 2017-07-01 | 2017-12-01
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/982541 — Construction of IAY House -IAY REG. NO. MP3981773 | Completed | 16340 | 15480 | 2017-05-27 | 2018-02-01
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/982843 — Construction of IAY House -IAY REG. NO. MP3994675 | Completed | 18050 | 18335 | 2021-05-30 | 2021-09-03
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007011/LD/1435 — मेढ बंधान कार्य अनकलाल/अमरलाल | Completed | 60000 | 52386 | 2011-08-12 | 2012-12-30
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007011/LD/1436 — मेढ बंधान कार्य अन्‍तराम/चौखे | Completed | 43000 | 32405 | 2011-08-18 | 2012-12-30
MOHKHED | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007011/LD/1662 — खेल मैदान मा0शा0 पौनार | Completed | 499000 | 405275.45 | 2012-12-08 | 2014-03-13
MOHKHED | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007011/LD/1663 — मेढ बंधान कार्य हुन्‍नीलाल/मुल्‍लू | Completed | 43000 | 43361 | 2012-12-08 | 2012-12-30
MOHKHED | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007011/LD/1777 — मेढ बंधान कार्य रेखा/रामलयाल | Completed | 70000 | 40656 | 2013-01-19 | 2013-03-27
MOHKHED | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007011/LD/1778 — मेढ बंधान कार्य रामदास/फग्‍गु | Completed | 75000 | 41316 | 2013-02-09 | 2013-03-31
MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1736007011/LD/22012034295200 — SHANTIDHAM POUNAR DHANA | Deleted | 180000 | 0 | 2016-12-31
MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/22012034182567 — द्वितीय श्रेणी रोड बेनी के खेत से सिंगराज देव कि त | Completed | 498000 | 364581.09 | 2013-09-14 | 2014-03-28
MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034184370 — C.C.Road from house of Nanhi Baie towards Sosaiety | Completed | 122600 | 118502 | 2013-09-23 | 2014-01-18
MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034184371 — C.C. Road from house of Munnalal towards house of | Completed | 63900 | 63014 | 2013-09-21 | 2014-01-20
MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/22012034185402 — ROAD FROM SINGRAJ DEO TOWARDS TEKADI POUNAR | Completed | 484000 | 348260.15 | 2013-09-28 | 2016-08-09
MOHKHED | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034218600 — C.C.ROAD JHIRPAL TO CALONI POUANR DHANA | Completed | 120000 | 113923 | 2014-06-21 | 2014-09-19
MOHKHED | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/22012034219217 — SUDOOR SADAK FIFLD OF RAMDAS TO DAYARAM DHANA | Deleted | 1495000 | 0 | 2014-04-24
MOHKHED | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/22012034219219 — KHET SADAK (MAIN ROAD P[OUNAR TO FIELD O SHIVLAL)O | Deleted | 1598000 | 0 | 2014-04-24
MOHKHED | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007011/RC/22012034285018 — SUDOOR ROAD RAMDAS KE KHET SE DYARAM DHANA | Completed | 1090000 | 1056161.83 | 2015-10-17 | 2020-05-25
MOHKHED | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007011/RC/22012034301770 — Sudor Sadak Yojna- Ramdas ke khet se Dayaram Dhana tak | Deleted | 0 | 0 | 2015-10-30
MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034327325 — C C ROAD SAKHRAM KE GHAR KE SE SUKHRAM KUMARE KE GHAR TAK | Completed | 137000 | 130382 | 2017-03-18 | 2017-12-23
MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034329541 — CC ROAD WITH NALI GUDI KE GHAR SE FATYAB KE GHAR TAK | Deleted | 35000 | 0 | 2017-03-04
MOHKHED | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034398138 — C C ROAD PRAHLAD KE GHAR SE RADHESHYAM KE GHAR OR | Completed | 101000 | 100998 | 2018-10-13 | 2019-06-19
MOHKHED | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034470921 — C.C.ROAD INDAR KE GHAR SE RAMA KE GHAR TAK | Completed | 76000 | 76451 | 2019-09-28 | 2020-02-10
MOHKHED | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034503464 — C C ROAD GUDDI BAI KE GHAR SE FATIYAB KE GHAR TAK | Completed | 57375 | 57005 | 2019-12-28 | 2020-05-04
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034517921 — PULIYA NIRMAN KARYA BHAIRAPUR ROAD POUNAR | Completed | 154000 | 153440 | 2020-05-02 | 2020-08-05
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007011/RC/22012034556173 — PULIYA NIRMAN KARY - NISATARI TALAB KE PASS CHHOTI NADI TIGAI ROAD | Closed | 0 | 0 | 2020-10-02
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034567115 — C C ROAD MUNNA GADEWAL KE GHAR SE GANPAT CHOURIYA KE GHAR TAK | Completed | 41400 | 40904 | 2021-08-21 | 2021-11-23
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034579794 — C C ROAD POUNAR DHANA SCHOOL SE BHOLE KHA KE GHAR KI OR | Deleted | 0 | 0 | 2021-04-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034579795 — C C ROAD POUNAR DHANA SCHOOL SE BHOLE KHA KE GHAR KI OR | Deleted | 0 | 0 | 2021-04-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034579796 — C C ROAD POUNAR DHANA SCHOOL SE BHOLE KHA KE GHAR KI OR | Deleted | 0 | 0 | 2021-04-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034579798 — C C ROAD POUNAR DHANA SCHOOL SE BHOLE KHA KE GHAR KI OR | Deleted | 0 | 0 | 2021-04-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034579799 — C C ROAD POUNAR DHANA SCHOOL SE BHOLE KHA KE GHAR KI OR | Deleted | 0 | 0 | 2021-04-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034579800 — C C ROAD POUNAR DHANA SCHOOL SE BHOLE KHA KE GHAR KI OR | Completed | 45900 | 45600 | 2021-10-02 | 2021-11-07
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034591110 — C C ROAD POUNAR MAIN ROAD SE M.SCHOOL TAK | Completed | 63000 | 57760 | 2021-11-01 | 2021-12-23
MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034619018 — NALI NIRMAN KARY JUGAL KE GHAR SE RAJKUMAR KE GHAR TAK | Completed | 87300 | 87030 | 2022-11-08 | 2022-12-19
MOHKHED | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034819420 — सी. सी. सड़क मलखे के घर से मोहन विश्वकर्मा के घर तक | Completed | 53000 | 51642 | 2025-02-01 | 2025-06-28
MOHKHED | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/22012034851560 — CC ROAD NIRMAN SANIF KHAN KE MAKAN SE KAMLESH NARVARE KE GHAR KI OR | Completed | 48000 | 47998.22 | 2025-12-29 | 2026-02-05
MOHKHED | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/8990 — 2 श्रेणीरोड निर्माण कार्य पौनार से करलाकला भाग 2 | Completed | 192000 | 408389 | 2008-12-06 | 2011-08-03
MOHKHED | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/9160 — दितीय सडक निर्माण कार्य पौनार से सिंगराज करलाकला भाग-1 | Completed | 499000 | 454666 | 2011-02-05 | 2012-07-17
MOHKHED | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007011/RC/9318 — पच परमेश्‍वर सी सी रोड निर्माण कार्य पौनार | Completed | 170000 | 108588 | 2012-10-27 | 2013-10-03
MOHKHED | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/पाैनार से पटनिया/12 — ग्रेवल मार्ग/पौनार से पटनिया | Completed | 360000 | 386467.96 | 2008-01-27 | 2012-07-17
MOHKHED | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007011/RC/पौनार001 — द्वितीय श्रेणी सडक निर्माण पैनार से करलाकला | Completed | 480000 | 299271 | 2008-06-12 | 2010-11-10
MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736007011/RS/22012035118271 — RCC DRAIN NIRMAN KARY NARAYAN CHOUHAN KE GHAR SE BHOLARAM SAHU KE GHAR TAK | Completed | 58000 | 57990 | 2023-10-14 | 2024-06-18
MOHKHED | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736007011/RS/22012035126440 — RCC Nali Nirman Kary Akikrat Vidhyal Se Panchayat Bhavan Tak | Completed | 60000 | 60000 | 2024-06-22 | 2025-04-28
MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736007011/RS/22012035126441 — RCC Nali Nirman Kary Akikrat Vidhyal Se Panchayat Bhavan Tak | Deleted | 0 | 0 | 2024-01-24
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/WC/22012034317304 — NISTARI TALAB TIGAI ROAD | Deleted | 0 | 0 | 2017-01-26
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/WC/22012034317309 — NIRMAL NEER PANCHAYAT BHAVAN KE PASS | Deleted | 0 | 0 | 2017-01-26
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/WC/22012034326977 — TALAB NIRMAN PANCHAYAT BHAVAN KE PICHE | Completed | 1116000 | 1096628.27 | 2017-05-27 | 2020-06-11
MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736007011/WC/22012034701507 — वाटर हार्वेस्टिंग - एकीकृत विद्यालय पौनार | Completed | 40012.04 | 38897 | 2024-09-14 | 2025-10-16
MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007011/WC/22012034701520 — शोक पिट - हैंडपंप पंचायत भवन के पास | Completed | 10835.21 | 10564.57 | 2022-04-30 | 2023-03-15
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007011/WC/22012034786904 — शोक पिट - हैंडपंप पौनार ढाना स्कूल के सामने | Deleted | 0 | 0 | 2021-05-27
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007011/WC/22012034786907 — शोक पिट - हैंडपंप पौनार ढाना स्कूल के सामने | Closed | 17057.23 | 0 | 2021-05-27
MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007011/WC/22012034786910 — शोक पिट - हैंडपंप बदनूर रोड | Closed | 16966.36 | 0 | 2021-01-27
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007011/WC/22012034809538 — Shok Pit Nirmal Neer Kup Shanti Dham Ke Pass | Closed | 0 | 0 | 2021-08-15
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007011/WC/22012034903488 — CTR-NALA SURESH KE KHET SE POUNAR DHANA PULIYA TAK | Closed | 0 | 0 | 2022-01-24
MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1736007011/WC/22012034921211 — Maa Ki Bagiya M. School Pounar | Completed | 9809.53 | 4342 | 2022-07-23 | 2022-12-10
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1736007011/WC/22012034921212 — Maa Ki Bagiya M. School Pounar | Deleted | 0 | 0 | 2022-01-24
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1736007011/WC/22012034921214 — Maa Ki Bagiya M. School Pounar | Deleted | 0 | 0 | 2022-01-24
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1736007011/WC/22012034921215 — Maa Ki Bagiya M. School Pounar | Deleted | 0 | 0 | 2022-01-24
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1736007011/WC/22012034922296 — Maa Ki Bagiya PS Pounar Dhana | Closed | 9552.51 | 0 | 2022-01-24
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1736007011/WC/22012034922297 — Maa Ki Bagiya PS Pounar Dhana | Deleted | 0 | 0 | 2022-01-24
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007011/WC/22012034940026 — CTR/TS/10 Box Treanch Golahari | Closed | 66125.68 | 0 | 2022-03-21
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007011/WC/22012034946807 — चैक डेम निर्माण कार्य बड़ी नदी पर | Deleted | 0 | 0 | 2022-03-21
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007011/WC/22012034947090 — चैक डेम निर्माण कार्य छोटा नाला स्टेम के पास | Closed | 0 | 0 | 2022-03-21
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007011/WC/22012034947092 — चैक डेम निर्माण कार्य छोटा नाला स्टेम के पास | Deleted | 397665.88 | 0 | 2022-03-21
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1736007011/WC/22012035079702 — BOLDER BANDHAN NAMDEV KE KHET KE PASS | Closed | 0 | 0 | 2023-04-14
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1736007011/WC/22012035079711 — NALA GAHARIKARAN NAMDEV KE KHET KE PASS | Completed | 169688.05 | 166623.15 | 2023-09-16 | 2024-10-11
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1736007011/WC/22012035080227 — Gabiyan Struture Nirman Kary Namdev Ke Khet Ke Pass Pounar | Closed | 354187.63 | 0 | 2023-04-14
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007011/WC/22012035170760 — कन्टूरट्रेच निर्माण कार्य | New | 0 | 0 | 2023-10-02
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736007011/WC/22012035220586 — Parcolation tank at Manohar ke Ghar ke Pass Pataniya Road | Physically Completed | 498407.05 | 386708.32 | 2025-04-19 | 2026-06-29
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007011/WC/22012035269025 — Dugwell Recharge Pit Nirmal Neer Vard No 12 Ke Pass Pounar | Physically Completed | 25899.46 | 24870.32 | 2025-05-15 | 2026-01-21
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007011/WC/22012035269038 — Dugwell Recharge Pit Nirman Shantidham Ke Pass Pounar | Physically Completed | 25899.46 | 25650.32 | 2025-04-29 | 2026-01-21
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007011/WC/8250 — नीर्मल नीर झिरपाल के तरफ ग्राम पंचायत पौनार | Completed | 378000 | 212127.26 | 2010-05-01 | 2014-02-15
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736007011/WH/22012034456103 — Stap Dam Jirnooudhar Santosh Choure Ke Khet Ke Pass Kundi Nadi Pounar | Completed | 257835.29 | 181904.77 | 2022-02-19 | 2022-12-10