## Work List
Exported on: 2026-09-30 09:52:20
Filters applied:
Data source: MGNREGA
District: CHHINDWARA
Block: All
Panchayat: BHANDKHAPA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MOHKHED | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007030/AV/22012034375026 — ANGANWADI BHAWAN NIRMAN BHANDKHAPA | Closed | 312000 | 0 | 2017-10-02
MOHKHED | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007030/AV/22012034376324 — Anganwadi Bhawn Construction, Bhandkhapa | Completed | 312000 | 314264 | 2018-10-19 | 2021-01-05
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736007030/AV/22012034582557 — डायनिंग हॉल निर्माण हाई स्कूल भांड खापा | Closed | 47521.74 | 0 | 2021-01-26
MOHKHED | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007030/DP/22012034436157 — Nirmal Neer Koop Nirman Bhandkhapa | Completed | 445000 | 393389.85 | 2019-03-10 | 2020-06-25
MOHKHED | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007030/DP/22012034447057 — CONTOUR TRENCH BHANDKHAPA | Completed | 456354.51 | 408568 | 2020-02-07 | 2021-01-26
MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007030/DP/22012034521466 — Contur Tranch Aahirdev Pahadi | Completed | 601175.58 | 531582 | 2021-01-15 | 2021-09-25
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007030/DP/22012034530213 — CONTOURETRENCH NIRMAN KARYA DUNDASEONI | Completed | 1204069.43 | 1051058 | 2021-12-03 | 2026-04-25
MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1736007030/DP/22012034530751 — वृक्षारोपन कार्य शांति धाम मे | Closed | 394489.84 | 0 | 2021-01-26
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1736007030/DP/22012034603952 — अमृत वाटिका पंचायत परिसर | Closed | 55847.4 | 0 | 2023-04-14
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1736007030/DP/22012034610908 — Conture trench Nirman karya (jhandol pahdi Dundaseoni ) | Completed | 520167.85 | 235295.92 | 2023-11-03 | 2026-06-02
MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736007030/DP/22012034621630 — SHANTIDHAM ME VRAKSHAROPAN KARYA BHANDKHAPA | Ongoing | 457741.17 | 17961.5 | 2024-07-12
MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1736007030/DP/22012034621638 — BLOCK PLATATION KARYA AHIRDEV PAHADI BHANDKHAPA | Ongoing | 829925.21 | 75385.26 | 2024-07-12
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007030/DP/45874 — शांतीवन शमशान घाट व्रक्षारोपण कार्य प्रथम वर्ष ग्राम पंचायत भांड़खापा | Completed | 188000 | 114596.98 | 2010-04-24 | 2012-08-25
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007030/DP/45937 — व्रक्षारोपण कार्य भाण्‍डखापा | Completed | 342000 | 40853 | 2010-07-10 | 2010-08-05
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007030/DP/45938 — व्रक्षारोपण कार्य भांडखापा डूंडा सिवनी | Completed | 342000 | 44300 | 2010-07-22 | 2010-08-05
MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007030/IF/22012034319585 — varmi compost nirmaan | Closed | 0 | 0 | 2017-01-26
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007030/IF/22012034326516 — कपिलधारा कुप सह खेत तालाब निर्माण रामशीला / सेवक | Completed | 200000 | 190516 | 2017-05-19 | 2018-07-31
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034343213 — Plantation RSP -वृक्षारोपन सडक किनारे पंचायत भवन से नाले तक | Completed | 335000 | 117669 | 2017-06-02 | 2020-09-19
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034343247 — Plantation PCP - वृक्षारोपण स्कूल खेल मैदान भांडखापा | Completed | 335000 | 157287 | 2017-06-02 | 2020-09-19
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007030/IF/22012034385198 — kapildhara bhandkhapa | Closed | 0 | 0 | 2017-11-01
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007030/IF/22012034385200 — kapildhara bhandkhapa | Closed | 0 | 0 | 2017-11-01
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034385201 — Plantation bhandkhapa | Closed | 0 | 0 | 2017-11-01
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034579421 — Naino Archit(tilko/gopal) | Completed | 58200 | 31985.5 | 2020-07-18 | 2026-06-01
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034579437 — Naino Archit (dulari/harchandra) | Physically Completed | 58200 | 24242.5 | 2020-07-18 | 2026-06-10
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034579453 — Naino Archit (siyakali/goverdhan) | Completed | 58200 | 24275.5 | 2020-07-18 | 2026-02-16
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034579537 — Naino Archit (archna/rajesh) | Completed | 58200 | 26037.5 | 2020-07-18 | 2026-02-05
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034579544 — Naino Archit (Ramshila/sewak) | Completed | 58200 | 23577.5 | 2020-07-18 | 2026-02-16
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034581054 — Naino Archit (Sipti/Bhura) | Completed | 58200 | 30895.5 | 2020-07-24 | 2026-02-05
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034581060 — Naino Archit (Ramola/Munsiram) | Completed | 58200 | 18237.5 | 2020-07-24 | 2026-02-17
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034581071 — Naino Archit(Geeta/Narayan) | Completed | 58200 | 29167.5 | 2020-07-24 | 2026-02-17
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012034581589 — Naino Archit (rampa/laxman) | Completed | 58200 | 21162.5 | 2020-07-24 | 2026-02-17
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007030/IF/22012035497277 — Khet Talab Nirman Karya siyakali W/O Naresh Uikey Dundaseoni Bhandkhapa | New | 0 | 0 | 2025-04-15
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007030/IF/22012035497533 — Khet Talab Nirman Karya Siyakali W/O Naresh Dundaseoni Bhandkhapa | Physically Completed | 55865.38 | 39625.87 | 2025-05-15 | 2026-04-15
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007030/IF/22012035605014 — Ek Bagiya Maa Ke Namm Mamta Ratne MP 36 007 030 001 1214 | Ongoing | 266577.25 | 162343.17 | 2025-09-07
MOHKHED | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007030/IF/9993648889 — MAVESHI SHEAD JHEENI RAMCHARAN | Completed | 99000 | 98635.02 | 2014-08-08 | 2015-10-14
MOHKHED | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007030/IF/9993652665 — Maveshi Shed Nirman - Rambharosh s/o Bhadu | Deleted | 99000 | 0 | 2014-09-05
MOHKHED | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007030/IF/9993652669 — Maveshi Shed Nirman Gopal s/o boodan | Deleted | 1845180445 | 0 | 2014-04-26
MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/108414 — Construction of IAY House -IAY REG. NO. MP-36-007-030-002/01 | Completed | 15105 | 15324 | 2016-11-18 | 2019-01-07
MOHKHED | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/2098726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4111341 | Completed | 16720 | 16530 | 2019-08-02 | 2020-07-02
MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/2553703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5641248 | Completed | 18050 | 16102 | 2020-05-15 | 2021-01-05
MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/2707356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5524071 | Completed | 18050 | 6562 | 2021-09-11 | 2021-12-13
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/4065993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115120902 | Completed | 19380 | 18360 | 2022-06-03 | 2022-10-04
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/4202983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142221326 | Completed | 19380 | 18768 | 2023-01-30 | 2023-08-25
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/4303328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120578966 | Completed | 19380 | 18564 | 2022-10-01 | 2023-08-25
MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/4303333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120582265 | Completed | 19380 | 19176 | 2023-01-30 | 2023-08-25
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/4711505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126518725 | Completed | 24795 | 23175 | 2025-01-10 | 2026-03-20
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/4774818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125805445 | Completed | 24795 | 22356 | 2025-01-10 | 2026-03-20
MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/4856650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126731355 | Completed | 24795 | 23139 | 2025-01-10 | 2026-03-17
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/527904 — Construction of IAY House -IAY REG. NO. MP2750853 | Completed | 15865 | 14028 | 2017-05-05 | 2017-10-05
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5332873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120578022 | Completed | 24795 | 21792 | 2025-05-23 | 2026-03-20
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/538489 — Construction of IAY House -IAY REG. NO. MP3030604 | Completed | 15865 | 15560 | 2017-05-05 | 2018-10-14
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5387920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115121504 | Completed | 24795 | 24609 | 2025-05-23 | 2026-03-17
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5397474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125811263 | Completed | 24795 | 24609 | 2025-05-23 | 2026-03-17
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5467317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120576297 | Completed | 24795 | 24657 | 2025-05-23 | 2026-03-17
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5467318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120580291 | Completed | 24795 | 24615 | 2025-05-23 | 2026-03-17
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5472226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125822150 | Completed | 24795 | 23067 | 2025-05-23 | 2026-04-12
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5603359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120579648 | Physically Completed | 24795 | 24663 | 2025-05-23 | 2026-06-14
MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/5603997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115121434 | Physically Completed | 24795 | 23352 | 2025-05-23 | 2026-03-15
MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007030/IF/IAY/910205 — Construction of IAY House -IAY REG. NO. MP2279008 | Completed | 16340 | 14796 | 2018-02-16 | 2018-09-19
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1105 — मेढ्र बधान कार्य भादू गनाराम | Deleted | 24000 | 0 | 2010-04-15
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1106 — मेढ बंधान कार्य प्रहलाद गणाराम | Deleted | 24000 | 0 | 2010-04-12
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1107 — मेढ्र बंधान कार्य श्रीपाल/रमेश | Deleted | 24000 | 0 | 2010-04-12
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1108 — मेढ बंधान कार्य नारायण/मुशीलाल | Deleted | 24000 | 0 | 2010-04-12
MOHKHED | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1109 — मेढं बंधान कार्य मीरा/नारायण | Deleted | 24000 | 0 | 2010-04-12
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1136 — मेढ बंधान कार्य भादु/गनाराम | Completed | 40000 | 23956 | 2011-04-01 | 2011-05-07
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1137 — मेढ बंधान कार्य प्रहलाद/गणाराम | Completed | 40000 | 23816 | 2011-04-08 | 2011-05-19
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1138 — मेढ बंधान कार्य श्रीपाल/रमेश | Completed | 40000 | 17046 | 2011-04-01 | 2011-06-06
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1139 — मेढ बंधान कार्य नारायण/मुंशीलाल | Completed | 40000 | 22033 | 2011-04-01 | 2011-05-06
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1140 — मेढ बंधान कार्य मीरा/नारायण | Completed | 40000 | 23830 | 2011-04-08 | 2011-06-26
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1141 — मेढ बंधान कार्य नेपाल/नारायण | Completed | 40000 | 23524 | 2011-05-13 | 2011-06-02
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1165 — मेढ बंधान कार्य पुसिया/झब्‍बू | Completed | 40000 | 24072 | 2011-05-06 | 2011-05-18
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1166 — मेढ बंधान कार्य तुलाराम/अनोख | Completed | 40000 | 23424 | 2011-04-01 | 2011-04-06
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1167 — मेढ बंधान कार्य देवकरण/गणाराम | Completed | 40000 | 23520 | 2011-06-06 | 2011-06-26
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1168 — मेढ बंधान कार्य गोपीचंद/गेन्‍दू | Completed | 40000 | 12840 | 2011-04-22 | 2011-05-11
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1239 — मेड बधान कार्य सुखदयाल /लेखमन | Completed | 40000 | 23760 | 2011-06-01 | 2011-06-20
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1240 — मेड बधान कार्य रामजी /बसंता | Completed | 40000 | 23748 | 2011-06-10 | 2011-06-22
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1241 — मेड बधान कार्य सुब्‍बो गनाराम | Completed | 40000 | 23880 | 2011-05-23 | 2011-06-11
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/1247 — मेड बधान काय्या गोवधन/गेन्दू | Completed | 40000 | 23180 | 2011-06-24 | 2011-07-01
MOHKHED | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007030/LD/22012034258701 — Shamshan Ghat Shed | Deleted | 0 | 0 | 2015-10-30
MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1736007030/LD/22012034293668 — शांतीधाम निर्माण कार्य भाण्डखापा | Completed | 180000 | 181455.71 | 2016-12-02 | 2018-09-19
MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1736007030/LD/22012034941822 — Contoure trench nirman karya dundaseoni 2 | Physically Completed | 582146.8 | 244100.01 | 2024-12-20 | 2026-06-28
MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1736007030/PG/9425895159 — Khel Maidan PS and MS School Bhandkhapa | Completed | 186000 | 81536.02 | 2017-03-24 | 2018-09-21
MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034210644 — CC Road Nirman Budhman ke ghar se Dhannu ke ghar T | Completed | 157000 | 134662 | 2014-03-14 | 2015-01-15
MOHKHED | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007030/RC/22012034218806 — Sudur Sadak Nirman(Galichand Ke Khet Se Mandru Ke | Completed | 757000 | 571603.94 | 2014-05-23 | 2020-06-25
MOHKHED | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034227549 — P.P.C,C Road Bhandklhap se SamShan Ghat Tak | Completed | 173000 | 144344 | 2014-09-12 | 2015-01-15
MOHKHED | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034229295 — P.P.C.C Road Ghurkha Ke Ghar Se Sankh Road Tak | Completed | 67400 | 61098 | 2014-09-19 | 2015-01-15
MOHKHED | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007030/RC/22012034290195 — KHET SADAK PANI TANKI SE AMADIGHAT TAK | Completed | 1480000 | 146376 | 2015-11-27 | 2017-01-31
MOHKHED | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007030/RC/22012034302597 — Khet Sadak Yonja - Shamshan Ghat to Kharighat tak | Deleted | 0 | 0 | 2015-10-30
MOHKHED | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034483285 — CC ROAD NIRMAN CC ROAD SE MOKSHADHAM TAK | Completed | 69150 | 71860 | 2019-10-28 | 2020-07-02
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034535728 — CC ROAD NIRMAN BHAULAL KE GHAR TAK | Completed | 33120 | 13680 | 2020-09-11 | 2021-01-05
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034563226 — PULIYA NIRMAN KARYA DEVBABA NALE PAR | Closed | 0 | 0 | 2021-01-26
MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007030/RC/22012034563227 — puliya nirman karya devbaba nale par | Closed | 0 | 0 | 2021-01-26
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034578996 — CC ROAD NIRMAN HS SCHOOL BULDING SE GYANDAS KE MAKAN TAK | Closed | 106000 | 0 | 2021-07-01
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034579002 — RCC NALI NIRMAN REVARAM KE MAKAN SE SUSHIL KE MAKAN TAK | Completed | 50300 | 26634 | 2021-08-13 | 2023-02-04
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034605899 — सी सी सड़क निर्माण हाई स्कूल से ज्ञानदास के मकान तक | Deleted | 0 | 0 | 2021-10-02
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/22012034605900 — सी सी सड़क निर्माण हाई स्कूल से ज्ञानदास के मकान तक | Completed | 106000 | 101228 | 2022-02-18 | 2024-08-22
MOHKHED | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736007030/RC/22012034681693 — पुलिया निर्माण कार्य (देवबाबा रोड पर भांडखापा ) | Physically Completed | 1424656.2 | 1231560.54 | 2024-05-10 | 2026-06-01
MOHKHED | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007030/RC/786/120 — दितीय श्रेणी मार्ग भाण्‍डरपाप से वेन्‍दाघोती | Completed | 494000 | 221396 | 2007-05-11 | 2011-04-30
MOHKHED | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007030/RC/9069 — द्वितीय श्रेणी मार्ग भाड़खापा से कुकड़ा किरार स्‍टाप डेम ग्राम पंचायत भाड़ंखापा | Completed | 498000 | 29211 | 2010-05-18 | 2010-05-31
MOHKHED | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007030/RC/9186 — सडंक निर्माण चोपनटोला से रघुवीर के खेत तक | Completed | 498000 | 434730.92 | 2011-07-24 | 2015-01-15
MOHKHED | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007030/RC/9234 — सीसी रोड निर्माण कार्य शिव मंदिर से संतोष पटेल के | Completed | 321000 | 124080 | 2012-07-20 | 2013-10-20
MOHKHED | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007030/RC/9298 — द्वितीय श्रेणी सडक निर्माण कार्य सी सी रोड भाडखापा | Completed | 499000 | 448481.6 | 2013-02-08 | 2015-01-15
MOHKHED | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007030/RC/भाण्‍डाखापा/2543 — भाण्‍डाखापा से लेन्‍दाघोन्‍दी 2 श्रेणी मार्ग | Deleted | 0 | 0 | 2007-06-20
MOHKHED | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007030/RC/भाण्‍डाखापा/2543/1 — भाण्‍डाखापा से लेन्‍दाघोन्‍दी 2 श्रेणी मार्ग | Completed | 488000 | 267200 | 2007-08-24 | 2011-04-10
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Vermi Compost structure for Groups / Construction of Vermi Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1736007030/RS/22012034608509 — VERMI COMPOST NIRMAN DUNDASEONI 1 | Completed | 24107.01 | 9081.95 | 2022-03-20 | 2024-08-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1736007030/RS/22012034608517 — VERMI COMPOST NIRMAN DUNDASEONI 2 | Completed | 24107.01 | 9044.7 | 2022-03-18 | 2024-08-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1736007030/RS/22012034608526 — NADEP COMPOST NIRMAN KARYA DUNDFASEONI 2(RANGMANCH KE PASS) | Completed | 14006.51 | 9726.15 | 2022-03-18 | 2024-08-28
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1736007030/RS/22012034608529 — NADEP COMPOST NIRMAN DUNDASEONI (MUNSIRAM KE GHAR KE PASS) | Completed | 14006.51 | 9147.95 | 2022-03-18 | 2024-08-28
MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1736007030/RS/70195 — nali nirman from shiv mandir towards house of san | Deleted | 187000 | 0 | 2013-10-04
MOHKHED | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736007030/WC/22012034435783 — Nirmal Neer | Closed | 0 | 0 | 2018-10-02
MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736007030/WC/22012034921171 — Maa ki Bagiya (Govt.High School Bhandkhapa) | Closed | 8002.93 | 0 | 2022-03-03
MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007030/WC/22012035161388 — कन्टूरट्रेंच निर्माण कार्य | New | 0 | 0 | 2023-10-02
MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1736007030/WC/22012035179311 — NIRMAL NEER KOOP NIRMAN KARYA SHANTI DHAM BHANDKHAPA | Ongoing | 537251.35 | 243565.37 | 2024-05-10
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007030/WC/22012035273074 — DUG WELL RECHARGE PIT STRUCTURE NEERMAL NEER DEVBABA | Physically Completed | 25899.46 | 18920.44 | 2025-05-17 | 2026-03-17
MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007030/WC/22012035273126 — DUG WELL RECHARGE PIT STRUCTURE SARKARI KOOP BANTI KE KHET KE PASS | Physically Completed | 25899.46 | 22071.31 | 2025-05-17 | 2026-03-17
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/7919 — कपिल धारा कली झामसा भाण्‍डा | Deleted | 73000 | 0 | 2008-03-12
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8083 — कपिल धारा कूप निर्माण भादू / गनाराम | Deleted | 0 | 0 | 2008-01-26
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8084 — कूप निर्माण कार्य सुखदयाल/लोकमन | Deleted | 0 | 0 | 2008-01-26
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8085 — कूप निर्माण कार्य सुखदयाल/लोकमन | Completed | 44400 | 130254.83 | 2009-01-30 | 2009-07-11
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8086 — कपिल धारा कूप निर्माण भादू / गनाराम | Completed | 44400 | 166855.46 | 2009-02-19 | 2010-05-28
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8087 — कूप निर्माण कार्य मकरन/अनोखलाल | Completed | 44400 | 111510.48 | 2009-03-01 | 2009-07-18
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8088 — कपिल धारा कूप निर्माण मीराबाई / नारामण | Completed | 44400 | 114312 | 2009-02-16 | 2009-07-24
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8089 — कपिल धारा कूप निर्माण श्‍यामलाल / पाण्‍डू | Completed | 44400 | 102044.2 | 2008-12-29 | 2009-07-18
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8090 — कपिल धारा कूप निर्माण रमेश / पन्‍नालाल | Completed | 44400 | 93329 | 2009-01-15 | 2009-06-22
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8091 — सार्वजनिक कूप निर्माण कार्य | Completed | 44400 | 280436.18 | 2009-03-02 | 2011-02-05
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736007030/WC/8470 — कपिलधारा कुप निर्माण संतराम/बुदन भाण्‍डखापा | Completed | 237000 | 115965.96 | 2012-01-12 | 2013-03-20
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736007030/WC/8471 — कपिलधारा कुप निर्माण रामभरोष/भादू डूडासिंवनी | Completed | 237000 | 178146.7 | 2012-02-01 | 2013-03-20
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/8472 — कपिलधारा कुप निर्माण पंचु/बुदन | Completed | 237000 | 209171.5 | 2012-01-20 | 2014-08-16
MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007030/WC/8473 — कपिलधारा कुप निर्माण कुवंरलाल/शिवचरण | Completed | 237000 | 133123.84 | 2012-01-27 | 2014-08-15
MOHKHED | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007030/WC/9993665477 — Nirmal Neer -Bhandkhapa | Completed | 394000 | 309791.7 | 2016-01-22 | 2018-07-31
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/गोवर्धन/गेंन्‍दु/डूडासिवनी/846 — कपिलधारा/गोवर्धन/गेंन्‍दु/डूडासिवनी | Completed | 111000 | 107447.18 | 2007-12-25 | 2009-08-02
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/नारायण/डुडासिवनी/159 — कपिलधारा:नारायण/डुडासिवनी | Completed | 111000 | 74548.8 | 2008-01-08 | 2009-05-30
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/भाडखापा/10/9 — कपिल धारा कूप निमार्ण(हरिचन्‍द व गेनू) | Deleted | 111000 | 0 | 2008-01-04
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/भाडखापा/10/96 — कपिल धारा कूप निमार्ण(श्रीपाल व रमेश) | Completed | 111000 | 34011.08 | 2008-01-01 | 2009-06-24
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/ भाडखापा 10/969 — कपिल धारा रामबत्‍ती / चौखे | Deleted | 111000 | 33156.61 | 2008-01-11
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/भॉडखापा bn546 — कपिल धारा कूप निर्माण प्रहलाद / गणाराम | Completed | 111000 | 26558 | 2007-12-17 | 2009-06-06
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/भॉंडखापा gh231 — कपिल धारा कूप निर्माण गोपचंद/ गेंदू | Completed | 111000 | 21478.25 | 2007-12-28 | 2009-06-15
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/सुब्‍बो गणा/भांडखापा/426 — कपिलधारा कूप/सुब्‍बो गणा/भांडखापा | Completed | 496000 | 221965.9 | 2008-05-19 | 2010-06-16
MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/हरिचंद गेंदू/भांडखापा/752 — कपिधारा कूप/हरिचंद गेंदू/भांडखापा | Completed | 111000 | 161705.05 | 2008-04-06 | 2009-06-13
MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007030/WC/हरिचन्‍द्र/गेंन्‍दु/डूडासिवनी/846 — कपिलधारा/हरिचन्‍द्र/गेंन्‍दु/डूडासिवनी | Deleted | 0 | 0 | 2007-10-25
MOHKHED | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1736007030/WH/19962911 — तालाब जीर्णदुर चोपन टोला | Completed | 444000 | 216134.66 | 2017-06-16 | 2018-12-04
MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034609119 — Periodical Regraveling Of CMGSY Road From Bisapur Road to Dunda Seoni | Completed | 942000 | 913970.85 | 2022-03-12 | 2023-02-08