## Work List
Exported on: 2026-10-19 10:16:55
Filters applied:
Data source: VBGRAMG
District: CHHINDWARA
Block: All
Panchayat: KACHARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Prduction of building material (Comm) / Production of Building Material for Community | Construction of Other Community Building/Assets | 1736008012/AV/22012034667504 — MOKCH DHAM NIRMAN KARYA SASKIYE KOOP KE PASS BIJORI KHURD GRAM PANCHYAT KACHARIYA | Approved | 237790.36 | 0 | 2025-08-17
CHHINDWARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1736008012/DP/22012034604407 — बसुधा वंदन ग्राम में 75 पौधा रोपण कार्य पंचायत भवन के पास कचरिया | Physically Completed | 55847.4 | 0 | 2023-10-06 | 2026-10-09
CHHINDWARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Medicinal Trees for Community | Plantation | 1736008012/DP/22012034622065 — ब्रक्चारोपन कार्य सेमर टोली भाग 1 कचरिया | Ongoing | 423739.89 | 6000 | 2024-07-09
CHHINDWARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Medicinal Trees for Community | Plantation | 1736008012/DP/22012034622459 — व्रछारोपण कार्य भजन कोटवार के खेत के पास बिजोरी खुर्द कचरिया | Ongoing | 423739.89 | 31500 | 2024-07-09
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5948723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141487208 | Physically Completed | 28500 | 7350 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5948725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141493320 | Physically Completed | 28500 | 13800 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5949213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148172869 | Physically Completed | 28500 | 6600 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5950390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149154351 | Ongoing | 28500 | 0 | 2026-07-07
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5950466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149168029 | Completed | 24795 | 0 | 2026-05-13 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146387082 | Physically Completed | 28500 | 7350 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146402818 | Physically Completed | 28500 | 9000 | 2026-05-25 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146419433 | Ongoing | 28500 | 0 | 2026-06-02
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113763089 | Ongoing | 28500 | 0 | 2026-06-02
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148323088 | Physically Completed | 28500 | 0 | 2026-06-02 | 2026-09-20
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148340500 | Physically Completed | 28500 | 7200 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105925441 | Physically Completed | 28500 | 13800 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105925458 | Physically Completed | 28500 | 0 | 2026-06-02 | 2026-10-06
CHHINDWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5951978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146967558 | Approved | 28500 | 0 | 2026-02-02
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5952517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145072114 | Physically Completed | 28500 | 9000 | 2026-06-02 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5953284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148683721 | Ongoing | 28500 | 12600 | 2026-06-07
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5953285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148818903 | Ongoing | 28500 | 0 | 2026-06-07
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5954072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141820344 | Physically Completed | 28500 | 7500 | 2026-06-05 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5954177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148838987 | Physically Completed | 28500 | 13800 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5954407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149129958 | Completed | 28500 | 9000 | 2026-06-10 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5954653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146462539 | Physically Completed | 28500 | 9000 | 2026-06-02 | 2026-09-20
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5955254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148846753 | Physically Completed | 28500 | 0 | 2026-05-13 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5955540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146407667 | Completed | 24795 | 0 | 2026-05-25 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5956256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141823715 | Physically Completed | 28500 | 0 | 2026-06-10 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5956257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141825180 | Completed | 28500 | 6900 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5956282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100904809 | Completed | 28500 | 9000 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5956601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145058421 | Physically Completed | 28500 | 0 | 2026-06-05 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5956602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145077135 | Physically Completed | 28500 | 0 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5957036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148192335 | Physically Completed | 28500 | 0 | 2026-06-07 | 2026-09-20
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5957410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141496542 | Physically Completed | 28500 | 0 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5957694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148691680 | Ongoing | 28500 | 0 | 2026-07-07
CHHINDWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5957810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148187997 | Approved | 28500 | 0 | 2026-02-02
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5959033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148506896 | Physically Completed | 28500 | 0 | 2026-06-10 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5959036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148510668 | Physically Completed | 28500 | 0 | 2026-06-10 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5959037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148512194 | Physically Completed | 28500 | 0 | 2026-06-10 | 2026-10-06
CHHINDWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5959039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148527081 | Approved | 28500 | 0 | 2026-02-04
CHHINDWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5959323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146398269 | Approved | 28500 | 0 | 2026-02-02
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5959331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145064038 | Physically Completed | 28500 | 6600 | 2026-06-10 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5961445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146396047 | Physically Completed | 28500 | 0 | 2026-06-04 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5961608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148148173 | Completed | 24795 | 0 | 2026-05-25 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5961873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148547362 | Ongoing | 28500 | 7200 | 2026-06-07
CHHINDWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5962206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148531826 | Approved | 28500 | 0 | 2026-02-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5962944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146986354 | Physically Completed | 28500 | 0 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5963277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149135685 | Physically Completed | 24795 | 2850 | 2026-06-07 | 2026-08-16
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5963595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148842353 | Completed | 28500 | 7800 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5963596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148844329 | Physically Completed | 28500 | 13800 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5966287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149170516 | Completed | 28500 | 0 | 2026-05-25 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5966621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148501216 | Completed | 28500 | 18000 | 2026-06-02 | 2026-10-06
CHHINDWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5966655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146979999 | Approved | 28500 | 0 | 2026-02-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/5966656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141483481 | Completed | 28500 | 6000 | 2026-06-07 | 2026-10-06
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6277177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149176717 | Ongoing | 28500 | 0 | 2026-10-10
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6277613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148837349 | Ongoing | 28500 | 0 | 2026-10-10
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6281746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146846357 | Ongoing | 28500 | 0 | 2026-10-10
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6283540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142120490 | Ongoing | 28500 | 0 | 2026-10-10
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6343910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148521889 | Approved | 28500 | 0 | 2026-06-20
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6355385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148561974 | Approved | 28500 | 0 | 2026-06-25
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6360372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148524893 | Ongoing | 28500 | 0 | 2026-10-14
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6361779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148304956 | Ongoing | 28500 | 0 | 2026-10-14
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6362090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146428024 | Ongoing | 28500 | 0 | 2026-10-14
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6362876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148502818 | Ongoing | 28500 | 0 | 2026-10-14
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6362958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146411476 | Ongoing | 28500 | 0 | 2026-10-14
CHHINDWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6377925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148144925 | Approved | 28500 | 0 | 2026-03-10
CHHINDWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736008012/IF/IAY/6378207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142123073 | Ongoing | 28500 | 0 | 2026-10-10
CHHINDWARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736008012/WC/VB/22012035330295 — Construction of contour trench karya anil khet ke pass kachariya | Ongoing | 199508.48 | 1005 | 2026-08-03
CHHINDWARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736008012/WC/VB/22012035330358 — Construction of contour trench karya bhvan khet ke pass bijori khurd | Approved | 0 | 0 | 2026-04-14