## Work List
Exported on: 2026-09-11 10:17:10
Filters applied:
Data source: VBGRAMG
District: CHHINDWARA
Block: All
Panchayat: BAIRAGAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SAUSAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1736009026/AV/22012034664311 — SHANTIDHAM NIRMAN KARY NALE KE PAAS | New | 0 | 0 | 2025-01-26
SAUSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1736009026/IF/22012034687959 — Medh bandhan nirman karya dhanraj ledange bairagad | Ongoing | 61708.69 | 0 | 2021-04-22
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Bio-gas plant for individual | Bio-gas plant | 1736009026/IF/22012035238154 — nandan phalodhyan panchphula chore bhilapar | New | 0 | 0 | 2024-06-08
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736009026/IF/22012035243284 — nandan phalodhyan panchphula prabhakar thkre | New | 0 | 0 | 2024-06-08
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736009026/IF/22012035249092 — Nandan palodhyan karya prabhakar thakre bairagad | New | 0 | 0 | 2024-06-08
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736009026/IF/22012035291801 — कपिलधारा कुप निरमान कार्य पुंजाराम बंधाने बैरागड | Ongoing | 234473.03 | 0 | 2025-01-30
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736009026/IF/22012035334469 — J G S A 2025 Khet talab nirman karya mahadev chokharam bagde bairagad | Ongoing | 145373.83 | 0 | 2025-04-24
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736009026/IF/22012035608922 — EK BAGIYA MAA KE NAM NUTAN BANDU THAKRE KE KHET ME G P BAIRAGAD | New | 0 | 0 | 2025-08-16
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736009026/IF/22012035608936 — EK BAGIYA MAA KE NAM NUTAN BANDU THAKRE KE KHET ME G P BAIRAGAD | Ongoing | 282843.35 | 12600 | 2025-09-05
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736009026/IF/22012035609234 — ek Bagiya Maa ke naam shanti narate ke khet me Gp bairaghad | New | 0 | 0 | 2025-08-02
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736009026/IF/22012035634722 — EK BAGIYA MA KE NAN JAYMALA MAHADEV BAGDE KE KHET ME G P BAIRAGAD | Ongoing | 283219.2 | 3900 | 2026-02-14
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/4567019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116622145 | Ongoing | 28500 | 0 | 2024-09-27
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/4960694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124956301 | Ongoing | 28500 | 0 | 2025-04-22
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/4963234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126283270 | Approved | 28500 | 0 | 2025-03-03
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/5676956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126626951 | Ongoing | 28500 | 0 | 2025-12-10
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/5825191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127330948 | Approved | 28500 | 0 | 2025-02-21
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/5826359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124826673 | Approved | 28500 | 0 | 2025-02-21
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/5827880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127118107 | Approved | 28500 | 0 | 2025-03-13
SAUSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/5828160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149144623 | Approved | 28500 | 0 | 2025-03-13
SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/6141577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126518429 | Approved | 28500 | 0 | 2026-02-03
SAUSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009026/IF/IAY/6170639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123902389 | Ongoing | 28500 | 6300 | 2026-06-17
SAUSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736009026/IF/VB/22012035663888 — EK BAGIYA MAA KE NAM PRATIBHA UMESH KARADMARE KE KHET ME BHILAPAR G P BAIRAGARH | Approved | 287561.42 | 0 | 2026-08-03
SAUSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736009026/IF/VB/YD/22012035664939 — EK BAGIYA MAA KE NAM PRATIBHA UMESH KARADMARE BHILAPAR G P BAIRAGAD | New | 0 | 0 | 2026-04-14
SAUSAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736009026/RC/22012034673502 — c c road | New | 0 | 0 | 2023-10-02
SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736009026/WC/22012035289805 — JGSA 2025 Dug well Recharge pit nirman karya govinda kardmare ke khet me bhilapar | New | 0 | 0 | 2025-04-14