## Work List
Exported on: 2026-10-18 18:46:15
Filters applied:
Data source: VBGRAMG
District: CHHINDWARA
Block: All
Panchayat: KADEIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BICHHUA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1736010027/DP/22012034621900 — सामुदायिक पौधा रोपण निर्माण कार्य ग्राम पंचायत कढैया ग्राम देनी शामसान घाट के पास | Ongoing | 173305.98 | 5512.27 | 2024-07-12
BICHHUA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1736010027/DP/22012034624081 — सामुदायिक पौधा रोपण निर्माण कार्य ग्राम पंचायत कढैया ग्राम देनी पिपर घौंढढी पहाड टावर के पास | Ongoing | 588193.71 | 48707.97 | 2024-07-19
BICHHUA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1736010027/IC/22012034887947 — Samudayik Sichayi Koop Gram Kadeiya | Approved | 588165.42 | 0 | 2024-11-15
BICHHUA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736010027/IF/22012035610480 — Ek Bagiya Ma Ke Naam Girja Salame/Ghanshyam Salame GP Kadhaiya Gram Kadhaiya | Ongoing | 277406.25 | 14388.04 | 2025-09-05
BICHHUA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736010027/IF/22012035610504 — Ek Bagiya Ma Ke Naam Ramakbati/Fulchand Uikey GP Kadhaiya Gram Deni | Ongoing | 277406.25 | 15415.71 | 2025-09-06
BICHHUA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736010027/IF/IAY/4013660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119651322 | Approved | 28500 | 0 | 2022-05-06
BICHHUA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736010027/IF/IAY/5312686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105365854 | Approved | 28500 | 0 | 2025-03-27
BICHHUA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736010027/IF/IAY/5830540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105371526 | Ongoing | 28500 | 0 | 2025-09-29
BICHHUA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1736010027/WC/22012035158491 — conture tranch nirman | New | 0 | 0 | 2023-10-02
BICHHUA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736010027/WC/VB/22012035330743 — Contour Trench Nirman Kary Gram Kadhaiya GP Kadhaiya Shobhelal Ke Khet Ke Pas | Ongoing | 628655.42 | 77892.23 | 2026-09-18
BICHHUA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736010027/WC/VB/22012035330800 — Contour Trench Nirman Kary Gram Deni GP Kadhaiya Bhaurav Godane Ke Khet Ke Pas | Ongoing | 611016.83 | 148954.35 | 2026-09-04
BICHHUA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1736/WC/22012035313351 — Phase 2 Naveen Amrit Sarovar Kamalsingh ke Khet pas Kadhaiya | Ongoing | 3981000 | 0 | 2025-06-08