## Work List
Exported on: 2026-10-23 23:27:56
Filters applied:
Data source: VBGRAMG
District: BALAGHAT
Block: All
Panchayat: MOHGAON BO
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
LALBARRA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1738003016/AV/22012034651805 — AGANVADI BHAWAN NIRMAN KARYA BARGHAT | Physically Completed | 312000 | 0 | 2024-02-03 | 2026-08-05
LALBARRA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1738003016/FP/22012034638084 — Kachchi Nali Nirman work Mohgaon | New | 0 | 0 | 2024-01-24
LALBARRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/2446484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2163808 | Approved | 28500 | 0 | 2020-05-04
LALBARRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/2459375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3421901 | Approved | 28500 | 0 | 2020-05-04
LALBARRA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/2467574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3483394 | Approved | 28500 | 0 | 2020-05-04
LALBARRA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3326334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4076931 | Ongoing | 28500 | 0 | 2022-04-05
LALBARRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3481051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1818494 | Approved | 28500 | 0 | 2022-01-01
LALBARRA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3533245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4506713 | Ongoing | 28500 | 0 | 2022-05-15
LALBARRA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3556257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4954605 | Ongoing | 28500 | 0 | 2022-05-27
LALBARRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3584931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5410393 | Approved | 28500 | 0 | 2022-01-06
LALBARRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3634582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3358750 | Approved | 28500 | 0 | 2022-01-15
LALBARRA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3636570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4897694 | Ongoing | 28500 | 0 | 2022-05-27
LALBARRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3637440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5323455 | Approved | 28500 | 0 | 2022-01-15
LALBARRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/3637528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5359775 | Approved | 28500 | 0 | 2022-01-15
LALBARRA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/4317499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120589877 | Ongoing | 28500 | 0 | 2022-08-30
LALBARRA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/4352861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127138372 | Approved | 28500 | 0 | 2022-08-21
LALBARRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/4783195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126513855 | Approved | 28500 | 0 | 2024-10-09
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6123023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120280910 | Ongoing | 28500 | 7200 | 2026-04-15
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6125312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126293560 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6128258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121402913 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6128261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121403584 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6128264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121405922 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6128265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121407367 | Physically Completed | 28500 | 24300 | 2026-07-10 | 2026-09-13
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6129893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124109161 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6129997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126840996 | Physically Completed | 28500 | 4800 | 2026-05-19 | 2026-09-13
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6130195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126846593 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6134861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126862385 | Ongoing | 28500 | 0 | 2026-04-15
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6136677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126844772 | Physically Completed | 28500 | 12000 | 2026-05-19 | 2026-09-13
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6136827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126103119 | Ongoing | 28500 | 0 | 2026-04-15
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6138761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123868496 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6138762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123869155 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6138804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126847569 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6140243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126471858 | Ongoing | 28500 | 12900 | 2026-08-21
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6142562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126845665 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6143529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124547394 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6143531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124548986 | Ongoing | 28500 | 2400 | 2026-05-13
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6151108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124109603 | Ongoing | 28500 | 0 | 2026-04-15
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6151475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127104716 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6153906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126829625 | Ongoing | 28500 | 9900 | 2026-05-30
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6154312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126983291 | Ongoing | 28500 | 11400 | 2026-06-03
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6154827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121394821 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6155361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121400647 | Physically Completed | 28500 | 9900 | 2026-05-30 | 2026-09-13
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6155789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126849186 | Physically Completed | 28500 | 21000 | 2026-06-15 | 2026-10-04
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6158169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126297640 | Ongoing | 28500 | 0 | 2026-04-15
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6167411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123781452 | Ongoing | 28500 | 0 | 2026-05-04
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6167591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127104050 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6167939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124471498 | Ongoing | 28500 | 0 | 2026-04-15
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6169952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126860842 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6172339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121410246 | Ongoing | 28500 | 4200 | 2026-05-19
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6172520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126827394 | Physically Completed | 24795 | 0 | 2026-04-15 | 2026-07-19
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6174288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126876647 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6174339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121406378 | Approved | 28500 | 0 | 2026-02-11
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003016/IF/IAY/6174848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124110047 | Physically Completed | 24795 | 0 | 2026-04-15 | 2026-07-26
LALBARRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1738003016/WC/22012035328954 — Barghat Talab Me Fishing Pond Nirman Kary Part 2 | Approved | 467428.96 | 0 | 2025-11-27