## Work List
Exported on: 2026-10-22 23:15:37
Filters applied:
Data source: VBGRAMG
District: BALAGHAT
Block: All
Panchayat: ATRI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
LALBARRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1738003057/IF/22012035278711 — KAPILDHARA KUP NIRMAN KARY DALVAN/NANDLAL ATRI | Approved | 0 | 0 | 2024-12-14
LALBARRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1738003057/IF/22012035285297 — KAPILDHARA KUP NIRMAN KARY DIPENDRA /SOHANAL ATRI | Approved | 0 | 0 | 2024-10-02
LALBARRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1738003057/IF/22012035285299 — KAPILDHARA KUP NIRMAN KARY ISHWARY/DESHIRAM | New | 0 | 0 | 2024-10-02
LALBARRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1738003057/IF/22012035285302 — KAPILDHARA KUP NIRMAN KARY KAMLA/DESHIRAM ATRI | Approved | 0 | 0 | 2024-10-02
LALBARRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1738003057/IF/22012035523314 — Khet talab bhiv/eshulal atri | Approved | 136363.19 | 0 | 2025-04-14
LALBARRA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/2313882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4229344 | Ongoing | 28500 | 0 | 2019-10-30
LALBARRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/3561639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5042863 | Approved | 28500 | 0 | 2022-01-03
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6086392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125541737 | Physically Completed | 24795 | 0 | 2026-05-04 | 2026-08-10
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6089574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127154795 | Completed | 24795 | 8613 | 2026-05-04 | 2026-10-16
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6089605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127167785 | Completed | 28500 | 8874 | 2026-05-04 | 2026-10-16
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6089609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127169273 | Completed | 28500 | 9135 | 2026-05-04 | 2026-10-16
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6089753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127237604 | Ongoing | 28500 | 0 | 2026-05-04
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6089817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127277990 | Physically Completed | 24795 | 0 | 2026-05-04 | 2026-08-10
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6127173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127140901 | Ongoing | 28500 | 0 | 2026-05-04
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6130520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127151630 | Physically Completed | 24795 | 0 | 2026-05-04 | 2026-08-10
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6131137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127223622 | Completed | 28500 | 7569 | 2026-05-04 | 2026-10-16
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6134218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127742044 | Ongoing | 28500 | 0 | 2026-05-04
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6138956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127302354 | Physically Completed | 24795 | 0 | 2026-05-04 | 2026-08-10
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6144493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127159471 | Ongoing | 28500 | 0 | 2026-10-16
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6144495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127161879 | Physically Completed | 24795 | 0 | 2026-05-04 | 2026-08-10
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6148941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127164573 | Completed | 28500 | 9135 | 2026-05-04 | 2026-10-16
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6153524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145080598 | Ongoing | 28500 | 0 | 2026-05-04
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6166677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127348495 | Completed | 24795 | 13050 | 2026-05-04 | 2026-10-16
LALBARRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6174266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124710908 | Completed | 28500 | 5220 | 2026-05-04 | 2026-10-16
LALBARRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738003057/IF/IAY/6390348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124714745 | Approved | 28500 | 0 | 2025-03-03
LALBARRA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1738003057/RS/22012035132250 — Kachhi nali nirman Shivmandir Se Ghisri Nadi Tak Kacchi Nali Nirman Kary Atri | Approved | 99968.67 | 0 | 2024-09-26
LALBARRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1738003057/WC/22012035202943 — Nala Jidnodhaar Kary Bharat Khet Se Noharsingh Pardhi Ke Khet Tak | Approved | 48838.37 | 0 | 2024-04-14
LALBARRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1738003057/WC/22012035235977 — Percolation tank nirman flaudyan ke pas part 2 | Approved | 199660.52 | 0 | 2024-04-14
LALBARRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1738003057/WC/22012035235978 — Percolation tank nirman flaudyan me purane tank ke pass | Approved | 198900.3 | 0 | 2024-04-14
LALBARRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1738003057/WC/22012035249688 — Percolation tank nirman shed ke pass Atri | Approved | 192586.05 | 0 | 2025-01-02
LALBARRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1738003057/WC/22012035249689 — Percolation tank shed ke piche Atri | Approved | 192586.05 | 0 | 2025-01-02
LALBARRA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1738003057/WC/VB/22012035334105 — Construction of Recharge Pits for Community 1 | Ongoing | 20042.02 | 600 | 2026-09-04