## Work List
Exported on: 2026-09-06 09:06:45
Filters applied:
Data source: VBGRAMG
District: BALAGHAT
Block: All
Panchayat: BADGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PARASWADA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1738008012/AV/22012034619064 — Anganbadi bhavan nakatola badgaon | Ongoing | 500000 | 0 | 2022-09-23
PARASWADA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1738008012/IF/22012034993704 — plantation karya gorelal / holu badgaon | Ongoing | 222216.11 | 0 | 2022-08-31
PARASWADA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1738008012/IF/22012034993716 — plantation karya premsingh /jethu salhe | Ongoing | 222216.11 | 0 | 2022-10-13
PARASWADA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1738008012/IF/22012035141479 — Plantation work (Himat singh/Mukam singh)Dorli | Ongoing | 230818.75 | 0 | 2023-09-14
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035164897 — Kapildhara koop Nirman karya Hiresingh /nagarchi dorli | Ongoing | 256074.55 | 0 | 2024-06-22
PARASWADA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1738008012/IF/22012035240479 — thansing/ptiram nandan falodhyan | Approved | 173308.58 | 0 | 2024-04-14
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035282763 — Laghu Talab Indal singh / Jeevan | Approved | 399422.26 | 0 | 2024-08-15
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035282765 — Laghu Talab Suraj / Sarvanlal | Approved | 0 | 0 | 2024-08-15
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035282767 — Laghu Talab Melsingh/ Lalsingh | Approved | 399422.26 | 0 | 2024-08-15
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035523048 — Khet Talab Nirman Rajendra/Dharamsingh | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035523061 — Khet Talab Karya Hanslal/Suklal | New | 0 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035523081 — Khet Talab Karya Hanslal/Suklal | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035547944 — Khet Talab Karya Sumitra/Durgesh Badgaon | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035549140 — Khet Talab karya Ganesh/Bhagatsingh Badgaon | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035549150 — Khet Talab karya Sonu/Holu Badgaon | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035549159 — Khet Talab karya Govind/Sukhlal Badgaon | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035549179 — Khet Talab karya Somabti/Ajabsingh Badgaon | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035549188 — Khet Talab karya Sundrobai/Thamarsingh Badgaon | Approved | 147621.16 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568508 — Kapildhara kup Nirman Karya Surendra/Dhalsingh | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568513 — Kapildhara kup Nirman Karya Jaypal/Kattu | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568516 — Kapildhara kup Nirman Karya Rajpal/Kattu | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568519 — Kapildhara kup Nirman Karya Gyansingh/Omkar | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568521 — Kapildhara kup Nirman Karya Jhamsingh/Baisaku | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568526 — Kapildhara kup Nirman Karya Ranjeet/Chamrasingh | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568529 — Kapildhara kup Nirman Karya Sukhram/Suraj | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568537 — Kapildhara kup Nirman Karya Charansingh/Kashiram | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568542 — Kapildhara kup Nirman Karya Rajesh/Chandan | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568556 — Kapildhara kup Nirman Karya Manglusingh/Gorelal | Approved | 0 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568557 — Kapildhara kup Nirman Karya Suman/Jagu | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738008012/IF/22012035568614 — KapilDhara Kup Nirman Karya Himmatsingh Uikey | Approved | 327631.47 | 0 | 2025-04-14
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035574904 — Khet Talab Karya Poharsingh/Shobharam | Ongoing | 55865.38 | 0 | 2025-06-26
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035575398 — Khet Talab Karya Santosh/Mohan | Ongoing | 60353.81 | 0 | 2025-06-26
PARASWADA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738008012/IF/22012035575448 — khet talab Kishan / Jagat | Ongoing | 55865.38 | 0 | 2025-06-26
PARASWADA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/2665310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4122853 | Ongoing | 28500 | 0 | 2021-04-08
PARASWADA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/3316623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4957968 | Approved | 28500 | 0 | 2021-11-02
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4462513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151782061 | Ongoing | 28500 | 0 | 2024-05-19
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4542153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106070828 | Ongoing | 28500 | 0 | 2024-12-20
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4583139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119969470 | Ongoing | 28500 | 0 | 2025-03-25
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4585654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119664103 | Ongoing | 28500 | 0 | 2025-03-25
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4585657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119665847 | Ongoing | 28500 | 0 | 2025-03-25
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4761750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119969895 | Ongoing | 28500 | 0 | 2025-03-24
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4898270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152057069 | Ongoing | 28500 | 0 | 2025-03-24
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4908077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106326932 | Ongoing | 28500 | 0 | 2025-03-25
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4911049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119972119 | Ongoing | 28500 | 0 | 2025-03-24
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4911050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119972309 | Ongoing | 28500 | 0 | 2025-03-24
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/4911051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119974182 | Ongoing | 28500 | 0 | 2025-03-24
PARASWADA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738008012/IF/IAY/5297695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106326996 | Approved | 28500 | 0 | 2025-01-25
PARASWADA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738008012/RC/22012034676470 — gp badgaon me baigatola me cc sadak nirman | New | 0 | 0 | 2024-01-24
PARASWADA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738008012/RC/22012034836845 — Gulchand Ke Ghar Se Aama Talab Tak Nalli Nirman karya | Ongoing | 120900 | 0 | 2025-04-11
PARASWADA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738008012/RC/22012034836851 — CC Sadak Nirman karya Imlitola | Approved | 278000 | 0 | 2025-02-19
PARASWADA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1738008012/RS/22012034389503 — toilet nirman work tilok /fagulal | Ongoing | 9800 | 0 | 2018-01-21
PARASWADA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1738008012/WC/22012035070128 — nirmal neer koop nirman karya ward-10 dorli | Ongoing | 224266.55 | 0 | 2024-06-17
PARASWADA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1738008012/WC/22012035210464 — gram salai nala par stop dam nirman karya | Approved | 1496321.42 | 0 | 2024-04-14
PARASWADA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1738008012/WC/22012035278427 — Basantray uikey ke ghar ke same kup me rechage pit Salhe | Approved | 0 | 0 | 2025-04-14
PARASWADA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1738008012/WC/22012035279765 — JGSA consterction of Rechage fit bharet ka ghar ka pass | Approved | 0 | 0 | 2025-04-22
PARASWADA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1738008012/WC/22012035283501 — Thansingh ke ghar ke samne kup ke pas recharge pit Baigatola Badgaon | Approved | 0 | 0 | 2025-04-24
PARASWADA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1738008012/WC/22012035311210 — Jungle road ke baju me Borwell Recharge pit Badgaon | Approved | 25899.46 | 0 | 2025-04-14
PARASWADA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1738008012/WC/22012035311237 — Mansingh Itwari Ke ghar ke pas Borwell recharge pit | Approved | 25899.46 | 0 | 2025-04-14
PARASWADA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1738008012/WC/22012035311779 — Stag ke pas Borewell Recharge pit Dorli | Approved | 25899.46 | 0 | 2025-04-14
PARASWADA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1738008012/WC/22012035311783 — Dinesh Parte ke ghar ke Borewell Recharge pit Badgaon | Approved | 25899.46 | 0 | 2025-04-14
PARASWADA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1738008/DP/22012034557814 — van bhumi par bans vrakchharopan badgaon 1294 | Ongoing | 2101000 | 0 | 2022-07-02