## Work List
Exported on: 2026-10-20 05:51:42
Filters applied:
Data source: VBGRAMG
District: BALAGHAT
Block: All
Panchayat: AMEDA(P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
LANJI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1738010072/IF/IAY/108805 — Construction of IAY House -IAY REG. NO. MP-38-010-072-001/7808 | Approved | 28500 | 0 | 2015-10-05
LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738010072/IF/IAY/5713246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148476285 | Approved | 28500 | 0 | 2025-01-30
LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738010072/IF/IAY/5909247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148476574 | Approved | 28500 | 0 | 2025-01-30
LANJI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1738010072/RC/22012034640204 — AMEDA PA BHAUDAS KE MAKAN SE AMRIT SAROVAR TAK SUDUR SADAK NIRMAN | Physically Completed | 1494748.81 | 0 | 2023-06-12 | 2026-07-29
LANJI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1738010072/RC/22012034676513 — Ameda (Pa) Mukhya Marg se Rampura Tak Sudur sadak nirman kary | New | 0 | 0 | 2024-01-24
LANJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1738010072/WC/22012035165705 — Ameda (Pa) Water Kantrul Tramch chote ped ke jangal me nirman kary | New | 0 | 0 | 2024-01-24
LANJI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1738010072/WC/VB/22012035330135 — AMEDA PA BALWANT RAO KE KHET KE PAS STAGGERED TRENCH NIRMAN | Ongoing | 201335.8 | 41900 | 2026-08-03
LANJI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1738/DP/22012034490123 — Ameda P नर्सरी स्‍थापना | Ongoing | 5034408 | 0 | 2020-07-07