## Work List
Exported on: 2026-09-14 17:21:33
Filters applied:
Data source: VBGRAMG
District: UMARIA
Block: All
Panchayat: AMADONGARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KARKELI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1740002003/DP/22012034491020 — RFR वृक्षा रोपण कार्य घटवईया तालाब के मेड में | Ongoing | 390826.48 | 0 | 2020-08-10
KARKELI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1740002003/DP/22012034558771 — ASA CFT CTR RFR PLANTATION KARYA LITIYA DHAR K PASS GP AMADONGARI | Ongoing | 765431.75 | 0 | 2022-09-12
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740002003/IF/22012035335562 — construction of Farm Pond For Individuals khet talab Jagan singh / boddha k khet me GP Amadongari | New | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740002003/IF/22012035335625 — construction of Farm Pond For Individuals khet talab Jagan singh / boddha k khet me GP Amadongari | New | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035404192 — KAPIL DHARA KOOP NIRMAN KARYA PHUL SINGH K KHET M GP Amadongari | Approved | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035404302 — KAPIL DHARA KOOP NIRMAN KARYA Hari SINGH/ jhagru singh K KHET M GP Amadongari | Approved | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035404376 — KAPIL DHARA KOOP NIRMAN KARYA Maan SINGH/khattu singh K KHET M GP Amadongari | Approved | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035404468 — KAPIL DHARA KOOP NIRMAN KARYA Santosh SINGH/shobh singh K KHET M GP Amadongari | New | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035404572 — KAPIL DHARA KOOP NIRMAN KARYA Santosh singh /shobha singh K KHET M GP Amadongari | Approved | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035404659 — KAPIL DHARA KOOP NIRMAN KARYA Prahlad singh /Raam SINGH K KHET M GP Amadongari | Approved | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035495900 — kapil dhara koop nirman karya Gaytri bai / manrakhan singh k khet m GP Amadongari | Approved | 0 | 0 | 2025-04-14
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002003/IF/22012035521909 — KAPIL DHARA KOOP NIRMAN KARYA JAILAL SINGH /SARJU SINGH K KHET M GP AMADONGARI | Approved | 0 | 0 | 2025-04-14
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740002003/IF/22012035534515 — khet talab nirman karya jai singh /babulal singh k khet m GP Aadongari | Approved | 0 | 0 | 2025-04-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1740002003/IF/22012035650287 — Ek Bagiya Maa ke Naam Ananti bai w/o Suraj Singh ke khet me GP Amadongari | Approved | 0 | 0 | 2025-10-02
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1740002003/IF/22012035651304 — Ek Bagiya Maa ke Naam Yasoda bai w/o Manrakhan singh ke khet me GP Amadongari | Approved | 0 | 0 | 2025-10-02
KARKELI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/34869 — Construction of IAY House -IAY REG. NO. MP-40-002-003-001/32299845 | Approved | 28500 | 0 | 2015-11-16
KARKELI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/34870 — Construction of IAY House -IAY REG. NO. MP-40-002-003-001/36979603 | Approved | 28500 | 0 | 2015-11-16
KARKELI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/4840422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152018712 | Ongoing | 28500 | 0 | 2024-12-07
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/5255095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129506388 | Ongoing | 28500 | 0 | 2025-05-05
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/5403361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129509533 | Ongoing | 28500 | 0 | 2025-05-05
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/5693357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120567438 | Ongoing | 28500 | 0 | 2026-02-01
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/5696824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121570601 | Ongoing | 28500 | 0 | 2025-08-11
KARKELI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002003/IF/IAY/628283 — Construction of IAY House -IAY REG. NO. MP1379192 | Approved | 28500 | 0 | 2017-02-08
KARKELI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1740002003/RC/22012034819159 — CC RODE NIRMAN GANESH K GHAR SE KEHAR KE GHAR KI OR AUR KAMOD KE GHAR SE JAI SINGH K GHAR KI OR | Approved | 0 | 0 | 2024-06-08
KARKELI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1740002003/RC/22012034837700 — cc rode niraman kary mandir pas se hansi bai ke ghar ki our amaongri | Approved | 26000 | 0 | 2024-08-16
KARKELI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1740002003/RS/22012035131528 — Constraction of drainage line kailash singh ke ghar pass s upswasthkendra k pichhe ki or | Approved | 0 | 0 | 2024-08-16
KARKELI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1740002003/RS/22012035131530 — Constraction of drainage line kailash singh ke ghar pass s upswasthkendra k pichhe ki or | Approved | 0 | 0 | 2024-04-14
KARKELI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1740002003/RS/22012035131532 — Constraction of drainage line kailash singh ke ghar pass s upswasthkendra k pichhe ki or | Approved | 22000 | 0 | 2024-09-23
KARKELI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740002003/WC/22012035214420 — Jal Ganga Samvardhaan Abhiyaan Renovetion of maneger talab GP Amadongari | Approved | 387000 | 0 | 2024-06-08
KARKELI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740002003/WC/22012035252426 — parculation tank kunti bai k khet pass GP Amadongari | Approved | 0 | 0 | 2025-01-26
KARKELI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740002003/WC/22012035252428 — parculation tank samharu baiga k khet m jamun pass GP Amadongari | Approved | 0 | 0 | 2025-01-26
KARKELI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740002003/WC/22012035252429 — Talab nirman karya shiv mandir pass chhapra GP Amadongari | Approved | 0 | 0 | 2025-01-26
KARKELI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740002003/WC/22012035252431 — Parculation tank prahlad Singh k khet pass GP Amadongari | Approved | 0 | 0 | 2025-01-26
KARKELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1740002003/WC/VB/22012035330025 — Construction of Bolder check Dam mangal singh k khet pass Nala me GP Amadongari | Approved | 70698.95 | 0 | 2026-07-09
KARKELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1740002003/WC/VB/22012035330033 — Construction of Bolder check Dam lammu baiga aur mangal /buddha ke khet pass Nala me GP Amadongari | Approved | 0 | 0 | 2026-07-09
KARKELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1740002003/WC/VB/22012035330038 — Construction of Bolder check Dam Rakesh singh /dashrath ke khet pass Nala me GP Amadongari | Approved | 70698.95 | 0 | 2026-07-09
KARKELI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1740002003/WC/VB/22012035330042 — Construction of Bolder check Dam Nanda baiga ke khet pass Nala me GP Amadongari | Approved | 70698.95 | 0 | 2026-07-09