## Work List
Exported on: 2026-10-20 02:37:23
Filters applied:
Data source: VBGRAMG
District: UMARIA
Block: All
Panchayat: BARHATA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KARKELI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair & Maintenance of Anganwadi Centre Building for Community | Repair & Maint of Community infrastructure | 1740002012/AV/22012034567456 — Mejar Repairing Of M.S.Bilding Khairbhar AR 2 | Ongoing | 116000 | 0 | 2021-06-29
KARKELI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1740002012/AV/22012034567474 — Mejar Repairing Of M.S. Khairbhar | Ongoing | 196000 | 0 | 2021-06-29
KARKELI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1740002012/AV/22012034567478 — Mejar Repairing Of P.S. Hardua | Ongoing | 40000 | 0 | 2021-06-29
KARKELI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1740002012/AV/22012034567480 — Anganwadi Bhavan Repaier Karya Hardua | Ongoing | 48000 | 0 | 2021-06-29
KARKELI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1740002012/AV/22012034567481 — Anganwadi Bhavan Repaier Karya Khairbhar | Ongoing | 48000 | 0 | 2021-06-29
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1740002012/IF/22012035362236 — खेत तालाब निर्माण कार्य अजमेर/शम्भु बैगा | Ongoing | 399520.91 | 0 | 2025-04-22
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1740002012/IF/22012035382901 — डग बेल रिचार्ज हितग्राही Pandu singh | Ongoing | 25899.46 | 0 | 2025-04-26
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1740002012/IF/22012035382931 — डग बेल रिचार्ज हितग्राही Surendra singh | Ongoing | 25899.46 | 0 | 2025-04-26
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1740002012/IF/22012035383067 — डग बेल रिचार्ज हितग्राही Gopi singh | Ongoing | 25899.46 | 0 | 2025-04-26
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1740002012/IF/22012035383120 — डग बेल रिचार्ज हितग्राही Dilbahar singh | Ongoing | 25899.46 | 0 | 2025-04-26
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1740002012/IF/22012035383465 — डग बेल रिचार्ज हितग्राही Vishmbhar singh | Ongoing | 25899.46 | 0 | 2025-04-26
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1740002012/IF/22012035383510 — डग बेल रिचार्ज हितग्राही Jaymangal singh | Ongoing | 25899.46 | 0 | 2025-04-26
KARKELI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740002012/IF/22012035540207 — JGSA2025 RECHARGE STRUCHTER Pandu singh | Ongoing | 25899.46 | 0 | 2025-05-23
KARKELI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740002012/IF/22012035540238 — JGSA2025 RECHARGE STRUCHTER Gopi singh | Ongoing | 25899.46 | 0 | 2025-05-23
KARKELI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740002012/IF/22012035540258 — JGSA2025 RECHARGE STRUCHTER Dilbahar singh | Ongoing | 25899.46 | 0 | 2025-05-23
KARKELI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740002012/IF/22012035540276 — JGSA2025 RECHARGE STRUCHTER Surendra singh | Ongoing | 25899.46 | 0 | 2025-05-23
KARKELI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740002012/IF/22012035540298 — JGSA2025 RECHARGE STRUCHTER Vishambhar baiga | Ongoing | 25899.46 | 0 | 2025-05-23
KARKELI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740002012/IF/22012035540316 — JGSA2025 RECHARGE STRUCHTER Jaymangal singh | Ongoing | 25899.46 | 0 | 2025-05-23
KARKELI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740002012/IF/22012035540336 — JGSA2025 RECHARGE STRUCHTER Dilraj singh | Ongoing | 25899.46 | 0 | 2025-05-23
KARKELI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Well for Individual | Construction of Well | 1740002012/IF/9993728038 — HITESI KAPILDHARA /KHET TALAAB NIRMAN DEENA /MANTA KOL | Ongoing | 230000 | 0 | 2017-02-06
KARKELI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/4265110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116745883 | Ongoing | 28500 | 0 | 2025-03-02
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/4859741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100460356 | Ongoing | 28500 | 0 | 2025-10-24
KARKELI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/4868013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131605441 | Ongoing | 28500 | 0 | 2025-03-02
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/5458337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116125173 | Ongoing | 28500 | 0 | 2025-09-14
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/5458341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116126610 | Physically Completed | 28500 | 0 | 2025-09-19 | 2026-09-20
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/5628299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116124936 | Ongoing | 28500 | 0 | 2025-08-03
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/5695743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152094864 | Ongoing | 28500 | 0 | 2025-08-03
KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/5783252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152095804 | Ongoing | 28500 | 0 | 2025-10-24
KARKELI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740002012/IF/IAY/6302919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131605364 | Ongoing | 28500 | 0 | 2026-10-13
KARKELI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1740002012/RC/22012034377403 — सी सी रोड नि‍माण कार्य बधवाटोला मुख्‍य मार्ग से चैन ि‍संह के घर तक | Ongoing | 85000 | 0 | 2021-03-14
KARKELI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1740002012/RC/22012034646477 — सी.सी. रोड निर्माण लोटन सिंह के घर से लाल सिंह के घर तक हरदुआ | Ongoing | 54000 | 0 | 2023-10-05
KARKELI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1740002012/RC/22012034681565 — सी सी रोड निर्माण कार्य सूर्य भान सिंह के घर से जगदीश बारी के घर तक ग्राम हरदुआ ग्राम पंचायत बरहटा | Ongoing | 69000 | 25740 | 2024-03-12
KARKELI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1740002012/RC/22012034683542 — C C ROD NIRMAD KARY RAKESH KOL KE GHAR SE RAM VISHAL KE GHAR TAK HARDUA | Ongoing | 54000 | 0 | 2024-03-16
KARKELI | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair & Maintenance of Flood or Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1740002012/WC/22012034868989 — तालाब विस्तारीकरण कार्य रामशरण केवट के घर के पीछे बरहटा | Ongoing | 525550.91 | 0 | 2022-02-15
KARKELI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1740002012/WC/22012034944201 — पूरनहा हार तालाब विस्तारीकरण बरहटा | Ongoing | 559923.02 | 0 | 2024-03-16