## Work List
Exported on: 2026-09-05 00:54:43
Filters applied:
Data source: VBGRAMG
District: UMARIA
Block: All
Panchayat: KHICHKADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PALI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1740003017/AV/22012034594112 — बाउंड्रीबाल निर्माण m/s केलहारी | Ongoing | 380000 | 0 | 2021-11-24
PALI | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1740003017/AV/22012034609865 — segrigresion nirman kary gram chorha | Ongoing | 400414.39 | 0 | 2022-01-14
PALI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1740003017/DP/22012034423561 — BRACHCHHA ROPAN NIRMAN KHEL MAIDAN KHICHKIDI | Ongoing | 342000 | 0 | 2018-09-05
PALI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740003017/IF/22012034333647 — खेत तालाब सह कपिल धारा कूप निर्माण कार्य हितग्राही भूरा सिंह पिता श्री कंशे सिंह | Ongoing | 230000 | 0 | 2017-05-05
PALI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1740003017/IF/22012034440035 — कपिल धारा निर्माण कार्य हितग्राही शिवलाल सिंह /बाबूलाल सिंह | Ongoing | 235000 | 0 | 2019-02-13
PALI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Brushwood Check Dam for Individuals / Construction of Brushwood Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1740003017/IF/22012034440039 — कपिलधारा निर्माण कार्य हितग्राही रामलाल सिंह /पाढू सिंह | Ongoing | 235000 | 0 | 2018-12-18
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1740003017/IF/22012035361916 — JGSA Kup Richarag santosh baga ke ghar pass khichkidi | New | 0 | 0 | 2025-04-05
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1740003017/IF/22012035362053 — JGSA Kup Richarag santosh baga ke ghar pass khichkidi | New | 0 | 0 | 2025-04-05
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1740003017/IF/22012035362346 — JGSA Kup Richarag pit bhola singh khichkidi | Ongoing | 25899.46 | 0 | 2025-04-28
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740003017/IF/22012035512973 — JGSA khet talab nirman hitgrahi bhagvandas Singh/Ramkaran Singh | Ongoing | 383846.73 | 0 | 2025-05-16
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1740003017/IF/22012035629169 — ek Bagiya maa ke nam hitgrahi phool bai khichkidi | Ongoing | 192132.16 | 0 | 2026-01-02
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1740003017/IF/22012035629174 — ek Bagiya maa ke nam hitgrahi bunda bai khichkidi | Ongoing | 192132.16 | 0 | 2025-12-23
PALI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/1130878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2398578 | Approved | 28500 | 0 | 2017-05-13
PALI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/2038427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2338153 | Approved | 28500 | 0 | 2019-06-25
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/2306346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1480846 | Ongoing | 28500 | 0 | 2026-03-12
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5637296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010760 | Ongoing | 28500 | 0 | 2025-11-03
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5637352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151987991 | Ongoing | 28500 | 0 | 2025-12-23
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5637486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151972606 | Ongoing | 28500 | 0 | 2025-12-23
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5637487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151891530 | Ongoing | 28500 | 1560 | 2025-10-16
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5637493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151891493 | Ongoing | 28500 | 0 | 2025-10-16
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5637513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151891570 | Ongoing | 28500 | 0 | 2025-10-16
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5792468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151966857 | Ongoing | 28500 | 0 | 2026-06-05
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5792753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151966882 | Ongoing | 28500 | 0 | 2025-09-23
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003017/IF/IAY/5792754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151966896 | Ongoing | 28500 | 1560 | 2025-12-23
PALI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1740003017/RS/22012034606822 — Nadep nirman kary Govind singh ke ghar pass chorha | Ongoing | 18044.24 | 0 | 2022-01-13
PALI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boulder Check / Construction of Boulder Check Dam for Community | Boulder Check/Gully Plug | 1740003017/WC/22012034379301 — रपटा दूबी नाला कार्य निर्माण ग्राम खिचकिड़ी | Ongoing | 210000 | 0 | 2018-04-10
PALI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1740003017/WC/22012034379433 — चुरहा नाला स्टाप डेम निर्माण कार्य ग्राम खिचकिड़ी | Ongoing | 277000 | 0 | 2018-04-10
PALI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1740003017/WC/22012034440551 — W.H.T talab nirman kelhari shobha singh ke khet pass | Ongoing | 1366000 | 0 | 2019-03-06
PALI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1740003017/WC/22012034503843 — WHT nirman medha tola badvahi | Ongoing | 1491711.79 | 0 | 2019-12-16
PALI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1740003017/WC/22012035041611 — परकुलेशन टैंक निर्माण गोड्डा नाला बडवाही | Ongoing | 1456460.11 | 0 | 2023-02-03
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740003017/WC/22012035204478 — Takur baba talab gahari karan kelhari | Approved | 0 | 0 | 2024-06-06
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740003017/WC/22012035204497 — Vidala talab gahari Khichkidi | New | 0 | 0 | 2024-06-06
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1740003017/WC/22012035249423 — स्टॉप डेम निर्माण कार्य कोलूहरू नाला खिचकिडी | Approved | 0 | 0 | 2025-01-20
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1740003017/WC/22012035249433 — स्टॉप डेम निर्माण कार्य कोलूहरू नाला खिचकिडी | Ongoing | 323000 | 0 | 2025-03-10
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1740003017/WC/22012035250325 — Stap Dem nirman kary koluharu nala khichkidi | Approved | 0 | 0 | 2024-08-16
PALI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1740/RC/22012034343984 — सी.सी. रोड निर्माण भूपत सिंह के घर से सामुदायिक भवन तक चोरहा | Ongoing | 1124000 | 0 | 2017-10-26
PALI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1740/RC/22012034612151 — Regravelling | Ongoing | 439000 | 0 | 2024-03-09