## Work List
Exported on: 2026-09-10 09:25:50
Filters applied:
Data source: VBGRAMG
District: UMARIA
Block: All
Panchayat: MUDARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PALI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1740003027/IF/22012034646686 — Construction Of Kapil Dhara Koop Nirman Sanskali / Mahendra | Ongoing | 263855.24 | 753 | 2021-11-11
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740003027/IF/22012035297340 — CONSTRUCTION OF KAPILDHARA KOOP NIRMAN KARYA DEENDAYAL SINGH DADDI SINGH MUDARIA | New | 0 | 0 | 2025-01-10
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740003027/IF/22012035326703 — CONSTRUCTION OF KAPILDHARA KOOP NIRMAN KARYA DEENDAYAL SINGH DADDI SINGH MUDARIA | Ongoing | 300141.99 | 0 | 2025-05-22
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740003027/IF/22012035362543 — KHET TALAB NIRMAN KARYA HITGRAHI KAMAL SINGH/BHURA SINGH | Ongoing | 392887.25 | 0 | 2025-05-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740003027/IF/22012035362581 — KHET TALAB NIRMAN KARYA HITGRAHI RAMRATAN SINGH/RANMAT SINGH | Ongoing | 396676.59 | 0 | 2025-05-14
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740003027/IF/22012035421924 — CONSTRUCTION OF PASHU SED NIRMAN KARYA SANSKALI DEVI | New | 0 | 0 | 2025-04-20
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740003027/IF/22012035422037 — CONSTRUCTION OF PASHU SED NIRMAN KARYA SANSKALI DEVI | Approved | 0 | 0 | 2025-04-20
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740003027/IF/22012035483866 — CONSTRUCTION OF KAPILDHARA KOOP NIRMAN KARYA RAJU SINGH LACCHU SINGH MUDARIA | Approved | 0 | 0 | 2025-04-20
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4032276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149289163 | Ongoing | 28500 | 0 | 2023-05-11
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4417555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152006517 | Ongoing | 28500 | 0 | 2025-01-11
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4419342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152007548 | Ongoing | 28500 | 0 | 2024-03-10
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4433837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995535 | Ongoing | 28500 | 0 | 2025-07-28
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4433863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995630 | Ongoing | 28500 | 0 | 2026-01-28
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4433953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151995929 | Ongoing | 28500 | 0 | 2024-03-10
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4441143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151976765 | Ongoing | 28500 | 0 | 2024-03-02
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978829 | Ongoing | 28500 | 0 | 2025-02-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978840 | Ongoing | 28500 | 0 | 2025-04-02
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978842 | Ongoing | 28500 | 0 | 2024-03-02
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978850 | Ongoing | 28500 | 0 | 2026-01-28
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978855 | Ongoing | 28500 | 0 | 2024-06-14
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978932 | Ongoing | 28500 | 0 | 2026-03-18
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978933 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978936 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978937 | Ongoing | 28500 | 0 | 2026-01-04
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978938 | Approved | 28500 | 0 | 2024-01-26
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978941 | Ongoing | 28500 | 0 | 2026-05-14
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978942 | Ongoing | 28500 | 0 | 2026-05-14
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978943 | Ongoing | 28500 | 0 | 2025-03-16
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978944 | Ongoing | 28500 | 0 | 2026-05-14
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978945 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978946 | Ongoing | 28500 | 0 | 2025-04-28
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978948 | Ongoing | 28500 | 0 | 2025-04-28
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978956 | Ongoing | 28500 | 4200 | 2026-05-14
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978961 | Ongoing | 28500 | 0 | 2026-03-16
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978963 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4445676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978964 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4448605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151962292 | Ongoing | 28500 | 0 | 2025-05-26
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981182 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981358 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981483 | Ongoing | 28500 | 0 | 2026-01-02
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981512 | Ongoing | 28500 | 0 | 2025-04-02
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981551 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981632 | Ongoing | 28500 | 0 | 2024-02-13
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981675 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981716 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981800 | Ongoing | 28500 | 0 | 2026-01-02
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4449580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981849 | Ongoing | 28500 | 0 | 2024-03-02
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4457077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152004675 | Ongoing | 28500 | 0 | 2025-04-05
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4459635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151987914 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4461282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981275 | Ongoing | 28500 | 0 | 2024-02-13
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4461353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151984869 | Ongoing | 28500 | 0 | 2025-02-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4464381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151978940 | Ongoing | 28500 | 0 | 2024-05-07
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4466880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152007546 | Ongoing | 28500 | 0 | 2024-03-10
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4466894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014800 | Ongoing | 28500 | 0 | 2024-03-16
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4467149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981584 | Ongoing | 28500 | 0 | 2025-02-05
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4467750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152023868 | Ongoing | 28500 | 0 | 2024-03-09
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4505650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981766 | Ongoing | 28500 | 0 | 2025-08-01
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4506041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017534 | Ongoing | 28500 | 0 | 2025-10-27
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4659108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148832720 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4659514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148162896 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4659700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148211274 | Physically Completed | 24795 | 0 | 2025-01-22 | 2026-08-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4660485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149300661 | Ongoing | 28500 | 0 | 2025-03-19
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4660835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149165489 | Ongoing | 28500 | 0 | 2025-03-19
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4660972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149205891 | Physically Completed | 24795 | 0 | 2025-01-22 | 2026-08-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4661748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148981294 | Ongoing | 28500 | 0 | 2024-10-22
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4661773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149308255 | Ongoing | 28500 | 0 | 2024-10-07
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4662982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149510077 | Ongoing | 28500 | 0 | 2024-10-10
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4663609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149011168 | Ongoing | 28500 | 0 | 2024-10-07
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4663676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149029660 | Ongoing | 28500 | 0 | 2024-10-07
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4665648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150581441 | Ongoing | 28500 | 0 | 2024-10-07
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4834176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147910393 | Ongoing | 28500 | 0 | 2025-01-06
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4834863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149161684 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4835106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149727564 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4836111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149293713 | Ongoing | 28500 | 0 | 2025-01-22
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4867935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147858689 | Ongoing | 28500 | 0 | 2025-03-19
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/4867992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150224439 | Ongoing | 28500 | 0 | 2025-01-06
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5251767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149310449 | Ongoing | 28500 | 0 | 2025-05-27
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5253220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150545690 | Ongoing | 28500 | 0 | 2025-05-27
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5253752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150548497 | Ongoing | 28500 | 0 | 2025-05-27
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5266433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148994335 | Ongoing | 28500 | 0 | 2025-05-26
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5276209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150045922 | Ongoing | 28500 | 0 | 2025-07-20
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5294546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148161149 | Ongoing | 28500 | 1200 | 2025-04-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5303230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148139232 | Ongoing | 28500 | 0 | 2025-07-28
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5311294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150092013 | Ongoing | 28500 | 0 | 2025-07-28
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5318804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149284004 | Ongoing | 28500 | 0 | 2025-04-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5319911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149274135 | Ongoing | 28500 | 0 | 2025-05-26
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5320875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148683373 | Ongoing | 28500 | 0 | 2025-04-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740003027/IF/IAY/5654339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150102406 | Ongoing | 28500 | 0 | 2025-07-17
PALI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1740003027/LD/22012034592649 — JUNGLE CLEANGING SAF SAFAI KARYA MADHU COMPLEX SE REGRICATION KI OUR MUDARI | Ongoing | 24848.8 | 0 | 2023-04-20
PALI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1740003027/RC/22012034681442 — CONSTRUCTION OF GRAVEL ROAD NIRMAN KARYA CHARAN SINGH KE GHAR SE KHER MATA HS SCHOOL MUDARIA | Ongoing | 1969958.82 | 7812 | 2024-03-15
PALI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1740003027/WC/22012035068536 — CONSTRUCTION OF TALAB NIRMAN KARYA KHURAI DONGRI KE PASS | Ongoing | 1499664.69 | 0 | 2023-10-06
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1740003027/WC/22012035157576 — Construction Of Talab Nirman KARI MATI KUMURDU | Ongoing | 1380161.44 | 0 | 2024-12-21
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1740003027/WC/22012035269327 — DUGWELL RECHARGE STRUCTURE MUDARIYA 05 NAG | Approved | 129497.35 | 0 | 2025-04-14
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1740003027/WH/22012034940390 — TALAB JIRNODDHAR JAIKARAN KE KHET KE PASS | Approved | 0 | 0 | 2024-06-08
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1740003027/WH/22012034940392 — TALAB JIRNODDHAR RAM MILAN KALAYAN KHET KE PASS | Approved | 0 | 0 | 2024-06-08