## Work List
Exported on: 2026-10-22 15:13:27
Filters applied:
Data source: VBGRAMG
District: UMARIA
Block: All
Panchayat: PAHDIHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PALI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1740003029/DP/22012034422915 — VRAKSHAROPAS M.S.SCHOOL SE ARJUNI KI OR | Ongoing | 342000 | 0 | 2018-07-22
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Borewell for Individual | Well Recharge | 1740003029/IF/22012035385738 — JGSA कूप रिचार्ज निर्माण कार्य तेता बैगा/बाडई | Approved | 25899.46 | 0 | 2025-04-14
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Borewell for Individual | Well Recharge | 1740003029/IF/22012035385758 — JGSA कूप रिचार्ज निर्माण कार्य श्याम लाल बैगा/सुघई बैगा | Approved | 25899.46 | 0 | 2025-04-14
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1740003029/IF/22012035392503 — JGSA dugwell recharge Jatilal baiga/Rakhana baiga | Ongoing | 25899.46 | 0 | 2025-04-24
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1740003029/IF/22012035417579 — JGSA Khet Talab Arjurni Nohar lal | Approved | 394981.95 | 0 | 2025-04-14
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1740003029/IF/22012035627563 — EK BAGIYA MA KE NAAM GALIYA BAI | Ongoing | 169707.19 | 0 | 2025-10-08
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/2403373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4475899 | Ongoing | 28500 | 0 | 2024-05-07
PALI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/2920762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4956063 | Ongoing | 28500 | 3654 | 2021-04-15
PALI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/3253593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1981446 | Approved | 28500 | 0 | 2020-11-09
PALI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/3898431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149332965 | Approved | 28500 | 0 | 2022-05-03
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/3907728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148391617 | Ongoing | 28500 | 21924 | 2026-08-17
PALI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/3909310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148535717 | Approved | 28500 | 0 | 2022-04-29
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/3909312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148535781 | Ongoing | 28500 | 16704 | 2023-10-28
PALI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/3909761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148569871 | Approved | 28500 | 0 | 2022-05-03
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/3911311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148711598 | Ongoing | 28500 | 0 | 2023-09-19
PALI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4149341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143482962 | Approved | 28500 | 0 | 2022-05-23
PALI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4150922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148904899 | Approved | 28500 | 0 | 2022-05-24
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4205603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148711556 | Ongoing | 28500 | 7308 | 2023-04-13
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4458364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151850633 | Ongoing | 28500 | 0 | 2024-06-07
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4458365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151850848 | Ongoing | 28500 | 5742 | 2024-03-15
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4458378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151853288 | Ongoing | 28500 | 2800 | 2024-08-03
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4458468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151873593 | Ongoing | 28500 | 3654 | 2024-03-15
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4458828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936858 | Ongoing | 28500 | 0 | 2024-06-07
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4458924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151772984 | Ongoing | 28500 | 18270 | 2024-04-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4458994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151774905 | Ongoing | 28500 | 0 | 2024-04-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4459137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151964921 | Ongoing | 28500 | 5742 | 2024-06-07
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4459519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151919622 | Ongoing | 28500 | 14616 | 2025-07-30
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4459789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151992894 | Ongoing | 28500 | 0 | 2024-05-24
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4459791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151992968 | Ongoing | 28500 | 0 | 2026-06-01
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4459796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151993422 | Ongoing | 28500 | 7308 | 2024-09-05
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151952230 | Ongoing | 28500 | 2871 | 2025-07-16
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151954020 | Physically Completed | 28500 | 2088 | 2024-08-03 | 2026-09-13
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151780656 | Ongoing | 28500 | 0 | 2024-04-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151780733 | Physically Completed | 28500 | 2610 | 2024-04-21 | 2026-09-06
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151781199 | Ongoing | 28500 | 14616 | 2024-04-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151781208 | Ongoing | 28500 | 0 | 2024-07-17
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151785653 | Ongoing | 28500 | 7308 | 2024-04-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151787400 | Ongoing | 28500 | 6786 | 2024-04-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151810567 | Ongoing | 28500 | 13050 | 2024-04-21
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151974049 | Ongoing | 28500 | 550 | 2024-03-01
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151974735 | Ongoing | 28500 | 6003 | 2024-03-15
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151980703 | Ongoing | 28500 | 6003 | 2024-08-03
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4460926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151940260 | Ongoing | 28500 | 0 | 2024-03-15
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010304 | Ongoing | 28500 | 0 | 2026-01-30
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014286 | Ongoing | 28500 | 0 | 2025-04-19
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981413 | Ongoing | 28500 | 3654 | 2025-03-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151982217 | Ongoing | 28500 | 0 | 2026-02-18
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151812958 | Ongoing | 28500 | 1000 | 2024-03-15
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151813000 | Ongoing | 28500 | 0 | 2024-09-05
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151813059 | Ongoing | 28500 | 1650 | 2024-03-15
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151813136 | Ongoing | 28500 | 10962 | 2024-08-03
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4461442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151813602 | Ongoing | 28500 | 7308 | 2024-05-07
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151992719 | Ongoing | 28500 | 6003 | 2024-08-03
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151993023 | Ongoing | 28500 | 2871 | 2024-11-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151993229 | Ongoing | 28500 | 0 | 2024-04-04
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151994016 | Approved | 28500 | 0 | 2024-02-17
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152002945 | Ongoing | 28500 | 0 | 2024-11-07
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151974303 | Ongoing | 28500 | 7308 | 2024-07-17
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981319 | Physically Completed | 28500 | 2871 | 2024-11-09 | 2026-09-13
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151985946 | Ongoing | 28500 | 3654 | 2024-04-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151853386 | Ongoing | 28500 | 7308 | 2024-06-07
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4466434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151774461 | Ongoing | 28500 | 2980 | 2024-03-11
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4468038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151981883 | Approved | 28500 | 0 | 2024-02-22
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4483468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151945599 | Physically Completed | 28500 | 0 | 2025-09-06 | 2026-09-06
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4485581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151982049 | Ongoing | 28500 | 2871 | 2025-08-01
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4485603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151984775 | Approved | 28500 | 0 | 2024-01-10
PALI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4487954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151987394 | Approved | 28500 | 0 | 2024-01-10
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4492585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151873449 | Ongoing | 28500 | 0 | 2025-09-06
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4659854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148535380 | Approved | 28500 | 0 | 2024-09-12
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4659989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148574206 | Ongoing | 28500 | 2871 | 2025-03-03
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4660183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148904950 | Physically Completed | 24795 | 0 | 2025-08-04 | 2026-08-09
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4661855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149333359 | Ongoing | 28500 | 3654 | 2025-03-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4661873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149340579 | Ongoing | 28500 | 0 | 2025-11-21
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4662557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148391442 | Approved | 28500 | 0 | 2024-09-12
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4832914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147173815 | Ongoing | 28500 | 0 | 2025-07-30
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4832915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147173989 | Ongoing | 28500 | 0 | 2025-05-17
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4839926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014378 | Ongoing | 28500 | 0 | 2025-11-21
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041178 | Ongoing | 28500 | 1044 | 2025-08-01
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041201 | Ongoing | 28500 | 3654 | 2025-03-03
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041272 | Physically Completed | 28500 | 0 | 2025-07-06 | 2026-09-13
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041286 | Ongoing | 28500 | 3654 | 2025-09-06
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041295 | Ongoing | 28500 | 14616 | 2026-02-18
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041302 | Approved | 28500 | 0 | 2024-09-30
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041607 | Physically Completed | 28500 | 0 | 2026-05-07 | 2026-09-13
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041678 | Approved | 28500 | 0 | 2024-09-30
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041774 | Approved | 28500 | 0 | 2024-09-30
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4842189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041776 | Ongoing | 28500 | 0 | 2025-12-29
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4852506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041293 | Ongoing | 28500 | 0 | 2025-03-19
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/4852507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041304 | Ongoing | 28500 | 7308 | 2025-07-26
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5179454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148711332 | Ongoing | 28500 | 0 | 2025-07-06
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5575580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041309 | Ongoing | 28500 | 2349 | 2025-08-04
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5580103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041294 | Approved | 28500 | 0 | 2024-09-30
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5580104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041301 | Physically Completed | 28500 | 3654 | 2025-07-26 | 2026-09-06
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5580105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041306 | Physically Completed | 28500 | 10962 | 2025-07-26 | 2026-09-06
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5580666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041288 | Ongoing | 28500 | 0 | 2025-09-04
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5580668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041775 | Physically Completed | 28500 | 7308 | 2025-09-06 | 2026-09-06
PALI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/5637840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041381 | Ongoing | 28500 | 5742 | 2025-09-24
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/6276987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147619977 | Approved | 28500 | 0 | 2025-03-11
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/6279110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014373 | Approved | 28500 | 0 | 2026-05-20
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/6279527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041105 | Approved | 28500 | 0 | 2026-05-26
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/6279781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151777013 | Approved | 28500 | 0 | 2026-05-20
PALI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/6302904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152015745 | Approved | 28500 | 0 | 2024-09-30
PALI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1740003029/IF/IAY/6355589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041680 | Approved | 28500 | 0 | 2026-05-26
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1740003029/WC/22012035242823 — तालाब निर्माण का कार्य दया सिंह के खेत पास अर्जुनी | Approved | 0 | 0 | 2024-12-20
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1740003029/WC/22012035268792 — Dugwell Recharge 6 nos | Approved | 155396.83 | 0 | 2025-04-14
PALI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1740003029/WC/22012035268811 — Dugwell Recharge pahadiya Arjuni 1 nos | Approved | 25899.46 | 0 | 2025-04-14
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1740003029/WH/22012034940418 — TALAB JIRDODDHAR PURHANIYA TALAB | Approved | 0 | 0 | 2024-06-08
PALI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1740003029/WH/22012034940420 — TALAB JIRDODDHAR BASTI TALAB | Approved | 0 | 0 | 2024-06-08