## Work List
Exported on: 2026-10-05 01:47:34
Filters applied:
Data source: VBGRAMG
District: NEEMUCH
Block: All
Panchayat: BADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JAWAD | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1741001002/AV/22012034649674 — boundy wall primary school badi | Ongoing | 290600 | 0 | 2023-10-08
JAWAD | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1741001002/AV/22012034661446 — SHANTIDHAM TIN SHED NIRMAN GRAM CHAKSODIZER GP BADI | Approved | 229312.16 | 0 | 2024-10-02
JAWAD | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1741001002/AV/22012034664178 — KHEL MAIDAN NIRMAN GRAM BADI SUTARO KI BADI GP BADI | New | 0 | 0 | 2025-01-27
JAWAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1741001002/DP/22012034627233 — VARSHAROPAN WORK ANKUR UPVAN GRAM BADI NAVIN PANCHAYAT BHAVAN KE PASS GP BADI | Ongoing | 309689.07 | 2700 | 2024-12-03
JAWAD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/4006065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122120524 | Ongoing | 27000 | 0 | 2023-06-25
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/4886615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131103686 | Ongoing | 27000 | 0 | 2025-05-07
JAWAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5008247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119874265 | Approved | 27000 | 0 | 2024-11-08
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5010237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121043689 | Physically Completed | 23490 | 0 | 2025-07-10 | 2026-07-26
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5010633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121765200 | Physically Completed | 23490 | 3600 | 2025-10-17 | 2026-08-09
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5012367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122160447 | Ongoing | 27000 | 3600 | 2025-06-12
JAWAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5013900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118554293 | Approved | 27000 | 0 | 2024-11-08
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5015425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124742815 | Ongoing | 27000 | 1800 | 2026-02-19
JAWAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5017476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124816591 | Ongoing | 27000 | 0 | 2026-05-13
JAWAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5017482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124818866 | Approved | 27000 | 0 | 2025-02-18
JAWAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5083640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126795343 | Approved | 27000 | 0 | 2025-02-18
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5084453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127117324 | Ongoing | 27000 | 0 | 2025-04-09
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5084456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127118057 | Ongoing | 27000 | 0 | 2025-06-12
JAWAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5090968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131105791 | Approved | 27000 | 0 | 2025-02-18
JAWAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5096890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145220086 | Approved | 27000 | 0 | 2025-02-18
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5129597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121042185 | Physically Completed | 23490 | 0 | 2025-10-16 | 2026-08-09
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5306966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126617639 | Ongoing | 27000 | 7200 | 2026-01-03
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5420671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123226696 | Approved | 27000 | 0 | 2025-04-05
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5420796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130929435 | Ongoing | 27000 | 3600 | 2025-12-27
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5421036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126589454 | Approved | 27000 | 0 | 2025-04-05
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5629840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121043224 | Ongoing | 27000 | 0 | 2025-10-17
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5669766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127227423 | Ongoing | 27000 | 3600 | 2025-07-21
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5686622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126602301 | Ongoing | 27000 | 0 | 2026-02-14
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5686724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130929375 | Approved | 27000 | 0 | 2025-06-12
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5889335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118114677 | Approved | 27000 | 0 | 2025-04-14
JAWAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5903158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118529517 | Ongoing | 27000 | 7200 | 2026-08-06
JAWAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5904461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118304349 | Physically Completed | 27000 | 15900 | 2026-07-14 | 2026-09-20
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5905549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131102149 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5906352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131106326 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5907162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131104552 | Ongoing | 27000 | 7200 | 2026-08-09
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5907243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124743499 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5909138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131103974 | Ongoing | 27000 | 0 | 2026-09-12
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5909477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122162588 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5914675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131104493 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5915236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118529565 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5916392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124105444 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5916997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118264157 | Physically Completed | 23490 | 0 | 2026-03-23 | 2026-08-02
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5917156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117195872 | Ongoing | 27000 | 0 | 2026-03-23
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5918986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130928808 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5920993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131104239 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5922880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126767665 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1741001002/IF/IAY/5926620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123840175 | Approved | 27000 | 0 | 2026-02-15
JAWAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741001002/RC/22012034840741 — CC ROAD NIRMAN GRAM CHAKSODIZAR PRAKAS DHAKAD KE MKN SE RAMDEVJI MANDIR KI OR GP BADI | Approved | 84000 | 0 | 2025-01-27
JAWAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1741001002/RC/22012034840747 — CC ROAD NIRMAN GRAM BADI SHAMBHULAL KE MAKAN SE JITMAL KE MAKAN KI OR GP BADI | Approved | 56000 | 0 | 2025-01-27
JAWAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1741001002/RS/22012034561568 — COMPOST PIT NIRMAN GRAM BADI (BADI) | Ongoing | 7000 | 0 | 2021-11-14
JAWAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1741001002/RS/22012034642947 — SAMUDAYIK SVACHHATA PARISAR NIRMAN GRAM BADI(BADI) | Ongoing | 43700 | 0 | 2022-03-05
JAWAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1741001002/WC/22012035172731 — RICHARGE PIT NIRMAN GRAM BADI (BADI | Approved | 18153.63 | 0 | 2024-04-01
JAWAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1741001002/WC/22012035224368 — PERCULATION TANK NIRMAN GRAM CHAKSODIZER GP BADI | Ongoing | 317061.7 | 0 | 2024-12-22