## Work List
Exported on: 2026-09-15 00:08:21
Filters applied:
Data source: VBGRAMG
District: NEEMUCH
Block: All
Panchayat: DARU
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NEEMUCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov bldng premises Blck Plntation-Forestry-Comunty / Block Plantation of Forestry Trees in Government building premises for Community | Plantation | 1741002001/DP/22012034620242 — Plantation Work EGS Shala parisar New Aabadi Daru | Ongoing | 319961.07 | 0 | 2024-07-27
NEEMUCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741002001/IF/22012035428715 — Dugwell Recharge Pit Bhanwar lal S/O Kanhayalal GP Daru Gram Semarda | Approved | 25899.46 | 0 | 2025-04-01
NEEMUCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741002001/IF/22012035428755 — Dugwell Recharge Pit Prakash Chandra S/O Gopal Meena GP Daru | Approved | 25899.46 | 0 | 2025-04-01
NEEMUCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741002001/IF/22012035428783 — Dugwell Recharge Pit Rajendra Singh GP Daru | Approved | 25899.46 | 0 | 2025-04-01
NEEMUCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741002001/IF/22012035428800 — Dugwell Recharge Pit Bhanwar Singh S/O Shambhu Singh Rajput GP Daru | Approved | 25899.46 | 0 | 2025-04-01
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741002001/IF/22012035469605 — Khet talab nirman Mangalsingh Harisingh Daru | New | 0 | 0 | 2025-04-01
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741002001/IF/22012035561458 — Khet Talab Nirman Pratap Singh S/O Keshar Singh GP Daru Gram Semarda | Approved | 55865.38 | 0 | 2025-04-01
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1741002001/IF/22012035647086 — EK Bagiya ma ke name kamla bai regar Daru | Ongoing | 263511.37 | 15900 | 2025-12-03
NEEMUCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/109957 — Construction of IAY House -IAY REG. NO. MP-41-002-001-001/183 | Approved | 27000 | 0 | 2015-10-08
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/4907107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106115357 | Physically Completed | 23490 | 1800 | 2025-06-07 | 2026-08-09
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/4907111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106117953 | Ongoing | 27000 | 0 | 2025-05-17
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/4914794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145828877 | Ongoing | 27000 | 0 | 2025-05-17
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/4992795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106453352 | Ongoing | 27000 | 0 | 2025-06-07
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5097501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145841538 | Physically Completed | 23490 | 4200 | 2025-06-07 | 2026-08-02
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5099690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147275550 | Ongoing | 27000 | 0 | 2025-08-23
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5902964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145402941 | Ongoing | 27000 | 6300 | 2026-07-30
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5906392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106517656 | Ongoing | 27000 | 0 | 2026-08-31
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5911805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145229341 | Ongoing | 27000 | 4200 | 2026-05-14
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5912242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106511054 | Ongoing | 27000 | 4200 | 2026-07-23
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5913300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106518844 | Approved | 27000 | 0 | 2026-02-14
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5914945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145849360 | Ongoing | 27000 | 6300 | 2026-07-13
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5915668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106528859 | Approved | 27000 | 0 | 2026-02-14
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5917882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106109267 | Approved | 27000 | 0 | 2026-02-14
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5918360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145849646 | Approved | 27000 | 0 | 2026-02-14
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5918601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145831295 | Physically Completed | 27000 | 4200 | 2026-06-04 | 2026-09-06
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5918722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145834629 | Ongoing | 27000 | 0 | 2026-06-04
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5920328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113738032 | Approved | 27000 | 0 | 2026-02-14
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5921565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147276263 | Ongoing | 27000 | 4200 | 2026-06-04
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5924530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146827246 | Ongoing | 27000 | 4200 | 2026-07-23
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5926788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106460692 | Ongoing | 27000 | 4200 | 2026-07-17
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5927451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113698834 | Ongoing | 27000 | 0 | 2026-08-31
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5927870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113735174 | Approved | 27000 | 0 | 2026-02-14
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5930158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113732775 | Ongoing | 27000 | 6300 | 2026-07-13
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5949988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106451793 | Ongoing | 27000 | 4200 | 2026-07-23
NEEMUCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5956063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113722073 | Approved | 27000 | 0 | 2026-02-20
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5956535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145830492 | Ongoing | 27000 | 6027 | 2026-06-04
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5959668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145849209 | Ongoing | 27000 | 4200 | 2026-07-17
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5960442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106462797 | Ongoing | 27000 | 4200 | 2026-07-23
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/5961306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106464500 | Ongoing | 27000 | 6300 | 2026-07-13
NEEMUCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002001/IF/IAY/6156348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145401208 | Ongoing | 27000 | 0 | 2026-08-31
NEEMUCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1741002001/WC/22012035173228 — Nirmal nir | New | 0 | 0 | 2024-04-01
NEEMUCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002001/WC/22012035174041 — Check Dam | New | 0 | 0 | 2024-04-01
NEEMUCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741002001/WC/22012035240265 — Parcolathion tank nirman Gram Darukheda Gram Daru | Approved | 0 | 0 | 2024-04-01
NEEMUCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741002001/WC/22012035240580 — Parcolathion Tank Nirman Gram Darukheda Raste par Lalibai Bhil Ke khet ke pas Gram Daru | Ongoing | 199853.88 | 0 | 2025-02-19
NEEMUCH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1741002001/WC/VB/22012035333096 — Roof Top Water harvesting work Samudayik Bhawan Nirman Gram Daru | Approved | 30496.65 | 0 | 2026-08-01